## Contents Page
These statements are the primary sources of information National Highways' performance in accordance with the ORR Monitoring Guidelines1
Notes
- Detailed information regarding efficiency delivery and statement in relation to inflationary impact will be contained in the published National Highways Efficiency Report
- Regional data for 2021-22 has been published on the National Highways website.
Contents
Performance Specification statements
PS1 | Improving safety for all
PS2 | Providing fast and reliable journeys
PS3 | A well maintained and resilient network
PS4 | Delivering better environmental outcomes
PS5 | Meeting the needs of all road users
PS6 | Achieving efficient delivery
Investment Plan statements
IP1 | Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
IP2 | RIS 3 Development Pipeline
IP3 | Designated Funds
IP4 | Renewal Volume Reporting
IP5 | Maintenance Delivery Reporting
Financial Performance statements
F1 | Total income and expenditure
F2 | Regional resource income and expenditure
F2.1 | Resource income and projects expenditure
F2.2 | Analysis of protocols expenditure
F3 | Capital expenditure
F3.1 | Enhancement expenditure
F3.2 | Regional capital income and expenditure
Annual Statement
This report and its contents are taken as the Board’s statement of compliance with National Highway’s Licence and Framework Document obligations. It also confirms that National Highways maintains an effective assurance regime for the expenditure of public money and that its decision making meets the criteria set out in the National Highways Framework Document. This report constitutes National Highways’ annual progress report under clause 6.26 of the Licence. To the best of the Board’s knowledge and belief, having made all reasonable enquiries, the information contained in this document and the accompanying performance monitoring statements is set out appropriately. The Directors’ report was approved by the Board on 30 June 2022 and is signed on their behalf by: Nick Harris, CEO
1 https://www.orr.gov.uk/sites/default/files/om/monitoring-reporting-guidelines-for-highways-england-for-road-period-2.pdf
Note - The Performance and Monitoring Statements 2021-22 has been made available with the publication code PR152/22.

## PS1-Improving safety for all
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS1: Improving safety for all |  |  | For a definition of the metric and parameters for measuring and monitoring safety performance see National Highways’ Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
The number of people killed or seriously injured on the SRN.
Ongoing reduction in the number of people killed or seriously injured on the SRN as reported in STATS19 to support a decrease of at least 50% by the end of 2025 against the 2005-09 average baseline. A +/- variance of 5% each year has been agreed with DfT Road User Safety Division to support this target.
Note: baseline will change each year as adjusted figures are produced
2005-09 baseline | Performance Specification | 3,094 (original)
2,321 (revised)
2015 | Unadjusted | 1,784 (original) | 1,750 (original) | KPI | 34 (original)
| Adjusted | 2,328 (revised) | 2,332 (revised) |  | -4 (revised)
2016 | Unadjusted | 2,005 (original) | 1,678 (original) | KPI | 327 (original)
| Adjusted | 2,263 (revised) | 2,237 (revised) |  | 26 (revised)
2017 | Unadjusted | 1,853 (original) | 1,607 (original) | KPI | 246 (original)
| Adjusted | 2,072 (revised) | 2,142 (revised) |  | -70 (revised)
2018 | Unadjusted | 1,987 (original) | 1,536 (original) | KPI | 451 (original)
| Adjusted | 2,178 (revised) | 2,047 (revised) |  | 131 (revised)
2019 | Unadjusted | 1,948 (original) | 1,464 (original) | KPI | 484 (original)
| Adjusted | 2,060 (revised) | 2,096 (revised) |  | -36 (revised)
2020 | Unadjusted Adjusted | 1,288 (original) 1,397 (revised) | 1,393 (original) 1,875 (revised) | KPI | -105 (original) -478 (revised)
2021 | Adjusted |  |  | KPI | 0
2022 | Adjusted |  |  | KPI | 0
2023 | Adjusted |  |  | KPI | 0
2024 | Adjusted |  |  | KPI | 0
2025 | Adjusted |  |  | KPI | 0
Overall traffic levels on the SRN in 2020 reduced by 25.1% when compared to 2019, however, the number of KSIs reduced by 33.9% For context, there were 115,584 reported casualties in Great Britain in 2020. Of these, 7,873 were on the SRN. This represents a decrease of 36% for the SRN when compared with 25% for all roads nationally. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported. *Please note the adjusted figures are updated in line with the DfT updates and published data so they differ from the previously reported numbers.
PIs
The total number of people killed or injured on the SRN.
Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer.
2015 | Performance Specification | 16375 | N/A | PI | N/A
2016 | Performance Specification | 16233 | N/A | PI | N/A
2017 | Performance Specification | 14225 | N/A | PI | N/A
2018 | Performance Specification | 13380 | N/A | PI | N/A |  | 7988 | 8387 | 16375
2019 | Performance Specification | 12347 | N/A | PI | N/A |  | 7792 | 8441 | 16233
2020 | Performance Specification | 7873 | N/A | PI | N/A |  | 6930 | 7295 | 14225
2021 | Performance Specification |  | N/A | PI | N/A |  | 6507 | 6873 | 13380
2022 | Performance Specification |  | N/A | PI | N/A |  | 1948 | 10399 | 12347
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 shows that all casualties have reduced to 7,873, representing a decrease of 36.2% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The number of non-motorised and motorcyclist users killed or injured on the SRN.
The total number of pedestrian, pedal cyclist, motorcyclist and equestrian casualties on the SRN. Disaggregation will be provided by road user group to assist understanding of the PI but are not considered PIs in their own right.
2015 | Performance Specification | 1160 | N/A | PI | N/A
2016 | Performance Specification | 1170 | N/A | PI | N/A
2017 | Performance Specification | 1050 | N/A | PI | N/A
2018 | Performance Specification | 1036 | N/A | PI | N/A
2019 | Performance Specification | 962 | N/A | PI | N/A
2020 | Performance Specification | 605 | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 reports that the total number of vulnerable road user casualties on the Strategic Road Network has reduced to 605. This represents a decrease of 37% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The number of motorcyclist users killed or injured on the SRN.
2015 | Performance Specification | 849 | N/A | N/A | N/A
2016 | Performance Specification | 864 | N/A | N/A | N/A
2017 | Performance Specification | 760 | N/A | N/A | N/A
2018 | Performance Specification | 785 | N/A | N/A | N/A
2019 | Performance Specification | 694 | N/A | N/A | N/A
2020 | Performance Specification | 404 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in motorcyslist casualties on the SRN from 2019.
The number of cyclists killed or injured on the SRN.
2015 | Performance Specification | 153 | N/A | N/A | N/A
2016 | Performance Specification | 152 | N/A | N/A | N/A
2017 | Performance Specification | 137 | N/A | N/A | N/A
2018 | Performance Specification | 103 | N/A | N/A | N/A
2019 | Performance Specification | 112 | N/A | N/A | N/A
2020 | Performance Specification | 99 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in cyclist casualties on the SRN from 2019.
The number of pedestrians killed or injured on the SRN.
2015 | Performance Specification | 158 | N/A | N/A | N/A
2016 | Performance Specification | 154 | N/A | N/A | N/A
2017 | Performance Specification | 153 | N/A | N/A | N/A
2018 | Performance Specification | 148 | N/A | N/A | N/A
2019 | Performance Specification | 156 | N/A | N/A | N/A
2020 | Performance Specification | 102 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in pedestrian casualties on the SRN from 2019.
The number of equestrians killed or injured on the SRN.
2015 | Performance Specification | 0 | N/A | N/A | N/A
2016 | Performance Specification | 0 | N/A | N/A | N/A
2017 | Performance Specification | 0 | N/A | N/A | N/A
2018 | Performance Specification | 0 | N/A | N/A | N/A
2019 | Performance Specification | 0 | N/A | N/A | N/A
2020 | Performance Specification | 0 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows no equestrian casualties on the SRN.
Number of injury collisions on the SRN
The total number of collisions recorded that resulted in at least one injury (of any severity) on the SRN.
2020 | Performance Specification | 5267 | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 reports that the total number of injury collisions on the Strategic Road Network has reduced to 5,267. This represents a decrease of 26% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The accident frequency rate for National Highways staff
The accident frequency rate for National Highways staff based on Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.05 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The rolling 12-month AFR at March 2022 is 0.05 (consistent with March 2021). The AFR is based on 7 RIDDORs in the last 12 months.
The accident frequency rate for National Highways supply chain staff
The accident frequency rate for National Highways supply chain staff based on Reporting of Injuries Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.07 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The rolling 12-month AFR at March 2022 is 0.07. This represents a slight increase since March 2021 reported 0.05. The AFR is based on 27 RIDDORs in the last 12 months.
The % of traffic using iRAP 3* or above rated roads
IRAP based road safety investigations, developed in conjunction with the department, to feed into subsequent route strategies. Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer. We are committed to ensure that 90% of travel on our roads is 3* rated or higher by 2020. The latest data indicates that 95% of travel on our roads is on 3-star rated roads or above which exceeds the target set in our delivery plan The percentage of travel on roads with an International Road Assessment Programme (iRAP) safety rating of 3-star or better calculated using the latest version of the iRAP model (version 3.02).
2020-21 | Performance Specification | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 89% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Work has been completed to assess the star rating of our network using the iRAP Safety Rating Model v3.02. This has generated a baseline star rating assessment for the network at 2020 and provides a 2025 forecast which takes into account our current planned major investment programmes.
Commitments
Work with Transport Focus to investigate a rate-based measure for non-motorised user casualties. |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in April 2022.
1.1 Working with TF, investigate a rate-based measure for non-motorised user casualties
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | Following discussions with DfT, ORR and Transport Focus in December, it was then agreed to not progress further development.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
iRAP baseline to be established in 2021, and 2025 forecast developed, based on latest iRAP methodology. |  | Commitment completed. The metric has passed the Development milestones and will provide a baseline star rating assessment for our current network, as well as a 2025 forecast which considers current planned major investment programmes.
1.2 iRAP baseline to be established in 2021, and 2025 forecast and development, based on latest IRAP methodology
OMM Stages | Milestone
Concept Stage | N/A | N/A
Feasibility Stage | N/A | N/A
Development Stage | Q2 2021-22 | N/A
Validation Stage | N/A | N/A
Notes and commentary

## PS2-Fast and reliable
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS2: Providing fast and reliable journeys |  | For a definition of the metric and parameters for measuring and monitoring User satisfaction see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
Average Delay
Average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Ambition – Performance to be no worse at the end of Road Period 2 than it is at the end of Road Period 1. National Highways will be required to demonstrate how it has acted to reduce delays in support of this ambition. This KPI does not have a target.
2020-21 | Performance Specification | 6.7 | Ambition | KPI
2021-22 | Performance Specification | 8.8 | Ambition | KPI
2022-23 | Performance Specification |  | Ambition | KPI
2023-24 | Performance Specification |  | Ambition | KPI
2024-25 | Performance Specification |  | Ambition | KPI
In 2021-22 the average delay was 8.8 seconds per vehicle per mile. Average delay has increased in comparison to the last financial year, this is due to abnormal traffic flows last year during Covid and government lockdowns, but it is still within the target. This metric measures average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Roadworks Network Impact
The metric measures the lane-meter-days multiplied by a weighting factor to give an impact figure on the Strategic Road Network (SRN). It captures the records of Traffic Management (TM) restrictions by length and duration on the SRN and applies a weighting for each TM category.
Target: Roadworks Network Impact (weighted lane meter days) to not exceed a monthly average of: 43 million in 2021/22; 47 million in 2022/22; 48 million in 2023/24; and 47 million in 2024/25.
2020-21 | N/A | N/A | N/A (Not to exceed) | N/A | N/A
2021-22 | Performance Specification | 42.7 | 43 | KPI | -0.2m
2022-23 | - |  | 47 | KPI | 0%
2023-24 | - |  | 48 | KPI | 0%
2024-25 | - |  | 47 | KPI | 0%
This is an enhanced metric that has replaced the Network Availability metric from Year 2 of RIS2. This metric indicates the level of roadwork activity on the Strategic Road Network (SRN). National Highways was successful in not exceeding the 43 million (weighted lane metre days) monthly average in 2021-22.
Incident clearance rate
The percentage of incidents on the motorway that impact traffic flow but are cleared in less than one hour.
Target: 86% of motorway incidents cleared within one hour.
2020-21 | Performance Specification | 88.6% | 86% | KPI | 2.6%
2021-22 | Performance Specification | 87.1% | 86% | KPI | 1.1%
2022-23 | Performance Specification |  | 86% | KPI | -86%
2023-24 | Performance Specification |  | 86% | KPI | -86%
2024-25 | Performance Specification |  | 86% | KPI | -86%
In 2021-22 National Highways cleared 87.1% of incidents on motorways within an hour. We successfully maintained rolling in-year performance above the 86% target. However it is 1.5% lower than the previous year which had an abnormally lower traffic flow as a result of Covid-19.
PIs
Delay on smart motorways
Average delay to road users on smart motorways calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at upper limit for variable speed limit sections). It is a subset of the Average delay metric.
2020-21 | Performance Specification | 5.8 | N/A | PI | N/A
2021-22 | Performance Specification | 9.9 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
In 2021-22 the delay on smart motorways was 9.9 seconds which is 4.1 seconds higher than in 2020-21. However, the previous year had an abnormally lower traffic flow as a result of Covid-19. This metric measures the delay experienced by individual vehicles based on the difference between the observed average travel time, and the speed limit travel time on smart motorways.
Delay from roadworks
This metric measures the additional journey time during roadworks for all vehicle types, compared to an average benchmark journey time measured before the roadworks were in place. Calculated as average annual delay (minutes per hour travelled).
2020-21 | Performance Specification | 0.94 | N/A | PI | N/A
2021-22 | Performance Specification | 1.2 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This metric measures the total additional delay during roadworks, compared to an average benchmark journey time measured before the roadworks were in place. In 2021-22 the delay during roadworks was 1.20 mins per hour, which is 0.24 minutes higher than in 2020-21. However, the previous year had an abnormally lower traffic flow as a result of Covid-19.
Journey time reliability
The average difference between the observed travel time and the profile (typical) travel time.
2020-21 | Performance Specification | 1.9 | N/A | PI | N/A
2021-22 | Performance Specification | 2.8 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance data shows 2.8 spvpm for year-end 2021-22, representing increase in the performance from previous financial year. This is due to abnormal traffic flows last year during Covid and government lockdowns. This metric measures the average differences between the observed travel time and the profile(typical) travel time.
Delay on gateway routes
Average delay to users of gateway routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the average delay metric.
2020-21 | Performance Specification | 5.6 | N/A | PI | N/A
2021-22 | Performance Specification | 7.9 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance data shows 7.9 spvpm for year-end 2021-22, representing increase in performance in comparison to previous financial year. This is due to abnormal traffic flows last year during Covid and government lockdowns. This metric measures the average delay to users of Gateway Routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the Average Delay Metric.
Average speed
The average speed of vehicles travelling on the strategic road network
2020-21 | Performance Specification | 60.7 | N/A | PI | N/A
2021-22 | Performance Specification | 58.6 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance data shows 58.9 mph for year-end 2021-22, representing decrease in performance in comparison to previous financial year. This is due to abnormal traffic flows last year during Covid and government lockdowns. This metric measures the average speed of vehicles travelling on the Strategic Road Network (SRN)
Commitments
Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21 |  | National Highways successfully developed enhanced (Roadworks Network Impact) metric in line with our expected milestones and went live in April 2021.
2.1 Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Working with Transport Focus, investigate the development of new metrics on journey time reliability which reflects more accurately road users’ understanding of reliability, and delay in roadworks. |  | National Highways successfully completed the Feasibility stage in developing the new metrics on journey time reliability and delay in roadworks in line with our expected milestones for 2021-22. Work is on-track to complete the Development stage of these metrics in development in Q3 2022-23.
2.2 Working with TF, investigate the development of the new metrics on journey time reliability which reflects more accurately road users understanding of reliability, and delay in roadworks
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | The milestone was achieved in Q2 2021-22.
Development Stage | Q3 2022-23 | N/A
Validation Stage | TBC following review | N/A
Investigate new PIs on delays from incidents and delays on the local road/SRN boundary, and an alternative performance measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives. |  | National Highways successfully achieved the Feasibility stage and entered Development stage for delay from incidents and the alternative smart motorways measure. Work is on track to complete the Development stage of these metrics in development in Q2 2022-23. However, following the Concept stage investigation, it was established that the desired outcomes of the new metric for delays on the local road and Strategic Road Network (SRN) boundary can be achieved using existing metrics. Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in May 2022.
2.3 Investigate new PIs on delays from incidents &delays on local road/ SRN boundary, & an alternative perf. Measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | The milestone was achieved in Q2 2021-22.
Development Stage | Q2 2022-23 | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## PS3-Maintainance and resilience
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS3: A well maintained and resilient network |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Pavement condition
The percentage of pavement asset that does not require further investigation for possible maintenance. This measure reports on the overall strategic road network condition as a result of deterioration of the pavement network due to time and traffic and restoration of condition from the annual investment in maintenance. Target: Percentage of the network (as defined by HAPMS, excluding DBFOs) requiring no further investigation to be maintained at 95% or above.
2020-21 | Performance Specification | 95.2% | 95% | KPI | 0.2%
2021-22 | Performance Specification | 95.5% | 95% | KPI | 0.5%
2022-23 | - |  |  | KPI | 0%
2023-24 | - |  |  | KPI | 0%
2024-25 | - |  |  | KPI | 0%
Performance over 2021-22 has been consistent, with a score of 95.5% and consistently delivering over the national target of 95%. The current metric that has been used since RIS 1 will be updated from April 2022 as determined by the current RIS commitment.
PIs
Structures condition
The condition of National Highways' structures across the strategic road network.
2020-21 | Performance Specification | 81.2% | N/A | PI | N/A
2021-22 | Performance Specification | 81% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The structure condition metric continues to maintain consistent results in the current road period, based on two years reporting. For 2021-22, the reported Average Structural Condition (SCav) is 85.3%, and Critical Element Condition (SCrit) 63.5%. This represents a marginal decline in the Average score and a minor increase in the Critical position. The Structural Condition Index (SCI) data indicates a slight decline to 81% from 81.2% last year.
Technology availability
The percentage of time that roadside technology assets are available and functioning. The assets are considered available and functioning if they are not experiencing a service-affecting fault.
2020-21 | Performance Specification | 95.06% | N/A | PI | N/A
2021-22 | Performance Specification | 96.88% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This metric has averaged 96.88% over 2021-22.
Drainage resilience
The percentage length of carriageway that does not have an observed significant susceptibility to flooding
2020-21 | Performance Specification | 72% | N/A | PI | N/A
2021-22 | Performance Specification | 71% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
On average 71% of the network does not have an observed significant susceptibility to flooding. The remaining 29% isn't considered a high risk of flooding, but this section of the network has catchments including high risk flooding hotspots.
Geotechnical condition
The percentage length of the National Highways' geotechnical asset that is in good condition based on the ability of the asset to perform its function at the time of inspection (i.e. to support other highways assets).
2020-21 | Performance Specification | 99.62% | N/A | PI | N/A
2021-22 | Performance Specification | 99.59% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The geotechnical asset condition for 2021-22 remains stable, averaging 99.59% of the asset length in good condition, based on a condition grade across the year. This remains largely consistent with the geotechnical asset condition reported for 2020-21.
Commitments
Implement the AMDP for RP2 as described above. |  | Progress has been made against the 14 business requirements agreed in the Plan. 12 of the in-year milestones have been confirmed as complete, with 2 actions expected to continue into year-3.
3.1 Implement the AMDP for RP2 as described above (in the RIS document)
OMM Stages / milestone
Agree AMDP deliverables for the following financial year: Q4 each year |  | The milestone was achieved in Q4 2020-21.
End of year report: Q1 the following year |  | N/A
End of year review of deliverables: Q2 the following year |  | N/A
Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets |  | Commitment is on track at year-end 2021-22. Detailed investigation of feasibility recommendations is ongoing, with the team on-track to report back to the Metric Assurance Group on development in October 2022 (Q3 2022-23). Following the approval of the Feasibility Stage milestone at Q2 2021-22, National Highways has engaged with the Department for Transport, Office of Rail and Road and Transport Focus and presented future development options to investigate over the remainder of Roads Period 2.
3.2 Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21 for both Structure and Technology.
Feasibility Stage | Q2 2021-22 | The milestone was atchieved in Q2 2021-22 for both Structure and Technology
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1 |  | Commitment completed. The new metric for pavement condition will be reported from April 2022 as a replacement of the current KPI.
3.3 Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | - | N/A
Validation Stage | Q4 2021-22 | This milestone was achieved in Q4 2021-22.
Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised |  | The Development stage milestone was met as planned in Q3 2021-22, with the validation stage to be completed in Q3 2023–24.
3.4 Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q4 2021-22 | This milestone was achieved in Q3 2021-22
Validation Stage | Q3 2023-24 | N/A
Notes and commentary

## PS4 - Environment
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS4 Delivering better environmental outcomes |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Cumulative | Target | KPI/PI | Difference (Actual vs Target) |  | Notes
KPIs
Noise
The number of households within mitigated Noise Important Areas where noise has been reduced through National Highways designated fund projects.
Target: 7,500 households benefitting from noise reduction in mitigated Noise Important Areas (defined by the Department for Environment, Food and Rural Affairs (DEFRA)) using funding from the environment and wellbeing designated fund during Road Period 2 | [6 empty] | A total of 1,067 households have been claimed in 2021-22. This consists of 874 through resurfacing schemes, 192 through barriers and 1 through insulation. This gives an RP2 total of 3,178 households against the target of 7,500; representing 42% of the RP2 target.
2020-21 | Performance Specification | 2111 | 2111 | 7500 | KPI | -5389
2021-22 | Performance Specification | 1067 | 3178 | 7500 | KPI | -6433
2022-23 | Performance Specification |  |  | 7500 | KPI | -7500
2023-24 | Performance Specification |  |  | 7500 | KPI | -7500
2024-25 | Performance Specification |  |  | 7500 | KPI | -7500
Biodiversity
Deliver no net loss of biodiversity, measured using an industry standard way of measuring biodiversity changes referred to as the biodiversity metric.
Target: Achieve no net loss of biodiversity, across all National Highways activities, by the end of Road Period 2.
2020-21 | - | 147.3 | N/A | No net loss | KPI
2021-22 | - | 299.79 | N/A | No net loss | KPI
2022-23 | - |  | N/A | No net loss | KPI
2023-24 | - |  | N/A | No net loss | KPI
2024-25 | - |  | N/A | No net loss | KPI
In 2021-22 we have claimed positive delivery of 299.8 Biodiversity Units. An additional 31.9 were retrospectively validated as delivered in 2020-21 increasing the Year 1 total from 115.4 to 147.3 Biodiversity Units. The total claimed at the end of Year 2 is 447.1 Biodiversity Units.
Air Quality
The number of strategic road network links in exceedance of the legal nitrogen dioxide (NO2) limits as set by the European Union and accepted by the government.
Bring links agreed with the department and based on the Pollution Climate Mapping model into compliance with legal NO2 limits in the shortest timescales possible
There is no change to the number of links reported as exceeding the limit value for nitrogen dioxide (31), nor the number of non-viable links (17 of the 31). Of the remaining 14, 8 links have speed limits implemented, 5 are undergoing feasibility work, and 1 considering public access measures.
National Highways carbon emissions
Target: Reduce National Highways’s carbon emissions as a result of electricity consumption, fuel use and other day-to-day operational activities during RP2, to levels defined by baselining and target setting activities in 2020-21. This metric will become operational from 1 April 2021.
2020-21 | - |  | N/A |  | KPI | 0
2021-22 | - | 37178 | N/A |  | KPI | 37178
2022-23 | - |  | N/A |  | KPI | 0
2023-24 | - |  | N/A |  | KPI | 0
2024-25 | - |  | N/A |  | KPI | 0
This is a new metric for this road period. This metric started reporting in April 2021. In 2021-22 we have used 37,178 tco2e.
PIs
Supply Chain Carbon emissions
The carbon footprint associated with National Highways' supply chain and also normalised by the volume of work undertaken.
|  | Absolute | Normalised
2020-21 | Performance Specification | 365353 | 128 | N/A | PI | N/A
2021-22 | Performance Specification | 286238 | * | N/A | PI | N/A
2022-23 | Performance Specification |  |  | N/A | PI | N/A
2023-24 | Performance Specification |  |  | N/A | PI | N/A
2024-25 | Performance Specification |  |  | N/A | PI | N/A
The validated position 286,238 tonnes/CO2e for 2021-22 is an decrease on Carbon emissions in comparison to previous financial year. National Highways is engaging and focusing support for the supply chain to further improve on Carbon emissions. * Validated data to be published in 2022-23 statements
Condition of Cultural Heritage assets
The overall condition of the culturally significant assets owned by National Highways.
2020-21 | Performance Specification | 51580 | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 51592 | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
The Cultural Heritage Unit Baseline for RP2 was 51,556. In Year 1 an additional 12 Cultural Heritage Units were validated increasing the baseline to 51,568. Due to improved data, this year a further 12 units were validated for Year 1 increasing the baseline for 2020-21 to 51,580. In Year 2 another 12 units have been validated increasing the baseline to 51,592 for 2021-22.
Water Quality
The length of watercourse enhanced through the mitigation of medium, high, and very high risk outfalls as well as through other enhancements, for example river retraining/rewilding.
2020-21 | Performance Specification | 17 | N/A |  | PI | N/A
2021-22 | Performance Specification | 15 | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
In 2021-22 four mitigations have been claimed, with two fish passes and two outfalls assured. This represents 15 km of improved watercourse and demonstrates an improving trend.
Litter
The percentage of the strategic road network where litter is graded at A or B as defined in the Code of practice on litter and refuse 2006.
2020-21 | Performance Specification | 49.2% | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 60.8% | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
This metric measures the percentage of the Strategic Road Network where litter is graded at A or B as defined in the Code of practice on litter and refuse. The metric covers the whole of the Asset Delivery network on an annual basis. The reported performance for 2021-22 was 60.8%, which is 11.6% higher than in 2020-21
Commitments
Highways England carbon emissions KPI: Reduce National Highways carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21 |  |  |  |  | Commitment completed. This metric has been reporting since April 2021.
4.1 National Highways carbon emissions KPI: Reduce National Highways' carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21
OMM Stages | Milestone
Inventory and asset register update; data collation including project action plans | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Start of formal sign-off process of new metric and target with DfT | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Completion of validation; approvals of target | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach. |  |  |  |  | The commitment has been formally ceased and will continue to be monitored as part of RIS3 governance.
4.2 Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage | Q2 2021-22 | This metric was formally ceased at the Feasibility stage.
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on National Highways work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in Year 1 of RP2, as well as potential implementation opportunities identified by that stage. |  |  |  |  | This commitment was removed as metric in development as agreed with Office of Rail and Road and Department for Transport. Monitoring will continue as a commitment only. Data capture plan has been developed in 2021-22. Work continues on developing the baseline and preparation for data collection.
4.3 Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on National Highways work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in year 1 od RP2, as well as potential implementation opportunities identified by that stage.
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21. A detailed timetable was produced in 2020-21 in line with the commitment.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## PS5-Needs of all road users
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS5: Meeting the needs of all road users |  |  |  | For a definition of the metric and parameters for measuring and monitoring performance regarding vulnerable users see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Road user satisfaction
The percentage of drivers who are satisfied with their journey on the strategic road network as measured by the Strategic Roads User Survey (SRUS) conducted by Transport Focus.
Target: Achieve an 82% road user satisfaction score in 2020-21 and 2021-22, with year-on-year increases in the following years. The exact targets for 2022-23, 2023-24, and 2024-25 will be set during 2021-22.
2020-21 | Performance Specification | N/A | 82% | KPI | N/A
2021-22 | Performance Specification | N/A | 82% | KPI | N/A
2022-23 |  |  |  | KPI
2023-24 |  |  |  | KPI
2024-25 |  |  |  | KPI
The face-to-face Strategic Roads User Survey (SRUS) has not been carried out this financial year as a result of the pandemic, and it has not been possible to monitor progress for the KPI. A web-based alternative, SRUS Online, has been running since April 2021. However, due to differences in methodology and surveyed demographics, there is insufficient data at present for it to be officially adopted and target set.
Roadworks information timeliness and accuracy
The percentage of overnight road closures that are accurately notified by Highways England seven days in advance. A correctly notified road closure is one that commences within +/- 1 hour of the start time stated 7 days in advance on the Network Occupancy Management System (NOMS).
Target: Achieve 90% accuracy of roadworks information seven days (rolling) in advance of works by 2024-25, with an increasing trajectory of improvement through Road Period 2 from the level of performance achieved by the end of Road Period 1
2020-21 | Performance Specification | 54.5% |  | KPI
2021-22 | Performance Specification | 68.1% |  | KPI
2022-23 | Performance Specification |  |  | KPI
2023-24 | Performance Specification |  |  | KPI
2024-25 | Performance Specification |  | 90% | KPI
Performance remained strong in 2021-22 with performance of 68.1%, a 13.6% rise in accuracy in-year. This follows a 12.9% improvement in 2020-21, as we move closer to the 90% target by the end of 2024-25.
PIs
Timeliness of information provided to road users through electronic signage
The average median time to set signs and signals on (all) motorways after Highways England has received notification of an incident, that requires signs and signals to be manually set.
2020-21 | Performance Specification | 0:02 | N/A | PI | N/A
2021-22 | Performance Specification | 0:02 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance has been consistent over 2021-22. The median time has gradually increased month on month, and the median time to set is 19 seconds longer than in 2020-21.
Ride Quality
This measure reports the ride quality for the strategic road network using a subset of the pavement condition metric condition parameters. It is represented by the percentage of pavement asset delivering ride quality consistent with the 3m Enhanced Longitudinal Profile Variance (ELPV) value in Highways England’s standards, which is based on engineering factors and driver comfort. Percentage of the network (as defined by HAPMS, excluding DBFOs) where 3m ELPV is deemed to be category 2 and better, in accordance with the road condition standard, HD29.
2020-21 | Performance Specification | 98.5% | N/A | PI | N/A
2021-22 | Performance Specification | 98.4% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance remained stable for the Ride Quality PI throughout 2021-22, reporting 98.4% at year-end. Performance was between 98.3% and 98.6% over the year.
Working with local highways authorities to review diversion routes for unplanned events.
2020-21 | Performance Specification | 53% | N/A | PI | N/A
2021-22 | Performance Specification | 97.2% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The reported performance for 2021-22 is 97.2% (44.2% higher than 2020-21). This metric annually reports the percentage of local highway authorities which National Highways engaged with to review diversion routes for unplanned events.
Commitments
Work with Transport Focus to develop satisfaction surveys for cyclists and pedestrians that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | No in-year milestones scheduled. We are commissioning a piece of work to explore alternatives, having agreed that the survey developed isn't suitable for a broader metric.
5.1 Work with TF to develop satisfaction surveys for cyclists & pedestrians that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Work with Transport Focus to develop satisfaction surveys for logistics and coach managers that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | No in-year milestones scheduled. A logistics and coach survey has been developed with Transport Focus. Agreement was received in March to move from the concept to feasibility stage, with the aim to complete by end Q1 2022-23.
5.2 Work with TF to develop satisfaction surveys for logistics & coach managers that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22. |  |  |  | The SRUS (face to face) survey remains suspended as a result of the pandemic, with insufficient data at present to formally adopt the alternative online survey. A Change Control has been approved to further annul the target for 2022-23 until such time as a stable baseline has been made available.
5.3 Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22
OMM Stages |  | Milestone
Concept Stage |  | N/A | N/A
Feasibility Stage |  | N/A | N/A
Development Stage |  | N/A | N/A
Validation Stage |  | Q4 2021-22 | N/A
Develop with Transport Focus during RP2 a measure of ride quality which reflects road users’ experience of the network. |  |  |  | A 6 month extension to implementing the improved ride quality PI has been approved due to Covid-19 impacting on the testing during the feasibility stage, and will now look to go live at the end of Q2 2022-23.
5.4 Develop with Transport Focus during RP2 a measure of ride quality which reflects road users' experience of the network
OMM Stages |  | Milestone
Concept Stage |  | Q2 2020-21 | The milestone was achieved in Q2 2020-21.
Feasibility Stage |  | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Development Stage |  | Q1 2022-23 | N/A
Validation Stage |  | Q2 2022-23 | N/A
Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks. |  |  |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in April 2022.
5.5 Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  | TBC following review | N/A
Validation Stage |  | TBC following review | N/A
Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs. |  |  |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in May 2022.
5.6 Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | N/A
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  | TBC following review | N/A
Validation Stage |  | TBC following review | N/A
Notes and commentary

## PS6-Efficiency of delivery
National Highways Performance Monitoring Statements Year end 2021-22
Statement PS6: Achieving efficient delivery
Performance specification
| Source of Target |  | Actual (£m) | Annual forecast milestone (£m) | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Total efficiency
The value of operational and capital expenditure efficiency achieved by the end of Road Period 2.
Target: Demonstrate efficiency of £2.230 bn of capital and operational expenditure by the end of Road Period 2. | [6 empty] | The annual forecast milestone numbers will be updated annually in line with the Delivery Plan update.
2020-21 | EIMM | In-year: | 243 | 233 | KPI
|  | Cumulative: | 243 | 233 | KPI | 10
2021-22 | EIMM | In-year: | 259 | 238 | KPI
|  | Cumulative: | 502 | 471 | KPI | 31
2022-23 | EIMM | In-year: |  | 405 | KPI
|  | Cumulative: | 502 | 876 | KPI | -374
2023-24 | EIMM | In-year: |  | 508 | KPI
|  | Cumulative: | 502 | 1384 | KPI | -882
2024-25 | Performance Specification | In-year: |  | 846 | KPI
|  | Cumulative: | 502 | 2230 | KPI | -1728
PIs
Cost performance index and Schedule performance index Progress of schemes in construction through reporting Cost performance index (CPI) and Schedule performance index (SPI).
100% of schemes in construction are reporting CPI and SPI through PRISM.
Cost Performance Index (CPI): Represents the amount of work being completed on a project for every unit of cost spent. CPI is computed by Earned Value / Actual Cost. A value above one means that the project is doing well against the budget. Schedule Performance Index (SPI): Represemts how close actual work is being completed compared to the schedule. SPI is computed by Earned Value / Planned Value. A value of above one means that the project is doing well against the value.
Commitments
Investigate and look to develop new or improved metrics to monitor cost and schedule for enhancement scheme development and construction, engaging with ORR. |  |  |  |  | The focus remains on establishing CPI/SPI for schemes in construction to meet present commitments, with the concept still in development. Further investigation is required before agreeing whether to develop a new metric or consider the commitment closed.
6.1 Investigate & look to develop new or improved metrics to monitor cost & schedule for enhancement scheme development & construction, engaging with ORR
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | N/A
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## IP1
Statement IP1: Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
National Highways Delivery Plan - Major Improvements
Milestone Definitions and Key:
Construction Phase - Start of Works - The date when the start of the works is declared, following approval of final business case and construction budget, award of contract is in place along with completion of “Notice to proceed” and where applicable the “Notice to Treat”. Physical construction works will be evident on site.
Open for Traffic - The date when works are substantially complete and the scheme is open to traffic. There may be partial or overnight closures to finalise any remedial works.
Delivery Plan Commitment - The date committed to in National Highways' 2020-2025 delivery plan.
Actual Achieved - The actual date the Delivery Plan commitment has been achieved.
*Scheme commitment under review - Scheme is under review and is subject to formal change control governance.
| Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works (SOW) |  | Open for Traffic
|  |  |  | Delivery Plan Commitment | Actual Achieved | Delivery Plan Commitment | Actual Achieved | Lane miles delivered (Actual)
National Highwys schemes | North East | 1 | A1 Scotswood to North Brunton | Pre RP2 | 2020-03-20 | 2022/2023
|  | 2 | A19 Testos | Pre RP2 | 2019-03-19 | 2021/2022 Q3 | 2021-06-21 | 3
|  | 3 | A19 Norton to Wynyard | Pre RP2 | 2020-03-20 | 2022/2023 | 2021-11-21 | 6.7
|  | 4 | M621 Junctions 1-7 | Pre RP2 | 2019-11-19 | 2022/2023
|  | 5 | A61 Westwood Roundabout | Pre RP2 | 2020-03-20 | 2021/2022 Q1 | 2021-02-21 | 0.8
|  | 6 | A1 Morpeth to Ellingham | 2022/2023 Q2 |  | 2024/2025
|  | 7 | A1 Birtley to Coal House | 2021/2022 Q2 | 2021-05-21 | 2024/2025
|  | 8 | A19 Down Hill Lane | 2020/2021 Q4 | 2020-09-20 | 2022/2023 | 2022-03-22 | 2.3
|  | 9 | A63 Castle Street | Pre RP2 | 2020-03-20 | 2024/2025
|  | 10 | M62 Junctions 25-30 | 2021/2022 Q4 |  | 2022/2023
| North West | 11 | A585 Windy Harbour to Skippool | Pre RP2 | 2020-03-20 | 2023/2024
|  | 12 | M62 Junctions 20-25 | 2022/2023 Q4 |  | RP3
|  | 13 | M6 Junction 19 | Pre RP2 | 2020-03-20 | 2021/2022 Q3 | 2021-11-21 | 2.1
|  | 14 | A66 Northern Trans-Pennine | 2023/2024 Q4 |  | -
|  | 15 | A5036 Princess Way | 2023/2024 Q4 |  | RP3
|  | 16 | M6 Junctions 21a-26 | 2020/2021 Q4 | 2021-03-21 | 2022/2023
|  | 17 | Mottram Moor Link Road & A57 Link Road | 2022/2023 Q4 |  | RP3
|  | 18 | M56 Junctions 6-8 | Pre RP2 | 2020-03-20 | 2021/2022 Q4
|  | 19 | M60/M62/M66 Simister Island Interchange | 2024/2025 |  | -
| Midlands | 20 | A500 Etruria | Pre RP2 | 2019-02-19 | 2020/2021 Q3 | 2020-07-20 | 1
|  | 21 | M6 Junctions 13-15 | Pre RP2 | 2018-03-18 | 2021/2022 Q2
|  | 22 | M42 Junction 6 | Pre RP2 | 2020-03-20 | 2024/2025
|  | 23 | A46 Coventry Junctions | Pre RP2 | 2020-03-20 | RP3
|  | 24 | M40/M42 Interchange | Pre RP2 | 2020-02-20 | 2023/2024
|  | 25 | A45/A6 Chowns Mill Junction | Pre RP2 | 2019-11-19 | 2021/2022 Q4 | 2021-12-21 | 0
|  | 26 | M1 Junctions 13-19 | Pre RP2 | 2015-11-15 | 2022/2023
|  | 27 | A38 Derby Junctions | 2021/2022 Q2 |  | 2024/2025
|  | 28 | M54-M6 Link Road | 2021/2022 Q4 |  | 2024/2025
|  | 29 | A5 Dodwells to Longshoot | #N/A
|  | 30 | A52 Nottingham Junctions | Pre RP2 | 2017-01-17 | 2023/2024
|  | 31 | M6 Junction 10 | Pre RP2 | 2020-01-20 | 2022/2023
|  | 32 | A46 Newark Bypass | 2024/2025 |  | -
|  | 33 | M42 Junctions 4-7 | 2023/2024 Q4 |  | 2024/2025
|  | 34 | M6 Junctions 4-5 | 2021/2022 Q2 |  | 2022/2023
|  | 35 | M6 Junctions 5-8 | 2022/2023 Q4 |  | 2024/2025
|  | 36 | M6 Junctions 8-10a | 2022/2023 Q2 |  | 2024/2025
| East | 37 | A14 Cambridge to Huntingdon | Pre RP2 | 2016-10-16 | 2020/2021 Q3 | 2020-05-20 | 134
|  | 38 | A47 Wansford to Sutton | 2022/2023 Q4 |  | 2024/2025
|  | 39 | A47 Great Yarmouth Junctions | 2023/2024 Q4 |  | 2024/2025
|  | 40 | A47 Guyhirn Junction | 2020/2021 Q4 | 2021-02-21 | 2022/2023 | 2022-03-22 | 0.3
|  | 41 | A47 North Tuddenham to Easton | 2022/2023 Q4 |  | 2024/2025
|  | 42 | A47 Thickthorn Junction | 2022/2023 Q4 |  | 2024/2025
|  | 43 | A47 Blofield to North Burlingham | 2022/2023 Q4 |  | 2024/2025
|  | 44 | A428 Black Cat to Caxton Gibbet | 2022/2023 Q2 |  | RP3
|  | 45 | A12 Chelmsford to A120 | 2023/2024 Q4 |  | RP3
|  | 46 | M1 Junctions 10-13 | 2022/2023 Q2 |  | 2023/2024
| South East | 47 | M4 Junctions 3-12 | Pre RP2 | 2017-03-17 | 2021/2022 Q4
|  | 48 | A34 Newbury to Oxford Enhancements | Pre RP2 | 2019-08-19 | 2021/2022 Q4 | 2021-11-21 | 0
|  | 49 | M3 Junctions 9-14 | Pre RP2 | 2020-01-20 | 2023/2024
|  | 50 | M27 Junctions 4-11 | Pre RP2 | 2018-04-18 | 2021/2022 Q2
|  | 51 | M25 Junction 25 | 2020/2021 Q4 | 2021-01-21 | 2022/2023
|  | 52 | M25 Junction 28 | 2021/2022 Q4 |  | 2024/2025
|  | 53 | M25 Junctions 10-16 | 2022/2023 Q2 |  | RP3
|  | 54 | M25 Junction 10 | 2021/2022 Q4 |  | 2023/2024
|  | 55 | M3 Junction 9 | 2023/2024 Q4 |  | RP3
|  | 56 | M27 Southampton Junction 8 | 2021/2022 Q2 |  | 2022/2023
|  | 57 | A27 Arundel Bypass | 2023/2024 Q4 |  | RP3
|  | 58 | A27 Worthing and Lancing improvements | 2024/2025 |  | RP3
|  | 59 | A31 Ringwood | 2020/2021 Q4 | 2021-03-21 | 2022/2023
|  | 60 | A2 Bean and Ebbsfleet | Pre RP2 | 2020-03-20 | 2022/2023
|  | 61 | M2 Junction 5 | 2021/2022 Q2 | 2021-09-21 | 2024/2025
|  | 62 | A27 East of Lewes Package | Pre RP2 | 2020-03-20 | 2022/2023
|  | 63 | Lower Thames Crossing | 2022/2023 Q4 |  | RP3
| South West | 64 | A303 Sparkford to Ilchester | 2021/2022 Q3 | 2021-09-21 | 2023/2024
|  | 65 | A303 Amesbury to Berwick Down | 2023/2024 Q2 |  | RP3
|  | 66 | A358 Taunton to Southfields | 2024/2025 |  | RP3
|  | 67 | A30 Chiverton to Carland Cross | Pre RP2 | 2020-03-20 | 2023/2024
|  | 68 | A417 Air Balloon | 2022/2023 Q4 |  | 2024/2025
|  | 69 | M4 Junctions 19-20 and M5 Junctions 16-17 | 2022/2023 Q2 |  | 2023/2024
|  | 70 | A21 Safety Package | 2021/2022 Q1 | 2021-06-21 | 2024/2025
FOR INFORMATION ONLY
Housing infrastructure fund schemes and third party schemes - These schemes will be delivered by local authorities and third parties with our support and are subject to future planning decisions. They are subject to different governance and funding arrangements
Delivery Plan - the date in the Highways England Delivery Plan
Start of Works forecast / actual - start of construction date as provided by external delivery organisation (third parties, local authority)
Open for Traffic forecast / actual - open for traffic date as provided by external delivery organisation (third parties, local authority)
* SOW / OFT Delivery Plan - dates updated to financial year format
External Delivery Organisation | Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works |  | Open for Traffic
|  |  |  | *Delivery Plan | Actual | *Delivery Plan | Actual
Housing infrastructure fund schemes | East | n/a | A120: Tendring/Colchester Border Garden Community | 2022/23 |  | 2024/25
| South West | n/a | M5 junction 10 and link road | 2022/23 |  | 2024/25
| South East | n/a | A249: Swale transport infrastructure | 2021/22 | 2022/23 | 2024/25
| North West | n/a | M6: South Lancaster Growth Catalyst – junction 33a | 2024/25 |  | RP3
| East | n/a | A5 Dordon to Atherstone | RP3 |  | RP3
External Delivery Organisation | Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works |  | Open for Traffic
|  |  |  | Delivery Plan | Actual | Delivery Plan | Actual
Third party schemes | Midlands | n/a | A5 Towcester relief road | 2021/22 | 2022-03-22 | RP3
| East | n/a | M11 junction 7a | 2020/21 Q2 | 2020-06-01 | 2022/23
| North West | n/a | M55 junction 2 | RP1 | 2019-09-01 | 2023/24
| North West | n/a | M62 junction 19 | 2020/21 Q3 | 2020-10-01 | 2022/23

## IP2
Statement IP2: RIS3 Development Pipeline
No. schemes started development - total number of schemes that have started development nationally between April 2021 - March 2022
Programme level commentary - description of progress made at a national level across the RIS3 Development pipeline between April 2021 - March 2022
Region | RIS3 Development Pipeline | Programme (National) level update
|  | No. schemes started development | Programme level commentary
North | A19 North of Newcastle Junctions | 33 | This year we have continued early development work at PCF Stage 0, Stage 1 and Stage 2 on 25 schemes, including M27 Southampton Access which has received Special Approval to proceed to PCF Stages 3-5. We have also started early development at PCF Stage 1 on 8 more projects since April 2021, including A303 South Petherton to Southfields which has been confirmed as the A303 Phase 2 upgrade scheme. Additions and Removals The A34 N&S Oxford scheme has been added to the RIS3 Pipeline. *The A21 Safety Package has been removed from the RIS3 Pipeline and is now being delivered in RP2 by NH Operations Directorate.
A64 Hopgrove
M1 Leeds Eastern gateway
M1/M62 Lofthouse interchange
M6 Junctions 19 to 21a Knutsford to Croft extra capacity
M1 Junctions 35 to 39 Sheffield to Wakefield extra capacity
A1 Doncaster to Darrington
M6 junction 22
Manchester South East junction improvements
East | A47/A1101 Elm Road junction
A11 Fiveways junction
M11 junction 13 Cambridge West
A12/A14 Copdock interchange
A120 Braintree to A12
Tilbury link road
A34 North & South Oxford
Midlands | M6 junction 15 Potteries southern access
A483 Pant-Llanymynech bypass (in cooperation with the Welsh Government)
M1 North Leicestershire extra capacity
M1 Leicester Western access
A5 Hinckley to Tamworth
South and West | Severn resilience package
A404 Bisham junction
A2 Brenley Corner
A303 Phase 2 upgrade
A3/A247 Ripley South
A21 safety package*
A2 Dover Access
A27 Lewes to Polegate
A27 Chichester Improvements
M27 Southampton Access
A38 Trerulefoot-Carkeel Safety Package
A404/M40 Junction 4 High Wycombe

## IP3
Statement IP3: Designated funds
There are 4 designated funds outlined in National Highways' Delivery Plan 2020-2025: 1. Safety and congestion - Safety and Congestion schemes 2. User and communities - Integration; Walkers, Cyclists & Horse Riders; Roadside Facilities; Communities; Freight and Information 3. Environment and wellbeing - Biodiversity; Noise; Air quality; Flooding; Water Quality; Carbon; Cultural Heritage; Landscape and Environmental Legacy 4. Innovation and modernisation - Design, construction and maintenance; Connected and Autonomous Vehicles; Customer Mobility; Energy and Environment; Operations. Under each designated fund there are individual themes. Projects which use designated funds are aligned to a fund and an individual theme.
Key Definitions: No. planned projects completing either feasibility, detailed design or implementation 2021-2022 - The combined number of projects planned to complete either the feasibility, detailed design or implementation stage for each fund Feasibility - The number of projects that have completed the feasibility stage at the end of the year Detailed design - The number of projects that have completed the detailed design stage at the end of the year Implementation - The number of projects that have completed the implementation stage at the end of the year Comments - Justification for any deviation or any supporting commentary
Fund | Projects planned 2021-2022 | Projects delivered 2021-2022 |  |  | Total count of stages complete | Comments
| No. planned projects completing either feasibility, detailed design or implementation | Feasibility | Detailed design | Implementation
Safety and congestion fund | 50 | 8 | 12 | 12 | 32 | Safety and Congestion has achieved 32 stage gates passed against an increased in year baseline target of 50. National Highways have reported a larger number of stage gates have been delivered in year than have been validated. These will require evidence and validation in 2022-23.
Users and communities fund | 60 | 12 | 4 | 6 | 22 | Users and Communities underperformed its baseline with 22 stage gates being passed against a target of 60. National Highways have reported a larger number of stage gates have been delivered in year than have been validated. These will require evidence and validation in 2022-23.
Environment and wellbeing fund | 110 | 16 | 5 | 29 | 50 | Environment and Wellbeing underperformed its baseline with 50 stage gates being passed against a target of 110. National Highways have reported a larger number of stage gates have been delivered in year than have been validated. These will require evidence and validation in 2022-23..
Innovation and modernisation fund | 30 | 6 | 4 | 6 | 16 | Innovation and Modernisation underperformed its baseline with 16 stage gates being passed against a target of 30. National Highways have reported a larger number of stage gates have been delivered in year than have been validated. These will require evidence and validation in 2022-23.

## IP4
Statement IP4: Renewal Volume Reporting
This statement details National Highways’ capital renewals delivery performance against planned volumes of activity associated with different asset types and interventions across the Strategic Road Network in 2021-22 (as set out in NH’s annual Delivery Plan).
Asset | Description | Unit | 2021-22
Full year Actual
|  |  | Total | Baseline | Variance | Comments
Asphalt road surface (pavement) | Total length of existing asphalt resurfaced | Lane Kilometers | 1704.3 | 1490 | 214.03 | The Asphalt Pavement plan of 1,490lkms (925.8 lane miles) was comprised of 270 schemes (some of which were broad assumptions of emergency reactive works). Included in the target were; - 46lkms planned on 58 Non-Asphalt PIT schemes (eg delivered alongside Drainage, RRS) - 748lkms on 149 ‘simple’ pavement and lining schemes - 696lkms on 63 complex schemes delivering multiple output types Of the 1,704lkms delivered; - 19lkms were delivered on 8 Non-Renewals schemes (eg Safety & Congestion) - 50lkms were delivered on Non-Asphalt PIT schemes - 657lkms were delivered on simple’ pavement and lining schemes - 806lkms on complex schemes delivering multiple output types (the programme tended to bundle more schemes as the year progressed) The outturn on the targeted schemes was 1,492lkms and met the plan overall. The additional 212lkms on non-target schemes was spread across all regions but almost 30% was delivered by the East as it redirected funds from its concrete programme. The total over delivery of 214lkms (14%) was lower than the 30% additional spend, however, half of that delivered outputs on a wide range of outputs in addition to lkms ie while the spend was assigned to the Pavement PIT, RRS and Drainage outputs were delivered at the same time.
Concrete road surface (pavement) | Total length of existing concrete road surface reconstructed and replaced with asphalt surface | Lane Kilometers | 108.3 | 101 | 7.3 | The Concrete Pavement plan assumed that the large reconstruction schemes in the East would be on the ground during 21/22. However, the complexity of the solution and contracts means that all reconstruction schemes have been deferred into 22/23+. The majority of the £77m deferred was planned for the East and, as this value was so large, the region replaced this with other Renewals delivery. If it had not done this, it would not have been able to deliver the shortfall alongside the new concrete programme in future years. The original concrete output target of 101lkms (63 lane miles) consisted of 13 schemes nationally, of which 8 schemes in the East planned 93lkms including 14lkms of reconstruction (high cost but low output). This meant that other Life Extension Works (LEW) could be progressed further to enable the target to be met. No full reconstruction lkms were delivered.
Safety barriers (steel) | Total length of steel safety barriers installed or renewed | Linear metres | 563397 | 382000 | 181397 | The Road Restraint Systems - Steel plan of 382,000 was comprised of 115 schemes. Included in the target were; - 38,514 (10%) planned on 55 Non-RRS Steel PIT schemes (eg delivered alongside Pavement and Structures schemes) - 215,616 on 38 ‘simple’ RRS Steel schemes - 127,870 on 22 complex schemes delivering multiple output types Of the 563,397 delivered; - 28,365 were delivered on 11 Non-Renewals schemes (eg Safety & Congestion) - 35,807 were delivered on Non-RRS Steel PIT schemes - 356,523 were delivered on simple’ RRS Steel schemes - 181,509 on complex schemes delivering multiple output types (the programme tended to both deliver more and bundle more schemes as the year progressed) The additional delivery of 181,397 was not matched by the change in PIT spend as RRS is often delivered alongside other PIT schemes (eg Pavement and Structures). Of the addition; - 28,365 was delivered by the non-Renewals funded schemes - 90,000 was delivered as part of complex schemes (eg the increase in Pavement PIT and Structures schemes) - The remainder of the addition was delivered as part of more efficient delivery
Safety barriers (concrete) | Total length of concrete safety barriers installed or renewed | Linear metres | 3106 | 2600 | 506 | The Road Restraint Systems - Concrete plan of 2,600 was comprised of 6 schemes. Included in the target were; - 2,050 on 3 schemes in YNE - 50 on 1 scheme in YNE as part of a Drainage PIT scheme - 245 on 1 scheme in NW - 252 on 1 scheme in the SW as part of a Waterproofing PIT scheme Of the 3,106 delivered; - 690 were delivered in YNE which was short of their plan as schemes were re-assessed and could not be delivered in year. - 291 was delivered in the NW - SW delivered a simpler RRS Steel solution - SE delivered 291 on a M20 scheme, replacing some steel with concrete - East delivered 160 on a A14 scheme, replacing some steel with concrete as part of a wider drainage scheme - 1,674 was delivered in the Midlands on three schemes on the M5, M50 and A40 The additional delivery of 506 was not matched by the change in PIT spend as RRS is often delivered alongside other PIT schemes (eg Drainage and Structures). However, the main addition/replacement of 1,410 was delivered in Midlands as part of efficient delivery and repair on the M5.
Significant structures | Number of significant structures | Number | 27 | 26 | 1 | We achieved 27 delivery milestones against the target of 44 with 8 schemes starting design, 5 starting construction and 14 completing construction.
Road markings | Length along the centre line of the road markings, including marking on new or replacement road surfacing | Linear metres | 4140514 | 3450000 | 690514 | The Road Markings plan of 3,450,000 consisted of 314 schemes. These were planned to be predominantly delivered in conjunction with the Pavement schemes but 50 schemes were mainly standalone marking schemes. In addition to the markings reported we also delivered 395,000 road studs (not part of the target). In common with previous years (see causes above), there was an over-delivery of markings compared to the target (690,514 – 20%). However, the over delivery is part of declining trend and is the lowest since we began recording the output (40% over-delivery in 20/21 for comparison). The additional expenditure on the markings PIT was 7.8% more than the budget but these secondary outputs are mainly delivery alongside pavement PIT schemes and the expenditure is therefore not in proportion to the output delivery. The Kerbs plan of 13,400 consisted of 43 schemes. These were planned to be predominantly delivered in conjunction. with the pavement and lining or more complex schemes. Only two of the schemes were ‘standalone’ schemes delivering kerbs as part of footpath renewal. In common with previous years (see causes above), there was an over-delivery of kerbs compared to the target (4,984 – 37%). However, although we delivered to target in 20/21, the over delivery is part of declining trend and is the lowest since we began recording the output. There is no separate PIT for kerbs as this is recorded as part of the wider ancillaries’ expenditure.
Kerbs | Total length of kerbs laid or renewed | Linear metres | 18384 | 13400 | 4984
Safety barriers (steel) | Total length of steel safety barriers installed or renewed | Linear metres | 563397 | 382000 | 181397 | See above
Safety barriers (concrete) | Total length of concrete safety barriers installed or renewed | Linear metres | 3106 | 2600 | 506 | See above
Drainage | Total length of drainage installed or renewed | Linear metres | 178457 | 148000 | 30457 | The Drainage plan of 148,000 was comprised of 105 schemes (some of which were broad assumptions of emergency flooding reactive works). Included in the target were; - 18,853 planned on 30 Non-Drainage PIT schemes (eg delivered alongside RRS, Pavement and Structures) - 118,529 on 67 ‘simple’ Drainage schemes - 10,618 on 8 complex schemes delivering multiple output types Of the 178,457 delivered; - 6,524 were delivered on 10 Non-Drainage schemes (eg Designated Funds, Environment) - 5,846 were delivered on Non-Drainage PIT schemes - 124,775 were delivered on simple’ Drainage schemes - 41,312 on complex schemes delivering multiple output types (the programme tended to bundle more schemes as the year progressed) The total over delivery of 30,257 (21%) was lower than the 53% additional spend, however, while some of the increased spend can be directly matched to the Drainage outputs, there was also a substantial amount of activity on drainage points and ponds than does not record a linear metres output. In terms of over-delivery, this was the lowest percentage since 2018/19 and lower than all other years apart from that.
Geotechnical | Total length of embankment / cutting treated parallel to the carriageway | Linear metres | 3148 | 2900 | 248 | The Geotech plan of 2,900 was comprised of 23 schemes. Included in the target were; - 772 planned on 9 Non-Geotech PIT schemes (eg delivered alongside Structures) - 967 on 7 ‘simple’ Geotech schemes - 1,161 on 7 complex schemes delivering multiple output types Of the 3,148 delivered; - 1,232 were delivered Non-Geotech PIT schemes - 891 on the ‘simple’ Geotech schemes - 1,025 on the complex schemes delivering multiple output types The over delivery of 248 (8.6%) was mainly delivered by 315 additional Geotech on the A34 Drayton Layby scheme funded outside of Renewals. The total over delivery was lower than the 48.3% additional spend, however, while some of the increased spend can be directly matched to the Geotech outputs, there was also a substantial amount of activity on Geotech that does not record a linear metres output.
Traffic signs (non-electrical) | Number of permanent non-electrical traffic signs installed or replaced | Number | 1534 | 1100 | 434 | The Traffic Signs (Non-Electrical) plan of 1,100 was comprised of 60 schemes. Included in the target were; - 1,051 planned on 50 Non-Traffic Signs PIT schemes (eg the vast majority delivered alongside Pavement schemes) - 49 on 10 ‘simple’ Traffic Signs schemes Of the 1,534 delivered; - 312 were delivered on non-Renewals funded schemes (eg Designated Funds schemes) - 1,085 delivered on the Non-Traffic Signs PIT schemes - 137 on the ‘simple’ Traffic Signs schemes The over delivery of 434 (39.5%) was mainly delivered by 312 signs outside of Renewals funding and additional simple signing renewal. The match between the additional spend on Traffic Signs of 27.5% is consistent with the net 11.5% over delivery (after disregarding the non-Renewals funding delivery). The PIT is not a good measure of Traffic Sign delivery due to the high proportion of delivery alongside other PITs (eg the main delivery alongside Pavement schemes).
Guardrail | Total length of new or replacement pedestrian guardrail | Linear metres | 912 | 800 | 112 | The Guardrail plan of 800 was comprised of just 6 schemes all of which were planned to be delivered as part of other, mainly, Structures schemes. Of the 912 delivered; - 270 were delivered on Non-Guardrail schemes (eg Safety & Congestion and two RIS funded schemes (A34 and A69)) - 642 were delivered on Non-Guardrail schemes (the main shortfall on the Renewals funded schemes was in the East with Pavement schemes not delivered due to road space issues) Boundary Fencing and Guardrail expenditure is captured as a single PIT. Expenditure decreased by 8.1% below plan, the increase in output delivery was contributed to by delivery on non-Renewals funded activity and efficient delivery of scheme through scheme bundling.
Boundary fencing | Total length of new or replacement boundary fencing | Linear metres | 70183 | 64000 | 6183 | The Boundary Fencing plan of 64,000 was comprised of 51 schemes. Included in the target were; - 1,683 planned on 13 Non-Boundary Fencing schemes (eg delivered alongside RRS schemes) - 62,207 on 37 ‘simple’ Boundary Fencing schemes - 110 on 1 complex schemes delivering multiple output types Of the 70,183 delivered; - 3,920 were delivered on Non-Boundary Fencing schemes (mainly two RIS funded schemes A34 and A69) - 62,411 on the ‘simple’ Boundary Fencing schemes - 3,852 on the complex schemes delivering multiple output types The over delivery of 6,183 (9.7%) was mainly delivered by the 3,920 non-Renewals funded schemes and additional delivery on more complex schemes as part of efficient delivery. Boundary Fencing and Guardrail expenditure is captured as a single PIT. Expenditure decreased by 8.1% below plan, the increase in output delivery was contributed to by delivery on non-Renewals funded activity and efficient delivery of scheme through scheme bundling.
Lighting | Number of road lighting columns installed or replaced | Number | 992 | 1050 | -58 | The Lighting (column renewal) plan of 1,050 was comprised of 28 schemes. Included in the target were; - 343 planned on 8 Non-Lighting schemes (eg delivered alongside RRS and Pavement schemes) - 677 on 18 ‘simple’ Lighting schemes - 30 on 2 complex schemes delivering multiple output types Of the 992 delivered; - 94 were delivered Non-Renewals schemes (mainly Safety & Congestion and Winter Maintenance funded schemes) - 320 delivered on Non-Lighting PIT schemes - 387 were delivered on the ‘simple’ Lighting schemes - 191 on the complex schemes delivering multiple output types. Additional delivery took place on schemes on the A1(M) and A26 as part of efficient scheme delivery The shortfall of 58 (5.5%) was mainly in YNE (under delivery of 290) due to the slower than planned transition to AD in Area. The shortfall in YNE was partially offset by the over-delivery in other Areas as above. The lighting column output for the Delivery Plan is for column renewal and does not over all aspects of lighting activity. The additional spend (42.2%) above the PIT plan was not all on column renewal. A The Lighting output was on track until the final month of the year, but South West had miss-classified some of its column renewals and these were then reported as part of the supplementary numbers above.
Bridge joint | Number of bridge deck expansion joint installations installed or renewed | Number | 516 | 450 | 66 | The Bridge Joints plan of 450 was comprised of 100 schemes. Included in the target were; - 273 planned on 49 Non-Bridge Joints schemes (eg delivered alongside Pavement and Waterproofing schemes) - 44 on 21 ‘simple’ Bridge Joint schemes - 133 on 30 complex schemes delivering multiple output types Of the 516 delivered; - 5 were delivered Non-Renewals schemes (A69 RIS funded scheme) - 305 delivered on Non-Bridge Joint PIT schemes - 31 were delivered on the ‘simple’ Bridge Joint schemes - 175 on the complex schemes delivering multiple output types. Additional delivery took place on schemes on the A1(M) and A26 as part of efficient scheme delivery The additional delivery of outputs was matched by the increase in PIT spend above the plan. The planning for bridge joints is not simple to assess and over-delivery is caused by joints being un-covered as schemes progress.
Bridge bearing | Number of bridge bearing units installed or renewed | Number | 172 | 90 | 82 | The Bridge Bearings plan of 90 was comprised of just 8 schemes. Included in the target were; - 46 planned on 4 Non-Bridge Bearing schemes (eg delivered alongside Waterproofing schemes) - 44 on 4 ‘simple’ Bridge Bearing schemes Of the 172 delivered; - 4 were delivered on a Non-Renewals scheme (Designated Funds, footbridge) - 76 delivered on Non-Bridge Bearings PIT schemes - 92 were delivered on the ‘simple’ Bridge Bearing schemes The additional delivery of outputs was mainly delivery in the East on the A14 Orwell and Brickfield Bridges. Much of that additional delivery occurred because the schemes had begun in the prior year and the outputs recordable in 21/22 and meant that outputs were increased and expenditure incurred in the prior year.
Parapet | Total length of vehicle parapet installed or renewed | Linear metres | 5099 | 5100 | -1 | The Parapet plan of 5,100 was comprised of 25 schemes. Included in the target were; - 1,988 planned on 8 Non-Parapet schemes (eg delivered alongside Waterproofing and Joint schemes) - 458 on 2 ‘simple’ Parapet schemes - 2,654 on 15 complex schemes delivering multiple output types Of the 5,099 delivered; - 630 were delivered on Non-Renewals schemes (A69 RIS scheme and two Safety & Congestion schemes) - 2,251 delivered on Non-Parapet PIT schemes - 447 were delivered on the ‘simple’ Parapet schemes - 1,771 were delivered on the complex multi output schemes The output target was missed by just 1. Within the total delivery, the biggest shortfall was mainly in YNE (under delivery of 886) due to the slower than planned transition to AD in Area. The shortfall in YNE was offset by the 630 additional non-Renewals funded outputs and additional delivery on the A14 Brickfield Bridge alongside the Bridge Joints above.
Waterproofing | Total surface area treated for waterproofing | Square metres | 24270 | 32500 | -8230 | The Waterproofing plan of 32,500 was comprised of 35 schemes. Included in the target were; - 15,848 planned on 13 Non-Waterproofing schemes (eg delivered alongside other structures schemes) - 522 on 2 ‘simple’ Waterproofing schemes - 16,130 on 20 complex schemes delivering multiple output types Of the 24,270 delivered; - 1,305 were delivered on Non-Renewals schemes (A69 RIS scheme and two Designated Fund schemes) - 12,426 delivered on Non-Waterproofing PIT schemes - 522 were delivered on the ‘simple’ Waterproofing schemes - 10,017 were delivered on the complex multi output schemes The output target was missed by 8,230 (25.3%) and was matched by the shortfall in the Waterproofing PIT expenditure outturn. In the East, the 4,893 shortfall was due to lack of road space, in YNE the 2,928 shortfall was due to the slower than planned transition to AD in Area 12. In SW the shortfall in delivery was matched by works brought forward in the SE.
Motorway communications equipment | Number of new or replaced motorway communications equipment items | Number | 272 | 215 | 57 | The Motorway Comms Equipment plan of 215 was comprised of 32 schemes. Included in the target were; - 25 planned on the M25 J23-25 RIS funded scheme - 119 planned on 24 Non-Motorway Comms Equipment schemes (eg delivered alongside Pavement schemes) - 13 on 1 ‘simple’ Motorway Comms Equipment scheme - 58 on 6 complex schemes delivering multiple output types Of the 272 delivered; - 50 were delivered on M25 J23-25 RIS funded scheme - 131 delivered on Non- Motorway Comms Equipment PIT schemes - 13 on the ‘simple’ Motorway Comms Equipment scheme - 78 were delivered on the complex multi output schemes Motorway Comms Equipment and Technology Renewals expenditure is captured as a single PIT. Expenditure decreased by 17.6% below plan, the increase in output delivery was contributed to by delivery on non-Renewals funded activity and efficient delivery of scheme through scheme bundling.
Technology renewals | Number of technology assets renewed or improved | Number | 369 | 370 | -1 | The Technology Renewals plan of 370 was comprised of 65 schemes. Included in the target were; - 2 planned on the M25 J23-25 RIS funded scheme - 177 planned on 25 Technology Renewals schemes (eg delivered alongside Pavement schemes) - 139 on 33 ‘simple’ Technology Renewals schemes - 52 on 5 complex schemes delivering multiple output types Of the 369 delivered; - 3 were delivered on M25 J23-25 RIS funded scheme - 184 delivered on Non- Technology Renewals PIT schemes - 105 on the ‘simple’ Technology Renewals scheme - 77 were delivered on the complex multi output schemes The Technology Renewals output was missed by just 1 with all regions close to target. Motorway Comms Equipment and Technology Renewals expenditure is captured as a single PIT. Expenditure decreased by 17.6% below plan, the increase in output delivery was contributed to by delivery on non-Renewals funded activity and efficient delivery of scheme through scheme bundling.

## IP5
Statement IP5: Maintenance Delivery Reporting
This statement details National Highways' 2021-22 performance against a set of key maintenance activity measures. They represent a combination of planned, cyclical and reactive maintenance activities. The purpose of the statement is to provide supplementary reporting and assurance, in addition to the asset KPI’s and PI’s, that Highways England is keeping the network in good condition and meeting the requirements of the Licence to operate a safe and serviceable network.
Activity | Type | % Completed 24 Hour Priority Defects within the required timescale | % Completed within the required timescale | Comments
Defects | Drainage Asset Defects/Service Duct Defects (AD Areas) | 94.3% | 87.3% | At a national level we have maintained strong overall performance. During the year, we have had 2 further areas transition into asset delivery and have maintained the performance with increased defect numbers.
| Fences/Walls Defects | 96% | 93.3%
| Geotechnical asset defects (AD Areas) | 99.4% | 94.9%
| Lighting defects | 91.5% | 88.9%
| Pavements/Paved area defects | 94.8% | 94.5%
| Road restraint systems defects | 93.8% | 89.1%
| Soft estate landscape defects (AD Areas) | 94.9% | 85.1%
| Structure defects (AD Areas) | 92.5% | 93.1%
| Sweeping and cleaning - (including offensive and non-offensive graffiti) | 93.1% | 93%
| Traffic signs/Road markings/Road studs defects | 95.6% | 91.5%
Activity | Type | % completed |  | Comments
Winter Service | The percentage of precautionary salting delivered within the precautionary salting and turnaround time as stated within the Severe Weather Plan | 99% |  | Consistent performance in salting throughout the year. An outlier in one region due to supplier contracts, which is being managed by the region to resolve.
| Percentage of instances where running lanes were available in accordance with the Service Provider Severe Weather Plan in relation to snow clearance. | 100% |  | Consistent performance in salting throughout the year. An outlier in one region due to supplier contracts, which is being managed by the region to resolve
Activity | Type | % of total catchment length with a low risk status |  | Comments
Drainage | Drainage Performance Indicator | 72% |  | Performance maintained at 100% throughout the year for running lanes.
Activity | Type | % of planned litter clearance completed |  | Comments
Litter | Percentage of planned litter clearance activities undertaken in accordance with ASC requirements or the accepted programme set out in ADAMr (AD) | 92% |  | Performance has remained strong. There has been a slight decrease in performance from Q3 in one region that has affected overall performance, and plans are in place to address
Activity | Type | % of cyclic works completed |  | Comments
Cyclical Maintenance (AD Areas only) | Percentage of Cyclic works that are completed within the required timescales | 79% |  | Small drop in performance during Q4 which has impacted end of year performance, however improvements have been seen compared to end of year in 20-21. Work continues with regions to improve this metric
Activity | Type | % of <24hr reactive works completed |  | Comments
Reactive Maintenance (AD Areas only) | Percentage of Reactive <24hr works that are completed within the required timescales | 93% |  | Consistent performance within Reactive Maintenance starting the year remaining at 93%. An improvement from EOY 20/21 (91%)
Activity | Type | Total No of claims |  | Comments
Red Claims | Total number of claims | 1198 |  | The number of red claims received is consistent with previous years. We have seen an increase in the number of green claims as areas transitioning into AD.
Total No of settled claims
| Total number of settled claims | 512
Green Claims | Total number of claims | 6898
Total No of settled claims
| Total number of settled claims | 7420
Activity | Type | % of programme completed |  | Comments
Planned Asset Condition Inspections | Structures | 92% |  | Operations have continued to work on completing the programme of inspections and ensuring the inspections don’t become overdue. Of the 65 structures inspections overdue, 52% have been physically undertaken and require validation in IAMIS. The remaining structures are due to frustrated access.
| VRS | 88%
| Lighting | 89%
| Geotech | 101%
| Traffic Signs & Technology | 101%

## F1
F1: Total income and expenditure
£m | RP1 | 2020-21 | 2021-22
| Actual | Actual | FY Actual | Budget | Budget Difference
Operating expenditure
Operations and Maintenance (B1, B2, B3) | 2403.4 | 537.9 | 505.5108 | 497.2745 | -8.2363
Private Finance Initiative (PFI) payments (B5) | 2135.6 | 434.7 | 419.504 | 443.8458 | 24.3418
Corporate Support (C1) | 799.4 | 133 | 149.1658 | 114.545 | -34.6208
Business Services (C2) |  | 44.9 | 39.0863 | 43.9702 | 4.8839
Protocols (D1) | 240.4 | 55.5 | 63.463 | 73.6644 | 10.2015
Total resource expenditure | 5578.8 | 1206 | 1176.7299 | 1173.3 | -3.4299
Capital expenditure
RIS1 Enhancements (A1) | 7059.5 | 1727.2 | 1346.6938 | 1894.0077 | 547.3139
RIS 2 Enhancements (A2) |  | 292.5 | 421.7444 | 368.8936 | -52.8508
RIS3 Development (A3) | X | 21.3 | 54.6631 | 69.7215 | 15.0584
Designated Funds (A4) | X | 162.5 | 123.318 | 196.7228 | 73.4047
Other capital expenditure (A5) | X | 35.7 | 8.8526 | 0 | -8.8526
Operations (B1, B2) | X | 187.9 | 222.302 | 246.2656 | 23.9636
Maintenance and Renewals (B3) | 3494 | 759.6 | 881.0926 | 884.5218 | 3.4292
Business Costs (C1, C2) | X | 109.2 | 126.8408 | 156.4727 | 29.6319
Total capital expenditure | 12160.3637 | 3295.9 | 3185.5073 | 3816.6056 | 631.0983
Total expenditure | 17739.1652 | 4501.9 | 4362.2372 | 4989.9056 | 627.6684
Resource Expenditure by Type
Income | -182.2 | -47.2 | -60.5743 | -32.048 | 28.5263
Pay | 668.9 | 161.4 | 154.0543 | 164.3416 | 10.2874
Non-Pay | 314.45 | -41.6 | -37.8618 | -44.1907 | -6.3288
Projects | 4777.65 | 1133.4 | 1121.1003 | 1085.197 | -35.9033
Total resource expenditure | 5578.8 | 1206 | 1176.7185 | 1173.3 | -3.4185
Commentary:
Our total Opex was £1,177m, which was £3.4million (0.3%) more than funding. This relates entirely to the cost associated with traffic mitigation measures on the M20 (Operation Brock) near Dover in Kent. This position had been agreed with the Department as Brock was not funded in the RIS or the latest Spending Review. On Capex, total expenditure for the year is £3,185m, representing an underspend of £621m (16%) against the original funding of £3,816.6m agreed at SR20. We agreed to revise our funding for the year down to £3,086m, £731m below our original funding for the year. The majority of this (£556m) was rolled forward to be used later in RIS2 as part of Spending Review 2021, with a further £175m moved forward at the supplementary estimates. We ended up spending £100m more than our revised funding.

## F2
F2: Regional operating income and expenditure
£m | 2020-21 | 2021-22
| Actual | FY Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
Centrally managed | 136.8 | 110.8924 | 116.3355 | 5.4431
East | 59.4 | 59.0371 | 58.4336 | -0.60344
Midlands | 97.4 | 94.4202 | 89.1198 | -5.3004
North West | 73.7 | 72.2356 | 61.7571 | -10.4786
South East | 75.4 | 71.5382 | 71.7963 | 0.25807
South West | 46.5 | 44.0986 | 45.3754 | 1.2768
Yorkshire & North East | 48.6 | 53.2887 | 54.4569 | 1.1682
Subtotal | 537.9 | 505.5108 | 497.2745 | -8.2363
Private Finance Initiative (PFI) payments (B5)
Centrally managed | -116 | -84.7159 | -86.432 | -1.7161
East | 64.8 | 58.9324 | 68.9917 | 10.0593
Midlands | 11.1 | 10.9116 | 11.8777 | 0.96603
North West | 0 | 0 | 0 | 0
South East | 303.2 | 308.8152 | 314.1209 | 5.3058
South West | 28.2 | 23.0648 | 24.4498 | 1.385
Yorkshire & North East | 143.2 | 102.4958 | 110.8378 | 8.3419
Subtotal | 434.7 | 419.504 | 443.8458 | 24.3418
Corporate Support (C1)
Centrally managed | 127.2 | 142.207 | 114.545 | -27.662
East | 0 | 0.019178 | 0 | -0.019178
Midlands | 0 | 0.014612 | 0 | -0.014612
North West | 0 | 0.0020183 | 0 | -0.0020183
South East | 5.7 | 6.9139 | 0 | -6.9139
South West | 0 | 0 | 0 | 0
Yorkshire & North East | 0 | 0.0068448 | 0 | -0.0068448
Subtotal | 133 | 149.1636 | 114.545 | -34.6185
Business Services (C2)
Centrally managed | 44.9 | 38.9513 | 43.9702 | 5.0189
East | 0 | 0.001553 | 0 | -0.001553
Midlands | 0 | 0.0053641 | 0 | -0.0053641
North West | 0 | 0.033617 | 0 | -0.033617
South East | 0 | 0.000793 | 0 | -0.000793
South West | 0 | 0.093024 | 0 | -0.093024
Yorkshire & North East | 0 | 0.000709 | 0 | -0.000709
Subtotal | 44.9 | 39.0863 | 43.9702 | 4.8839
Protocols (D1)
Centrally managed | 32 | 39.157 | 49.2108 | 10.0537
East | 0 | 0 | 0 | 0
Midlands | 0.1 | 0.055872 | 0.055876 | 4e-06
North West | 0 | 0 | 0 | 0
South East | 0 | 0 | 0 | 0
South West | 10.5 | 11.3974 | 11.3974 | 0
Yorkshire & North East | 13 | 12.853 | 13.0004 | 0.14739
Subtotal | 55.5 | 63.4633 | 73.6644 | 10.2011
Total | 1206 | 1176.728 | 1173.3 | -3.428
Commentary:
Our total Opex was £1,177m, which was £3.4million (0.3%) more than funding. This relates entirely to the cost associated with traffic mitigation measures on the M20 (Operation Brock) near Dover in Kent. This position had been agreed with the Department as Brock was not funded in the RIS or the latest Spending Review. We started the year with £16million of overprogramming (or ‘running hot’). We were able to handle this through material windfall savings from lower traffic volumes resulting in lower contract costs on PFI and Dartcharge, and lower pay costs because of vacancies.

## F2.1
F2.1: Operating income and projects expenditure
£m |  | 2020-21 | 2021-22
|  | Actual | FY Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
| Pay | 85.6 | 82.0347 | 88.9153 | 6.8806
| Non-Pay | 12 | 20.1981 | 20.1571 | -0.041031
| Income | -38.8 | -48.1309 | -24.935 | 23.1959
Non-projects | Non-projects Subtotal | 58.8 | 54.102 | 84.1374 | 30.0354
Projects - Maintenance and Renewals | Routine Maintenance | 273.2 | 265.0861 | 231.5951 | -33.491
| Winter Maintenance | 3.7 | 2.5856 | 2.594 | 0.0083754
| Technology - Maintenance | 34.4 | 36.0021 | 37.7598 | 1.7577
| Renewal of Roads | 1.5 | 1.5984 | 1.2396 | -0.3588
| Renewal of Structures | 9.1 | 8.0111 | 12.0406 | 4.0295
| Other Maintenance | 2.8 | 1.3645 | 1 | -0.36446
Projects - General Operations | S274/S278 Works | 15.6 | 19.8604 | 2.3486 | -17.5118
| Technology | 37.2 | 12.0002 | 16.1197 | 4.1194
| Other | 68.6 | 71.2095 | 80.6994 | 9.4899
Projects - Customer Operations | Customer Operations | 32 | 33.6655 | 27.7405 | -5.925
1.2
| Projects Subtotal | 479.1 | 451.3834 | 413.1371 | -38.2463
| Total | 537.9 | 505.4854 | 497.2745 | -8.2108
PFI (Private Finance Initiative)
| Pay | 0 | 0 | 0 | 0
| Non-Pay | -81.2 | -86.4323 | -86.432 | 0.00028872
| Income | 0 | 0 | 0 | 0
Non-projects | Non-projects Subtotal | -81.2 | -86.4323 | -86.432 | 0.00028872
Projects | A1(M) Darrington to Dishforth | 62 | 58.4076 | 63.5981 | 5.1906
| A19 Dishforth to Tyne Tunnel | 71.1 | 28.9329 | 32.2001 | 3.2672
| A249 Iwade to Queenborough | 14 | 13.6487 | 14.0163 | 0.36762
| A30/A35 Exeter to Bere Regis | 9.6 | 9.753 | 10.0182 | 0.26515
| A419/A417 Swindon to Gloucester | 18.6 | 13.3118 | 14.4316 | 1.1198
| A50/A564 Stoke - Derby link | 11.1 | 10.9116 | 11.8777 | 0.96603
| A69 Carlisle to Newcastle | 11.5 | 11.6829 | 12.1729 | 0.49003
| M1-A1 Yorkshire link | 22.8 | 23.826 | 27.6484 | 3.8224
| M25 London Orbital Motorway contract | 289.2 | 295.1665 | 300.1046 | 4.9381
| M40 Junctions 1-15 | 40.6 | 38.5789 | 44.2099 | 5.631
| Other | -34.8 | 1.7164 | 0 | -1.7164
| Projects Subtotal | 515.9 | 505.9363 | 530.2778 | 24.3415
| Total | 434.7 | 419.504 | 443.8458 | 24.3418
Corporate Support (C1)
| Pay | 46.7 | 45.3657 | 47.9673 | 2.6016
| Non-Pay | 36.8 | 38.6274 | 31.5667 | -7.0607
| Income | -7.4 | -6.7682 | -6.8131 | -0.044864
Non-projects | Non-projects Subtotal | 76.1 | 77.2249 | 72.7609 | -4.464
Projects | Lands | 52.3 | 5.1538 | 0 | -5.1538
| Other | 4.6 | 66.8305 | 41.8241 | -25.0064
| Projects Subtotal | 56.9 | 71.9843 | 41.8641 | -30.1602
| Total | 133 | 149.2092 | 114.665 | -34.6242
Business Services (C2)
| Pay | 22.7 | 20.2039 | 21.3141 | 1.1102
| Non-Pay | -9.4 | -10.3358 | -10.1134 | 0.22245
| Income | -0.6 | -4.7096 | 0 | 4.7096
Non-projects | Non-projects Subtotal | 12.6 | 5.1584 | 11.2007 | 6.0423
Projects | Research and Development | 8.9 | 23.0347 | 22.4845 | -0.5502
| Other | 23.4 | 10.8939 | 10.285 | -0.60887
| Projects Subtotal | 32.3 | 33.9286 | 32.7695 | -1.1591
| Total | 44.9 | 39.0869 | 43.9702 | 4.8833
Protocols (D1)
| Pay | 6.5 | 6.4501 | 6.1451 | -0.30501
| Non-Pay | 0.2 | 0.080725 | 0.63088 | 0.55015
| Income | -0.3 | -0.93558 | -0.3 | 0.63558
Non-projects | Non-projects Subtotal | 6.4 | 5.5952 | 6.4759 | 0.88073
Projects |  | 49.2 | 57.8678 | 67.1885 | 9.3207
| Projects Subtotal | 49.2 | 57.8678 | 67.1885 | 9.3207
| Total | 55.5 | 63.463 | 73.6644 | 10.2015
| Total resource expenditure | 1206 | 1176.7485 | 1173.42 | -3.4085

## F2.2
F2.2: Analysis of protocols expenditure
£m | 2020-21 | 2021-22
| Actual | FY Actual | Budget | Budget Difference
Abnormal Loads | 0.8 | 1.5433 | 1.8443 | 0.30099
Dart Charge | 25.1 | 27.792 | 36.6558 | 8.8638
M6 Toll | 0.1 | 0.055872 | 0.055876 | 4e-06
Historical Railways Estate | 13 | 13.4371 | 13.0047 | -0.43241
National Salt Reserve | 0.5 | 1.0628 | 1.3267 | 0.26389
Severn Crossings | 14 | 17.4718 | 18.677 | 1.2052
Technical Regulations | 2.1 | 2.1 | 2.1 | 0
Total Protocols Expenditure | 55.5 | 63.463 | 73.6644 | 10.2015

## F2.3
F2.3: Analysis of FTE
Directorates £m | 2020-21 | 2021-22
| Actual | FY Actual | Budget | Budget Difference
Centrally Managed | 0 | 0 | 0 | 0
Commercial and Procurement | 439.1 | 454.9911 | 544.2868 | 89.2957
Communications and Corporate Affairs Directorate | 133.2 | 120.4405 | 128.046 | 7.6055
Finance and Business Services | 374.4 | 362.3093 | 371.662 | 9.3527
Human Resources | 109.3 | 111.5617 | 110.5394 | -1.0223
Major Projects | 784.5 | 814.6414 | 817.0623 | 2.4209
Lower Thames Crossing | 31.7 | 40 | 119 | 79
Operations | 3185.6 | 3261.2953 | 3634.4 | 373.1047
Digital Services Directorate | 229.2 | 246.2567 | 282.33 | 36.0733
Safety, Engineering and Standards | 410.1 | 397.4244 | 415.498 | 18.0736
Strategy and Planning | 169.5 | 174.9647 | 180.0818 | 5.1171
General Counsel | 43.2 | 51.6972 | 50.9 | -0.7972
FTE Total | 5909.7 | 6035.5823 | 6653.8063 | 618.224
Regions £m | 2020-21 | 2021-22
| Actual | Actual | Budget | Budget Difference
Centrally managed | 2599.6 | 2486.5994 | 2763.5186 | 276.9192
East | 632.6 | 530.4172 | 590.5697 | 60.1525
Midlands | 605.2 | 722.8375 | 735.8656 | 13.0281
North West | 645.3 | 621.437 | 641.381 | 19.944
South East | 526.3 | 707.8174 | 859.8872 | 152.0698
South West | 440.1 | 415.5052 | 456.948 | 41.4428
Yorkshire & North East | 460.5 | 550.9686 | 605.6362 | 54.6676
FTE Total | 5909.7 | 6035.5823 | 6653.8063 | 618.224

## F3
F3: Capital Expenditure
£m | Scheme name | 2020-21 | 2021-22
|  | Actual | FY Actual | Budget | Budget Difference
Maintenance and Renewals
| Renewal of Roads | 521.5 | 627.097 | 602.9332 | -24.1638
| Renewal of Structures | 176.2 | 194.6982 | 223.761 | 29.0628
| Renewal of Technology | 35.7 | 26.6715 | 30.9857 | 4.3142
| Maintenance | 26.2 | 32.626 | 26.8419 | -5.7841
| TOTAL Maintain/Renew | 759.5 | 881.0926 | 884.5218 | 3.4292
RIS1 Enhancements
| RIP | 654.6 | 708.5863 | 804.5833 | 95.997
| SMP | 876.9 | 448.9327 | 516.607 | 67.6743
| CIP | 131.6 | 97.2045 | 149.045 | 51.8404
| Other RIS1 expenditure including Portfolio Risk/Contingency and Surpus Funding | 64.2 | 91.9703 | 423.7725 | 331.8022
| Total RIS1 Enhancements | 1727.2 | 1346.6938 | 1894.0077 | 547.3139
RIS2 Enhancements
| RIP | 42 | 76.6949 | 58.1046 | -18.5903
| SMP | 14.4 | 190.148 | 117.7153 | -72.4327
| CIP | 0 | 9.7069 | 0.55708 | -9.1499
| Lower Thames Crossing | 235 | 136.7288 | 150.677 | 13.9482
| Other RIS2 expenditure including Portfolio Risk/Contingency | 1.1 | 8.4658 | 41.8397 | 33.3739
| Total RIS2 Enhancements | 292.5 | 421.7444 | 368.8936 | -52.8508
RIS3 Development
| RIS3 Development | 21.3 | 54.6631 | 69.7215 | 15.0584
| Total RIS3 Development | 21.3 | 54.6631 | 69.7215 | 15.0584
Designated Funds
| Environment and Wellbeing | 58.2 | 53.4041 | 92.1296 | 38.7255
| Innovation and Modernisation | 39.1 | 22.5683 | 39.5266 | 16.9583
| Safety and Congestion Fund | 33.6 | 18.7964 | 31.89 | 13.0936
| Users and Communities | 31.6 | 28.549 | 33.1765 | 4.6276
| Total Designated Funds | 162.5 | 123.318 | 196.7228 | 73.405
Operations, Business Costs and Other Capital
| Operations | 187.9 | 222.302 | 246.2656 | 23.9636
| Business Costs | 109.2 | 126.8408 | 156.4727 | 29.6319
| Other Capital | 35.7 | 8.8526 | 0 | -8.8526
| Total Operations, Business Costs, and Other Capital | 332.8 | 357.9954 | 402.7383 | 44.7429

## F3.1
F3: Enhancement expenditure
£m | Scheme name | DP ref RIS2 |  | PIN | Programme | Region | 2020-21 | 2021-22
[7 empty] | Actual | FY | Budget | Budget Difference
RIS1 Enhancements
| A1 Birtley to Coal House | 7 | 551462 | 551462 | Regional Investment Programme North |  | 13.1193 | 42.8325 | 43.5115 | 0.67892
| A1 Morpeth to Ellingham and A1 North of Ellingham | N/A for RIS2 - look against CB/Op plan using PIN to see the two elements of the scheme | 551459 | 551459 | Regional Investment Programme North |  | 20.0692 | 16.7549 | 18.9973 | 2.2424
| A1 Scotswood to North Brunton | 1 | 551461 | 551461 | Regional Investment Programme North |  | 33.2788 | 49.8229 | 47.9708 | -1.8521
| A12 Chelmsford to A120 | 45 | 551497 | 551497 | Regional Investment Programme South |  | 32.31 | 37.5918 | 41.2786 | 3.6867
| A14 Cambridge to Huntingdon | 37 | 528983 | 528983 | Complex Infrastructure Programme |  | 84.804 | 48.0071 | 49.365 | 1.3579
| A19 Down Hill Lane | 8 | 600636 | 600636 | Regional Investment Programme North |  | 14.9881 | 23.1712 | 24.7686 | 1.5974
| A19 Norton to Wynyard | 3 | 551457 | 551457 | Regional Investment Programme North |  | 46.9885 | 6.5371 | 8.3721 | 1.8351
| A19 Testos | 2 | 514495 | 514495 | Regional Investment Programme North |  | 46.3598 | 15.9979 | 15.8265 | -0.17147
| A2 Bean and Ebbsfleet | 60 | 543917 | 543917 | Regional Investment Programme South |  | 24.3915 | 28.9161 | 16.3489 | -12.5672
| A27 Arundel Bypass | 57 | 551523 | 551523 | Regional Investment Programme South |  | 14.0271 | 26.9656 | 32.205 | 5.2394
| A27 East of Lewes Package | 62 | 552988 | 552988 | Regional Investment Programme South |  | 14.7555 | 20.139 | 21.9953 | 1.8563
| A27 Worthing and Lancing improvements | 58 | 551524 | 551524 | Regional Investment Programme South |  | 0.2584 | 0 | 0 | 0
| A30 Chiverton to Carland Cross | 67 | 551502 | 551502 | Regional Investment Programme South |  | 43.2388 | 73.4245 | 99.4566 | 26.0322
| A303 Amesbury to Berwick Down | 65 | 551506 | 551506 | Complex Infrastructure Programme |  | 26.2264 | 21.1565 | 51.1 | 29.9435
| A303 Sparkford to Ilchester | 64 | 551507 | 551507 | Regional Investment Programme South |  | 8.624 | 15.1186 | 34.0257 | 18.9071
| A31 Ringwood | 59 | 551516 | 551516 | Regional Investment Programme South |  | 2.741 | 8.5525 | 8.0984 | -0.4541
| A34 Newbury to Oxford Enhancements | 48 | 556541 | 601572, 601567, 601561, 601555, 604572, 601568, 601571, 601559 | Operations Enhancements |  | 0.86328 | 3.6814 | 5.8418 | 2.1604
| A358 Taunton to Southfields | 66 | 551508 | 551508 | Regional Investment Programme South |  | 7.7588 | 18.3118 | 14.924 | -3.3878
| A38 Derby Junctions | 27 | 514503 | 514503 | Regional Investment Programme North |  | 11.2493 | 8.1463 | 8.0978 | -0.048461
| A428 Black Cat to Caxton Gibbet | 44 | 551495 | 551495 | Complex Infrastructure Programme |  | 24.9242 | 28.0409 | 48.58 | 20.539
| A45/A6 Chowns Mill Junction | 25 | 559864 | 559864 | Operations Enhancements |  | 13.7 | 10.609 | 7.869 | -2.74
| A46 Coventry Junctions Binley | 23 |  |  | Regional Investment Programme North |  | 16.0239 | 33.289 | 29.7585 | -3.5305
| A47 Blofield to North Burlingham | 43 | 551490 | 551490 | Regional Investment Programme South |  | 4.0033 | 5.0794 | 10.5586 | 5.4792
| A47 Guyhirn Junction | 40 | 551493 | 551493 | Regional Investment Programme South |  | 4.38 | 6.2974 | 4.896 | -1.4013
| A47 North Tuddenham to Easton | 41 | 551489 | 551489 | Regional Investment Programme South |  | 7.7071 | 6.8728 | 6.9755 | 0.1027
| A47 Thickthorn Junction | 42 | 551492 | 551492 | Regional Investment Programme South |  | 3.2825 | 5.5227 | 5.5828 | 0.060088
| A47 Wansford to Sutton | 38 | 551494 | 551494 | Regional Investment Programme South |  | 2.9343 | 3.1544 | 5.5776 | 2.4231
| A5 Dodwells to Longshoot | N/A for RIS2 - look at CB/Op Plan using the PIN for scheme detail | 559863 | 559863 | Operations Enhancements |  | -0.012546 | 0 | 0.25 | 0.25
| A500 Etruria | 20 | 551483 | 551483 | Regional Investment Programme North |  | 1.0972 | 0.58599 | 0.12677 | -0.45922
| A5036 Princess Way | 15 | 549387 | 549387 | Regional Investment Programme North |  | 1.3444 | 1.1738 | 4.085 | 2.9111
| A52 Nottingham Junctions | 30 | 556304 | 556304 | Regional Investment Programme North |  | 1.9943 | 4.8 | 7.0005 | 2.2
| A585 Windy Harbour to Skippool | 11 | 548643 | 548643 | Regional Investment Programme North |  | 23.564 | 46.3471 | 49.9506 | 3.6035
| A61 Westwood Roundabout | 5 | 551468 | 551468 | Regional Investment Programme North |  | 13.6425 | 1.6883 | 1.3653 | -0.32296
| A63 Castle Street | 9 | 514508 | 514508 | Regional Investment Programme North |  | 48.5344 | 52.1836 | 47.4443 | -4.7393
| M1 Junctions 13-19 | 26 | 549348 | 549348 | Smart Motorway Programme |  | 165.8621 | 82.9244 | 83.7488 | 0.82442
| M2 Junction 5 | 61 | 551521 | 551521 | Regional Investment Programme South |  | 4.0936 | 8.1038 | 13.5174 | 5.4135
| M25 Junction 10 | 54 | 551522 | 551522 | Regional Investment Programme South |  | 13.4572 | 6.1864 | 38.7204 | 32.534
| M25 Junction 25 | 51 | 551518 | 551518 | Regional Investment Programme South |  | 3.8785 | 11.3373 | 13.4347 | 2.0974
| M25 Junction 28 | 52 | 551519 | 551519 | Regional Investment Programme South |  | 6.5705 | 7.0508 | 6.3269 | -0.72392
| M25 Junctions 10-16 | 53 | 551532 | 551532 | Smart Motorway Programme |  | 5.1074 | 9.4549 | 7.7001 | -1.7548
| M27 Junctions 4-11 | 50 | 549344 | 549344 | Smart Motorway Programme |  | 125.7276 | 50.3682 | 21.1887 | -29.1795
| M27 Southampton Junction 8 | 56 | 551514 | 551514 | Regional Investment Programme South |  | 1.7206 | 2.862 | 7.1354 | 4.2734
| M3 Junction 9 | 55 | 551511 | 551511 | Regional Investment Programme South |  | 5.0213 | 4.7007 | 3.5611 | -1.1397
| M3 Junctions 9-14 | 49 | 549338 | 549338 | Smart Motorway Programme |  | 9.8587 | 25.56 | 62.5906 | 37.0306
| M4 Junctions 3-12 | 47 | 514451 | 514451 | Smart Motorway Programme |  | 329.8769 | 156.5455 | 175.3542 | 18.8086
| M40/M42 Interchange | 24 | 551530 | 551530 | Smart Motorway Programme |  | 4.7979 | 11.3446 | 17.5494 | 6.2048
| M42 Junction 6 | 22 | 551485 | 551485 | Regional Investment Programme North |  | 23.7923 | 44.7778 | 41.2003 | -3.5775
| M54-M6 Link Road | 28 | 514465 | 514465 | Regional Investment Programme North |  | 7.8346 | 8.0531 | 9.281 | 1.2279
| M56 Junctions 6-8 | 18 | 549345 | 549345 | Smart Motorway Programme |  | 18.1315 | 32.8062 | 41.8759 | 9.0697
| M6 Junction 10 | 31 | 551484 | 551484 | Regional Investment Programme North |  | 14.7413 | 19.5 | 12.1833 | -7.3168
| M6 Junction 19 | 13 | 548641 | 548641 | Regional Investment Programme North |  | 26.0602 | 12.56 | 10.6093 | -1.9507
| M6 Junctions 13-15 | 21 | 549346 | 549346 | Smart Motorway Programme |  | 97.7331 | 6.3389 | 7.179 | 0.84007
| M6 Junctions 21a-26 | 16 | 549339 | 549339 | Smart Motorway Programme |  | 10.815 | 59.8081 | 79.9086 | 20.1005
| M62 Junctions 20-25 | 12 | 551534 | 551534 | Smart Motorway Programme |  | 8.1442 | 11.5581 | 10.9682 | -0.58985
| M621 Junctions 1-7 | 4 | 551464 | 551464 | Regional Investment Programme North |  | 2.9102 | 2.0822 | 12.5242 | 10.442
| Mottram Moor Link Road & A57 Link Road | 17 | 551473 | 551473 | Regional Investment Programme North |  | 5.7936 | 9.3326 | 8.5685 | -0.76416
| A47 Great Yarmouth Junctions | 39 | 551491 | 551491 | Operations Enhancements |  | 0.092442 | 1.542 | 0.865 | -0.67696
| Other RIS1 expenditure |  |  |  | Centrally Managed |  | 222.0569 | 91.1238 | 435.8124 | 344.6891
| Total RIS1 Enhancements | [5 empty] | 1727.2492 | 1346.6938 | 1894.0077 | 547.3139
RIS2 Enhancements
| A46 Newark Bypass | 32 | 551478 | 551478 | Regional Investment Programme North |  | 1.1863 | 4.0551 | 3.9244 | -0.13078
| A417 Air Balloon | 68 | 551505 | 551505 | Regional Investment Programme South |  | 17.858 | 15.7419 | 21.0039 | 5.262
| M60/M62/M66 Simister Island Interchange | 19 | 548642 | 548642 | Regional Investment Programme North |  | 1.2501 | 6.071 | 9.0491 | 2.9781
| Lower Thames Crossing | 63 | 540039 | 540039 | Complex Infrastructure Programme |  | 234.9985 | 136.7288 | 150.677 | 13.9482
| A66 Northern Trans-Pennine | 14 | 565627 | 565627 | Regional Investment Programme North |  | 13.7437 | 42.3108 | 22.0218 | -20.2891
| M4 Junctions 19-20 and M5 Junctions 16-17 | 69 | 608068 | 608068 | Smart Motorway Programme |  | 0.15683 | 2.0437 | 1.0347 | -1.009
| M42 Junctions 4-7 | 33 | 608072 | 608072 | Smart Motorway Programme |  | 0.21848 | 0.79589 | 0.78164 | -0.014251
| M6 Junctions 4-5 | 34 | 608069 | 608069 | Smart Motorway Programme |  | 0.37552 | 4.4489 | 10.2366 | 5.7877
| M6 Junctions 5-8 | 35 | 608070 | 608070 | Smart Motorway Programme |  | 0.26256 | 1.2269 | 3.0852 | 1.8583
| M6 Junctions 8-10a | 36 | 608071 | 608071 | Smart Motorway Programme |  | 0.17451 | 2.202 | 2.4134 | 0.21134
| M62 Junctions 25-30 | 10 | 608073 | 608073 | Operations Enhancements |  | 0.2178 | 3.7966 | 3.9412 | 0.14463
| M1 J10-13 DHS to ALR upgrade | 46 | 608074 | 608074 | Smart Motorway Programme |  | 0.2 | 1.4476 | 6.351 | 4.9034
| A21 Safety Package | 70 |  |  | Operations Enhancements |  | 0 | 0.090804 | 4 | 3.9092
| Other RIS2 expenditure |  |  |  | Centrally Managed |  | 21.9 | 200.7842 | 130.3736 | -70.4106
| Total RIS2 Enhancements | [5 empty] | 292.4545 | 421.7444 | 368.8936 | -52.8508

## F3.2
F3.2: Regional capital income and expenditure
£m | 2020-21 | 2021-22
| Actual | FY Actual | Budget | Budget Difference
Maintenance & Renewals
Centrally managed | 18.5 | 29.7423 | 26.1032 | -3.6391
East | 128.5 | 246.0127 | 259.8325 | 13.8197
Midlands | 164.7 | 132.2056 | 124.0332 | -8.1724
North West | 130.7 | 136.1097 | 132.9538 | -3.1558
South East | 112.9 | 118.3229 | 114.5807 | -3.7422
South West | 95.2 | 99.7892 | 91.9622 | -7.827
Yorkshire & North East | 109 | 118.9058 | 135.056 | 16.1503
Subtotal | 759.5 | 881.0882 | 884.5218 | 3.4336
RIS1 Enhancements
Centrally managed | 5.3 | 83.402 | 385.735 | 302.333
East | 178.7 | 142.0884 | 175.8664 | 33.778
Midlands | 375.5 | 212.1912 | 233.1062 | 20.9149
North West | 157.2 | 165.9784 | 195.8306 | 29.8522
South East | 648.6 | 379.6689 | 453.2916 | 73.6227
South West | 102 | 135.2353 | 209.2799 | 74.0446
Yorkshire & North East | 260.1 | 228.1296 | 240.8981 | 12.7685
Subtotal | 1727.2 | 1346.6938 | 1894.0077 | 547.3139
RIS2 Enhancements
Centrally managed | 13.8 | 118.0645 | 131.5902 | 13.5257
East | 6.5 | 5.8983 | 3.3423 | -2.556
Midlands | 2.5 | 44.5394 | 26.7922 | -17.7472
North West | 14.9 | 48.3439 | 31.0709 | -17.273
South East | 235.4 | 182.6014 | 148.53 | -34.0714
South West | 19 | 17.7856 | 22.0386 | 4.253
Yorkshire & North East | 0.4 | 4.5113 | 5.5294 | 1.0181
Subtotal | 292.5 | 421.7444 | 368.8936 | -52.8508
RIS3 Development
Centrally managed | 6 | 24.1926 | 26.216 | 2.0235
East | 0 | 0 | 0 | 0
Midlands | 0.8 | 5.4039 | 6.3346 | 0.93067
North West | 5 | 1.6688 | 0.64882 | -1.02
South East | 5.9 | 17.4762 | 27.2303 | 9.7542
South West | 1.2 | 1.1829 | 3.4163 | 2.2334
Yorkshire & North East | 2.4 | 4.7387 | 5.8754 | 1.1367
Subtotal | 21.3 | 54.6631 | 69.7215 | 15.0584
Designated Funds
Centrally managed | 58.5 | 34.3032 | 80.3458 | 46.0425
East | 9.8 | 10.0223 | 22.3879 | 12.3656
Midlands | 10 | 19.4712 | 16.6979 | -2.7733
North West | 15 | 13.1942 | 16.1953 | 3.0011
South East | 27.1 | 20.1025 | 26.8073 | 6.7049
South West | 22.5 | 19.3547 | 24.8929 | 5.5382
Yorkshire & North East | 19.6 | 6.8699 | 9.3956 | 2.5257
Subtotal | 162.5 | 123.318 | 196.7228 | 73.4047
Operations, Business Costs, and Other Capital Expenditure
Centrally managed | 260.6 | 308.4586 | 357 | 48.5414
East | 4.4 | 5.2847 | 6.2027 | 0.918
Midlands | 7.4 | 5.5051 | 6.4515 | 0.94644
North West | 7.0 | 9.8427 | 10.4564 | 0.61373
South East | 44.7 | 19.2805 | 12.8396 | -6.441
South West | 3.5 | 3.2998 | 4.2425 | 0.94275
Yorkshire & North East | 5.2 | 6.3241 | 5.5456 | -0.77846
Subtotal | 332.8 | 357.9954 | 402.7383 | 44.7429
Total | 3,295.8 | 3185.5029 | 3816.6056 | 631.1027
Commentary:
On Capex, total expenditure for the year is £3,185m, representing an underspend of £631m (16%) against the original funding of £3,816.6m agreed at SR20. We agreed to revise our funding for the year down to £3,086m, £731m below our original funding for the year. The majority of this (£556m) was rolled forward to be used later in RIS2 as part of Spending Review 2021, with a further £175m moved forward at the supplementary estimates. We ended up spending £100m more than our revised funding. The £556m of reprofiled funding consisted of: • £367million surplus which was identified at the beginning of the year (£290m DCO delays and £77m of other enhancements) • £47million of Designated Funds investment reprofiled to future years • £142m of other reprofiled costs including £72m further DCO delays arising in year, and £70m covering unallocated Risk Reserve and Lease costs which were not required The remainder of the underspend is driven by further movements that were baked into the Supplementary Estimates forecast and will be flexed into future years. At the year end we had strong delivery meaning that the underspend was not as large as originally planned, improving the position for future years' delivery.
Note on A52: Rowlands, Charlotte: Corporate Support, Business Services, Other Capital, Operate General, Support General