## Contents Page
These statements are the primary sources of information National Highways' performance in accordance with the ORR Monitoring Guidelines1
Notes
- Detailed information regarding efficiency delivery and statement in relation to inflationary impact will be contained in the published National Highways Efficiency Report
- Regional data for 2022-23 has been published on the National Highways website.
Contents
Performance Specification statements
PS1 | Improving safety for all
PS2 | Providing fast and reliable journeys
PS3 | A well maintained and resilient network
PS4 | Delivering better environmental outcomes
PS5 | Meeting the needs of all road users
PS6 | Achieving efficient delivery
Investment Plan statements
IP1 | Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
IP2 | RIS 3 Development Pipeline
IP3 | Designated Funds
IP4 | Renewal Volume Reporting
IP5 | Maintenance Delivery Reporting
Financial Performance statements
F1 | Total income and expenditure
F2 | Regional resource income and expenditure
F2.1 | Resource income and projects expenditure
F2.2 | Analysis of protocols expenditure
F3 | Capital expenditure
F3.1 | Enhancement expenditure
F3.2 | Regional capital income and expenditure
Annual Statement
This report and its contents are taken as the Board’s statement of compliance with National Highway’s Licence and Framework Document obligations. It also confirms that National Highways maintains an effective assurance regime for the expenditure of public money and that its decision making meets the criteria set out in the National Highways Framework Document. This report constitutes National Highways’ annual progress report under clause 6.26 of the Licence. To the best of the Board’s knowledge and belief, having made all reasonable enquiries, the information contained in this document and the accompanying performance monitoring statements is set out appropriately. The Directors’ report was approved by the Board on 29 June 2023 and is signed on their behalf by: Nick Harris, CEO
1 https://www.orr.gov.uk/sites/default/files/om/monitoring-reporting-guidelines-for-highways-england-for-road-period-2.pdf
Note - The Performance and Monitoring Statements 2022-23 has been made available with the publication code PR28/23.

## TestforRenata (hidden)
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS1: Improving safety for all |  |  | For a definition of the metric and parameters for measuring and monitoring safety performance see National Highways’ Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
The number of people killed or seriously injured on the SRN.
Ongoing reduction in the number of people killed or seriously injured on the SRN as reported in STATS19 to support a decrease of at least 50% by the end of 2025 against the 2005-09 average baseline. A +/- variance of 5% each year has been agreed with DfT Road User Safety Division to support this target.
Note: baseline will change each year as adjusted figures are produced
2005-09 baseline | Performance Specification | 3,094 (original)
2,321 (revised)
2015 | Unadjusted | 1,784 (original) | 1,750 (original) | KPI | 34 (original)
| Adjusted | 2,328 (revised) | 2,332 (revised) |  | -4 (revised)
2016 | Unadjusted | 2,005 (original) | 1,678 (original) | KPI | 327 (original)
| Adjusted | 2,263 (revised) | 2,237 (revised) |  | 26 (revised)
2017 | Unadjusted | 1,853 (original) | 1,607 (original) | KPI | 246 (original)
| Adjusted | 2,072 (revised) | 2,142 (revised) |  | -70 (revised)
2018 | Unadjusted | 1,987 (original) | 1,536 (original) | KPI | 451 (original)
| Adjusted | 2,178 (revised) | 2,047 (revised) |  | 131 (revised)
2019 | Unadjusted | 1,948 (original) | 1,464 (original) | KPI | 484 (original)
| Adjusted | 2,060 (revised) | 2,096 (revised) |  | -36 (revised)
2020 | Unadjusted Adjusted | 1,288 (original) 1,397 (revised) | 1,393 (original) 1,875 (revised) | KPI | -105 (original) -478 (revised)
2021 | Adjusted |  |  | KPI | 0
2022 | Adjusted |  |  | KPI | 0
2023 | Adjusted |  |  | KPI | 0
2024 | Adjusted |  |  | KPI | 0
2025 | Adjusted |  |  | KPI | 0
This box is being filled in as a Test
PIs
The total number of people killed or injured on the SRN.
Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer.
2015 | Performance Specification | 16375 | N/A | PI | N/A
2016 | Performance Specification | 16233 | N/A | PI | N/A
2017 | Performance Specification | 14225 | N/A | PI | N/A
2018 | Performance Specification | 13380 | N/A | PI | N/A |  | 7988 | 8387 | 16375
2019 | Performance Specification | 12347 | N/A | PI | N/A |  | 7792 | 8441 | 16233
2020 | Performance Specification | 7873 | N/A | PI | N/A |  | 6930 | 7295 | 14225
2021 | Performance Specification |  | N/A | PI | N/A |  | 6507 | 6873 | 13380
2022 | Performance Specification |  | N/A | PI | N/A |  | 1948 | 10399 | 12347
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 shows that all casualties have reduced to 7,873, representing a decrease of 36.2% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The number of non-motorised and motorcyclist users killed or injured on the SRN.
The total number of pedestrian, pedal cyclist, motorcyclist and equestrian casualties on the SRN. Disaggregation will be provided by road user group to assist understanding of the PI but are not considered PIs in their own right.
2015 | Performance Specification | 1160 | N/A | PI | N/A
2016 | Performance Specification | 1170 | N/A | PI | N/A
2017 | Performance Specification | 1050 | N/A | PI | N/A
2018 | Performance Specification | 1036 | N/A | PI | N/A
2019 | Performance Specification | 962 | N/A | PI | N/A
2020 | Performance Specification | 605 | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 reports that the total number of vulnerable road user casualties on the Strategic Road Network has reduced to 605. This represents a decrease of 37% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The number of motorcyclist users killed or injured on the SRN.
2015 | Performance Specification | 849 | N/A | N/A | N/A
2016 | Performance Specification | 864 | N/A | N/A | N/A
2017 | Performance Specification | 760 | N/A | N/A | N/A
2018 | Performance Specification | 785 | N/A | N/A | N/A
2019 | Performance Specification | 694 | N/A | N/A | N/A
2020 | Performance Specification | 404 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in motorcyslist casualties on the SRN from 2019.
The number of cyclists killed or injured on the SRN.
2015 | Performance Specification | 153 | N/A | N/A | N/A
2016 | Performance Specification | 152 | N/A | N/A | N/A
2017 | Performance Specification | 137 | N/A | N/A | N/A
2018 | Performance Specification | 103 | N/A | N/A | N/A
2019 | Performance Specification | 112 | N/A | N/A | N/A
2020 | Performance Specification | 99 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in cyclist casualties on the SRN from 2019.
The number of pedestrians killed or injured on the SRN.
2015 | Performance Specification | 158 | N/A | N/A | N/A
2016 | Performance Specification | 154 | N/A | N/A | N/A
2017 | Performance Specification | 153 | N/A | N/A | N/A
2018 | Performance Specification | 148 | N/A | N/A | N/A
2019 | Performance Specification | 156 | N/A | N/A | N/A
2020 | Performance Specification | 102 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows a decrease in pedestrian casualties on the SRN from 2019.
The number of equestrians killed or injured on the SRN.
2015 | Performance Specification | 0 | N/A | N/A | N/A
2016 | Performance Specification | 0 | N/A | N/A | N/A
2017 | Performance Specification | 0 | N/A | N/A | N/A
2018 | Performance Specification | 0 | N/A | N/A | N/A
2019 | Performance Specification | 0 | N/A | N/A | N/A
2020 | Performance Specification | 0 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2020 shows no equestrian casualties on the SRN.
Number of injury collisions on the SRN
The total number of collisions recorded that resulted in at least one injury (of any severity) on the SRN.
2020 | Performance Specification | 5267 | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 reports that the total number of injury collisions on the Strategic Road Network has reduced to 5,267. This represents a decrease of 26% from 2019. Safety data continues to be reported by calendar year, with the validated results released by the DfT in September 2021. This explains the lag in performance reported.
The accident frequency rate for National Highways staff
The accident frequency rate for National Highways staff based on Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.05 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The rolling 12-month AFR at March 2022 is 0.05 (consistent with March 2021). The AFR is based on 7 RIDDORs in the last 12 months.
The accident frequency rate for National Highways supply chain staff
The accident frequency rate for National Highways supply chain staff based on Reporting of Injuries Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.07 | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The rolling 12-month AFR at March 2022 is 0.07. This represents a slight increase since March 2021 reported 0.05. The AFR is based on 27 RIDDORs in the last 12 months.
The % of traffic using iRAP 3* or above rated roads
IRAP based road safety investigations, developed in conjunction with the department, to feed into subsequent route strategies. Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer. We are committed to ensure that 90% of travel on our roads is 3* rated or higher by 2020. The latest data indicates that 95% of travel on our roads is on 3-star rated roads or above which exceeds the target set in our delivery plan The percentage of travel on roads with an International Road Assessment Programme (iRAP) safety rating of 3-star or better calculated using the latest version of the iRAP model (version 3.02).
2020-21 | Performance Specification | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 89% | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Work has been completed to assess the star rating of our network using the iRAP Safety Rating Model v3.02. This has generated a baseline star rating assessment for the network at 2020 and provides a 2025 forecast which takes into account our current planned major investment programmes.
Commitments
Work with Transport Focus to investigate a rate-based measure for non-motorised user casualties. |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in April 2022.
1.1 Working with TF, investigate a rate-based measure for non-motorised user casualties
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | Following discussions with DfT, ORR and Transport Focus in December, it was then agreed to not progress further development.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
iRAP baseline to be established in 2021, and 2025 forecast developed, based on latest iRAP methodology. |  | Commitment completed. The metric has passed the Development milestones and will provide a baseline star rating assessment for our current network, as well as a 2025 forecast which considers current planned major investment programmes.
1.2 iRAP baseline to be established in 2021, and 2025 forecast and development, based on latest IRAP methodology
OMM Stages | Milestone
Concept Stage | N/A | N/A
Feasibility Stage | N/A | N/A
Development Stage | Q2 2021-22 | N/A
Validation Stage | N/A | N/A
Notes and commentary

## PS1-Improving safety for all
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS1: Improving safety for all |  |  | For a definition of the metric and parameters for measuring and monitoring safety performance see National Highways’ Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
The number of people killed or seriously injured on the SRN.
Ongoing reduction in the number of people killed or seriously injured on the SRN as reported in STATS19 to support a decrease of at least 50% by the end of 2025 against the 2005-09 average baseline. A +/- variance of 5% each year has been agreed with DfT Road User Safety Division to support this target.
Note: baseline will change each year as adjusted figures are produced
2005-09 baseline | Performance Specification | 3,094 (original)
2,321 (revised)
2015 | Unadjusted | 1,784 (original) | 1,750 (original) | KPI | 34 (original)
| Adjusted | 2,328 (revised) | 2,332 (revised) |  | -4 (revised)
2016 | Unadjusted | 2,005 (original) | 1,678 (original) | KPI | 327 (original)
| Adjusted | 2,263 (revised) | 2,237 (revised) |  | 26 (revised)
2017 | Unadjusted | 1,853 (original) | 1,607 (original) | KPI | 246 (original)
| Adjusted | 2,072 (revised) | 2,142 (revised) |  | -70 (revised)
2018 | Unadjusted | 1,987 (original) | 1,536 (original) | KPI | 451 (original)
| Adjusted | 2,178 (revised) | 2,047 (revised) |  | 131 (revised)
2019 | Unadjusted | 1,948 (original) | 1,464 (original) | KPI | 484 (original)
| Adjusted | 2,060 (revised) | 2,096 (revised) |  | -36 (revised)
2020 | Unadjusted Adjusted | 1,288 (original) 1,397 (revised) | 1,393 (original) 1,875 (revised) | KPI | -105 (original) -478 (revised)
2021 | Unadjusted Adjusted | 1,692 (original) 1,857 (revised) | 1,346 (original) 1,859 (revised) | KPI | -2 (revised)
2022 | Adjusted |  |  | KPI | 0
2023 | Adjusted |  |  | KPI | 0
2024 | Adjusted |  |  | KPI | 0
2025 | Adjusted |  |  | KPI | 0
In 2021, the number of people killed or seriously injured reduced by 42% against our 2005-2009 baseline. Fatalities reduced by 38% Casualties overall were 55% lower and the number of child casualties reduced by 52%. These casualties were from 6,539 collisions, which is 53% fewer collisions compared to the baseline average. Of those collisions, 1,575 resulted in death or serious injury, a 41% decrease on the baseline. It must be noted that in 2021, it was a partial Covid year and did not have the full yearly traffic flows.
PIs
The total number of people killed or injured on the SRN.
Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer.
2015 | Performance Specification | 16375 | N/A | PI | N/A
2016 | Performance Specification | 16233 | N/A | PI | N/A
2017 | Performance Specification | 14225 | N/A | PI | N/A
2018 | Performance Specification | 13380 | N/A | PI | N/A |  | 7988 | 8387 | 16375
2019 | Performance Specification | 12347 | N/A | PI | N/A |  | 7792 | 8441 | 16233
2020 | Performance Specification | 7873 | N/A | PI | N/A |  | 6930 | 7295 | 14225
2021 | Performance Specification | 9819 | N/A | PI | N/A |  | 6507 | 6873 | 13380
2022 | Performance Specification |  | N/A | PI | N/A |  | 1948 | 10399 | 12347
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
This represents a 25 per cent increase in casualties on SRN compared with 2020.
The number of non-motorised and motorcyclist users killed or injured on the SRN.
The total number of pedestrian, pedal cyclist, motorcyclist and equestrian casualties on the SRN. Disaggregation will be provided by road user group to assist understanding of the PI but are not considered PIs in their own right.
2015 | Performance Specification | 1160 | N/A | PI | N/A
2016 | Performance Specification | 1170 | N/A | PI | N/A
2017 | Performance Specification | 1050 | N/A | PI | N/A
2018 | Performance Specification | 1036 | N/A | PI | N/A
2019 | Performance Specification | 962 | N/A | PI | N/A
2020 | Performance Specification | 605 | N/A | PI | N/A
2021 | Performance Specification | 803 | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Pedestrians and motorcyclists accounted for 19 and 10 per cent of all fatalities respectively.
The number of motorcyclist users killed or injured on the SRN.
2015 | Performance Specification | 849 | N/A | N/A | N/A
2016 | Performance Specification | 864 | N/A | N/A | N/A
2017 | Performance Specification | 760 | N/A | N/A | N/A
2018 | Performance Specification | 785 | N/A | N/A | N/A
2019 | Performance Specification | 694 | N/A | N/A | N/A
2020 | Performance Specification | 404 | N/A | N/A | N/A
2021 | Performance Specification | 547 | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Motorcycle user fatalities increased by 44 per cent to 23 on the SRN compared with 2020.
The number of cyclists killed or injured on the SRN.
2015 | Performance Specification | 153 | N/A | N/A | N/A
2016 | Performance Specification | 152 | N/A | N/A | N/A
2017 | Performance Specification | 137 | N/A | N/A | N/A
2018 | Performance Specification | 103 | N/A | N/A | N/A
2019 | Performance Specification | 112 | N/A | N/A | N/A
2020 | Performance Specification | 99 | N/A | N/A | N/A
2021 | Performance Specification | 113 | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Pedal cyclist fatalities increased by 2 from 1 in 2020.
The number of pedestrians killed or injured on the SRN.
2015 | Performance Specification | 158 | N/A | N/A | N/A
2016 | Performance Specification | 154 | N/A | N/A | N/A
2017 | Performance Specification | 153 | N/A | N/A | N/A
2018 | Performance Specification | 148 | N/A | N/A | N/A
2019 | Performance Specification | 156 | N/A | N/A | N/A
2020 | Performance Specification | 102 | N/A | N/A | N/A
2021 | Performance Specification | 143 | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
42 pedestrians were killed, 83 percent higher than in 2020.
The number of equestrians killed or injured on the SRN.
2015 | Performance Specification | 0 | N/A | N/A | N/A
2016 | Performance Specification | 0 | N/A | N/A | N/A
2017 | Performance Specification | 0 | N/A | N/A | N/A
2018 | Performance Specification | 0 | N/A | N/A | N/A
2019 | Performance Specification | 0 | N/A | N/A | N/A
2020 | Performance Specification | 0 | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
No equastrians were killed or injured on SRN.
Number of injury collisions on the SRN
The total number of collisions recorded that resulted in at least one injury (of any severity) on the SRN.
2020 | Performance Specification | 5267 | N/A | PI | N/A
2021 | Performance Specification | 6539 | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
There were 6,539 reported road injury collisions on the SRN, 53 per cent fewer compared with the 2005 to 2009 baseline values.
The accident frequency rate for National Highways staff
The accident frequency rate for National Highways staff based on Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.05 | N/A | PI | N/A
2022-23 | Performance Specification | 0.03 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The National Highways employee AFR to March 2023 remained at 0.03. This is based on 4 RIDDORs in the last 12 months.
The accident frequency rate for National Highways supply chain staff
The accident frequency rate for National Highways supply chain staff based on Reporting of Injuries Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification | 0.07 | N/A | PI | N/A
2022-23 | Performance Specification | 0.08 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The overall Supply Chain 12 month rolling AFR to March 2023 remained at 0.08. There have been 28 RIDDORs in the rolling 12-month period.
The % of traffic using iRAP 3* or above rated roads
IRAP based road safety investigations, developed in conjunction with the department, to feed into subsequent route strategies. Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer. We are committed to ensure that 90% of travel on our roads is 3* rated or higher by 2020. The latest data indicates that 95% of travel on our roads is on 3-star rated roads or above which exceeds the target set in our delivery plan The percentage of travel on roads with an International Road Assessment Programme (iRAP) safety rating of 3-star or better calculated using the latest version of the iRAP model (version 3.02).
2020-21 | Performance Specification | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 89% | N/A | PI | N/A
2022-23 | Performance Specification | 89% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This was reviewed in 2021-22 and there is no change year on year. These results will stand until the 2025 survey and will be reportable in 2026-27 financial year.
Commitments
Work with Transport Focus to investigate a rate-based measure for non-motorised user casualties. |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in April 2022.
1.1 Working with TF, investigate a rate-based measure for non-motorised user casualties
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | Following discussions with DfT, ORR and Transport Focus in December, it was then agreed to not progress further development.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
iRAP baseline to be established in 2021, and 2025 forecast developed, based on latest iRAP methodology. |  | Commitment completed. The metric has passed the Development milestones and will provide a baseline star rating assessment for our current network, as well as a 2025 forecast which considers current planned major investment programmes.
1.2 iRAP baseline to be established in 2021, and 2025 forecast and development, based on latest IRAP methodology
OMM Stages | Milestone
Concept Stage | N/A | N/A
Feasibility Stage | N/A | N/A
Development Stage | Q2 2021-22 | N/A
Validation Stage | N/A | N/A
Notes and commentary

## PS2-Fast and reliable
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS2: Providing fast and reliable journeys |  | For a definition of the metric and parameters for measuring and monitoring User satisfaction see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
Average Delay
Average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Ambition – Performance to be no worse at the end of Road Period 2 than it is at the end of Road Period 1. National Highways will be required to demonstrate how it has acted to reduce delays in support of this ambition. This KPI does not have a target.
2020-21 | Performance Specification | 6.7 | 9.5 | KPI
2021-22 | Performance Specification | 8.8 | 9.5 | KPI
2022-23 | Performance Specification | 9.5 | 9.5 | KPI
2023-24 | Performance Specification |  | 9.5 | KPI
2024-25 | Performance Specification |  | 9.5 | KPI
In 2022-23 the average delay was 9.5 seconds per vehicle per mile. Average delay has continued a broad upwards trend to near pre-Covid-19 levels, This metric measures average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Roadworks Network Impact
The metric measures the lane-meter-days multiplied by a weighting factor to give an impact figure on the Strategic Road Network (SRN). It captures the records of Traffic Management (TM) restrictions by length and duration on the SRN and applies a weighting for each TM category.
Target: Roadworks Network Impact (weighted lane meter days) to not exceed a monthly average of: 43 million in 2021/22; 47 million in 2022/22; 48 million in 2023/24; and 47 million in 2024/25.
2020-21 | N/A | N/A | N/A (Not to exceed) | N/A | N/A
2021-22 | Performance Specification | 42.7 | 43 | KPI | -0.2m
2022-23 | Performance Specification | 42.3 | 47 | KPI | 0%
2023-24 | Performance Specification |  | 48 | KPI | 0%
2024-25 | Performance Specification |  | 47 | KPI | 0%
This metric indicates the level of roadwork activity on the Strategic Road Network (SRN). National Highways was successful in not exceeding the 47 million (weighted lane metre days) monthly average in 2022-23.
Incident clearance rate
The percentage of incidents on the motorway that impact traffic flow but are cleared in less than one hour.
Target: 86% of motorway incidents cleared within one hour.
2020-21 | Performance Specification | 88.6% | 86% | KPI | 2.6%
2021-22 | Performance Specification | 87.1% | 86% | KPI | 1.1%
2022-23 | Performance Specification | 87.2% | 86% | KPI | 1.2%
2023-24 | Performance Specification |  | 86% | KPI | -86%
2024-25 | Performance Specification |  | 86% | KPI | -86%
In 2022-23 National Highways cleared 87.2% of incidents on motorways within an hour. We successfully maintained rolling in-year performance above the 86% target.
PIs
Delay on smart motorways
Average delay to road users on smart motorways calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at upper limit for variable speed limit sections). It is a subset of the Average delay metric.
2020-21 | Performance Specification | 5.8 | N/A | PI | N/A
2021-22 | Performance Specification | 9.9 | N/A | PI | N/A
2022-23 | Performance Specification | 11.2 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
In 2022-23 the delay on smart motorways was 11.2 seconds which is 1.3 seconds higher than in 2021-22. This metric measures the delay experienced by individual vehicles based on the difference between the observed average travel time, and the speed limit travel time on smart motorways.
Delay from roadworks
This metric measures the additional journey time during roadworks for all vehicle types, compared to an average benchmark journey time measured before the roadworks were in place. Calculated as average annual delay (minutes per hour travelled).
2020-21 | Performance Specification | 0.94 | N/A | PI | N/A
2021-22 | Performance Specification | 1.2 | N/A | PI | N/A
2022-23 | Performance Specification | 1.34 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This metric measures the total additional delay during roadworks, compared to an average benchmark journey time measured before the roadworks were in place. In 2022-23 the delay during roadworks was 1.34 mins per hour, which is 0.14 minutes higher than in 2021-22.
Journey time reliability
The average difference between the observed travel time and the profile (typical) travel time.
2020-21 | Performance Specification | 1.9 | N/A | PI | N/A
2021-22 | Performance Specification | 2.8 | N/A | PI | N/A
2022-23 | Performance Specification | 2.9 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
In 2022-23 performance data shows 2.9 spvpm, representing slight decrease in the performance from previous financial year. This metric measures the average differences between the observed travel time and the profile(typical) travel time.
Delay on gateway routes
Average delay to users of gateway routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the average delay metric.
2020-21 | Performance Specification | 5.6 | N/A | PI | N/A
2021-22 | Performance Specification | 7.9 | N/A | PI | N/A
2022-23 | Performance Specification | 8.8 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
In 2022-23 performance data shows 8.8 spvpm, representing decrease in performance in comparison to previous financial year. This metric measures the average delay to users of Gateway Routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the Average Delay Metric.
Average speed
The average speed of vehicles travelling on the strategic road network
2020-21 | Performance Specification | 60.7 | N/A | PI | N/A
2021-22 | Performance Specification | 58.6 | N/A | PI | N/A
2022-23 | Performance Specification | 57.9 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
In 2022-23 performance data shows 57.9 mph, representing decrease in performance in comparison to previous financial year. This metric measures the average speed of vehicles travelling on the Strategic Road Network (SRN)
Commitments
Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21 |  | National Highways successfully developed enhanced (Roadworks Network Impact) metric in line with our expected milestones and went live in April 2021.
2.1 Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Working with Transport Focus, investigate the development of new metrics on journey time reliability which reflects more accurately road users’ understanding of reliability, and delay from roadworks. |  | National Highways successfully completed the Development stage for a new journey time reliability metric in line with our expected milestones for 2022-23. The development stage for a new delay from roadworks metric was extended to Q4 2022-23 before being approved. Work is ongoing to complete the Validation stage for both metrics by Q3 2023-24.
2.2 Working with TF, investigate the development of the new metrics on journey time reliability which reflects more accurately road users understanding of reliability, and delay from roadworks
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | The milestone was achieved in Q2 2021-22.
Development Stage | Q3 2022-23 | The milestone was achieved in Q3 2022-23 (journey time reliability) and Q4 2022-23 (delay from roadworks).
Validation Stage | Q3 2023-24 | N/A
Investigate new PIs on delays from incidents and delays on the local road/SRN boundary, and an alternative performance measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives. |  | National Highways successfully achieved the Development stage of these metrics in development in early Q3 2022-23. Work is ongoing to complete the Validation stage of these metrics in development in Q3 2023-24.
2.3 Investigate new PIs on delays from incidents &delays on local road/ SRN boundary, & an alternative perf. Measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | The milestone was achieved in Q2 2021-22.
Development Stage | Q2 2022-23 | The milestone was achieved in Q3 2022-23
Validation Stage | Q3 2023-24 | N/A
Notes and commentary

## PS3-Maintainance and resilience
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS3: A well maintained and resilient network |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Pavement condition
The percentage of pavement asset that does not require further investigation for possible maintenance. This measure reports on the overall strategic road network condition as a result of deterioration of the pavement network due to time and traffic and restoration of condition from the annual investment in maintenance. Target: Percentage of the network (as defined by HAPMS, excluding DBFOs) requiring no further investigation to be maintained at 95% or above.
2020-21 | Performance Specification | 95.2% | 95% | KPI | 0.2%
2021-22 | Performance Specification | 95.5% | 95% | KPI | 0.5%
2022-23 | Performance Specification | 96.2% | 96.2% | KPI | 0%
2023-24 | Performance Specification |  |  | KPI | 0%
2024-25 | Performance Specification |  |  | KPI | 0%
This is a new metric for 2022-23. Performance has met the 96.2% target.
PIs
Structures condition
The condition of National Highways' structures across the strategic road network.
2020-21 | Performance Specification | 81.2% | N/A | PI | N/A
2021-22 | Performance Specification | 81% | N/A | PI | N/A
2022-23 | Performance Specification | 81.4% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance at end of 2022-23 is 81.4%, very slightly above the 2022 value of 81.0%.
Technology availability
The percentage of time that roadside technology assets are available and functioning. The assets are considered available and functioning if they are not experiencing a service-affecting fault.
2020-21 | Performance Specification | 95.06% | N/A | PI | N/A
2021-22 | Performance Specification | 96.88% | N/A | PI | N/A
2022-23 | Performance Specification | 95.31% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Over 2022-23, this metric has averaged 95.31%.
Drainage resilience
The percentage length of carriageway that does not have an observed significant susceptibility to flooding
2020-21 | Performance Specification | 72% | N/A | PI | N/A
2021-22 | Performance Specification | 71% | N/A | PI | N/A
2022-23 | Performance Specification | 69% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
While performance over 2022-23 is 2% lower compared to 2021-22 year-end, this reflects more flooding events were reported on the network. Reporting of flood events in the system has improved as a result of continued work. This will positively influence on the reporting element of metric performance. The metric measures the % of carriageway (catchment length) including flood hot spots and not the length of network flooded.
Geotechnical condition
The percentage length of the National Highways' geotechnical asset that is in good condition based on the ability of the asset to perform its function at the time of inspection (i.e. to support other highways assets).
2020-21 | Performance Specification | 99.62% | N/A | PI | N/A
2021-22 | Performance Specification | 99.59% | N/A | PI | N/A
2022-23 | Performance Specification | 99.65% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The geotechnical asset condition performance metric remains stable at 2022-23 end-year. The current metric reporting processing is semi-automated and work is ongoing to make it more automated in the future.
Commitments
Implement the AMDP for RP2 as described above. |  | Progress has been made against business requirements agreed in the Plan. 17 of the in-year milestones have been confirmed as complete, bringing us in line with our Asset Management Transformation Programme.
3.1 Implement the AMDP for RP2 as described above (in the RIS document)
OMM Stages / milestone
Agree AMDP deliverables for the following financial year: Q4 each year |  | This commitment was removed as metric in development. Monitoring will continue as a commitment only. Managed by SES.
End of year report: Q1 the following year |  | N/A
End of year review of deliverables: Q2 the following year |  | N/A
Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets |  | Detailed investigation of feasibility recommendations was presented and the team reported internally on the development stage in October 2022 (Q3 2022-23).
3.2 Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21 for both Structure and Technology.
Feasibility Stage | Q2 2021-22 | The milestone was achieved in Q2 2021-22 for both Structure and Technology
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1 |  | Commitment completed. The new metric for pavement condition will be reported from April 2022 as a replacement of the current KPI.
3.3 Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | - | N/A
Validation Stage | Q4 2021-22 | This milestone was achieved in Q4 2021-22.
Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised |  | The Development Stage milestone was met as planned in Q3 2021-22, with the validation stage to be completed in Q3 2023–24. Data will be shadow reported alongside the non-weather normalised drainage metric throughout the validation phase, with online implementation forecast by the end of 2024-25.
3.4 Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q4 2021-22 | This milestone was achieved in Q3 2021-22
Validation Stage | Q3 2023-24 | N/A
Notes and commentary

## PS4 - Environment
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS4 Delivering better environmental outcomes |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see National Highways' Operational Metrics Manual
Performance specification
| Source of Target | Actual | Cumulative | Target | KPI/PI | Difference (Actual vs Target) |  | Notes
KPIs
Noise
The number of households within mitigated Noise Important Areas where noise has been reduced through National Highways designated fund projects.
Target: 7,500 households benefitting from noise reduction in mitigated Noise Important Areas (defined by the Department for Environment, Food and Rural Affairs (DEFRA)) using funding from the environment and wellbeing designated fund during Road Period 2 | [6 empty] | In 2022-23 we delivered 4,163 households to date, against the RP2 target of 7,500 households. Year 1: 2,111 households Year 2: 1,067 households Year 3: 985 households
2020-21 | Performance Specification | 2111 | 2111 | 7500 | KPI | -5389
2021-22 | Performance Specification | 1067 | 3178 | 7500 | KPI | -6433
2022-23 | Performance Specification | 985 | 4163 | 7500 | KPI | -6515
2023-24 | Performance Specification |  |  | 7500 | KPI | -7500
2024-25 | Performance Specification |  |  | 7500 | KPI | -7500
Biodiversity
Deliver no net loss of biodiversity, measured using an industry standard way of measuring biodiversity changes referred to as the biodiversity metric.
Target: Achieve no net loss of biodiversity, across all National Highways activities, by the end of Road Period 2.
2020-21 | Performance Specification | 147.3 | N/A | No net loss | KPI
2021-22 | Performance Specification | 356.8 | N/A | No net loss | KPI
2022-23 | Performance Specification | 1617.72 | N/A | No net loss | KPI
2023-24 | - |  | N/A | No net loss | KPI
2024-25 | - |  | N/A | No net loss | KPI
In 2022-23 we have built upon the work we did in 2021-22, focusing on improving outputs through design using our project budgets. This has resulted in us forecasting a net positive outcome for the Major Projects core programme during the year. We have delivered 1617.7 units in 2022-23. We have revised our 2021-22 output to capture additional delivery validated in 2022-23. This has seen delivery increase from 299.8 to 356.8.
Air Quality
The number of strategic road network links in exceedance of the legal nitrogen dioxide (NO2) limits as set by the European Union and accepted by the government.
Bring links agreed with the department and based on the Pollution Climate Mapping model into compliance with legal NO2 limits in the shortest timescales possible
The Annual Evaluation Report (2021) and supporting documents was published on National Highways website in middle of December 2022.
National Highways carbon emissions
Target: Reduce National Highways’s carbon emissions as a result of electricity consumption, fuel use and other day-to-day operational activities during RP2, to levels defined by baselining and target setting activities in 2020-21. This metric will become operational from 1 April 2021.
2020-21 | - |  | N/A |  | KPI | 0
2021-22 | Performance Specification | 37178 | N/A |  | KPI | 37178
2022-23 | Performance Specification | 44809 | N/A |  | KPI | 44809
2023-24 | Performance Specification |  | N/A |  | KPI | 0
2024-25 | Performance Specification |  | N/A |  | KPI | 0
In 2022-23 we have used 44,809 tCO2e, a decrease on Carbon emissions when compared to 2021-22 (the figure reported for 2021-22 is based on the original factors. Based on current methodolgy the number would have been 50,388). We are on track to meet RIS2 target. Following recent change control approval from DfT we have switched to reporting emissions based on actual carbon factors. Audit are commencing a re-validation of the previous years' RIS2 performance figures based on the new methadology.
PIs
Supply Chain Carbon emissions
The carbon footprint associated with National Highways' supply chain and also normalised by the volume of work undertaken.
|  | Absolute | Normalised
2020-21 | Performance Specification | 365353 | 128 | N/A | PI | N/A
2021-22 | Performance Specification | 286238 | 134 | N/A | PI | N/A
2022-23 | Performance Specification | 346910 | 134 | N/A | PI | N/A
2023-24 | Performance Specification |  |  | N/A | PI | N/A
2024-25 | Performance Specification |  |  | N/A | PI | N/A
The 2022-23 validated position is 346,910 tonnes/CO2e. This is an increase on Carbon emissions in comparison to previous financial year. The Carbon Intensity Figure has been calculated as 134 (to 1 d.p). NH continue to work closely with the Supply Chain to increase compliance with Carbon reporting, with steps in place to drive improvement for 2023/24.
Condition of Cultural Heritage assets
The overall condition of the culturally significant assets owned by National Highways.
2020-21 | Performance Specification | 51580 | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 51592 | N/A | N/A | PI | N/A
2022-23 | Performance Specification | 51626 | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
In 2022-23 projects reported their cultural heritage performance for the year so the systems are in place to receive further submissions and the baseline is robust and ready for updating.
Water Quality
The length of watercourse enhanced through the mitigation of medium, high, and very high risk outfalls as well as through other enhancements, for example river retraining/rewilding.
2020-21 | Performance Specification | 17 | N/A |  | PI | N/A
2021-22 | Performance Specification | 15 | N/A |  | PI | N/A
2022-23 | Performance Specification | 6.7 | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
During the year 6 projects were delivered. This has resulted in 6.69km of watercourse enhanced rounded off to 6.7km.
Litter
The percentage of the strategic road network where litter is graded at A or B as defined in the Code of practice on litter and refuse 2006.
2020-21 | Performance Specification | 49.2% | N/A | N/A | PI | N/A
2021-22 | Performance Specification | 60.8% | N/A | N/A | PI | N/A
2022-23 | Performance Specification | 53.6% | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
The proportion of the Strategic Road Network where litter is graded at A or B as defined in the Code of Practice on Litter and Refuse was 53% in 2022-23. The performance dropped by 7.2% compared to 2021-22.
Commitments
Highways England carbon emissions KPI: Reduce National Highways carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21 |  |  |  |  | Commitment completed. This metric has been reporting since April 2021.
4.1 National Highways carbon emissions KPI: Reduce National Highways' carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21
OMM Stages | Milestone
Inventory and asset register update; data collation including project action plans | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Start of formal sign-off process of new metric and target with DfT | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Completion of validation; approvals of target | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach. |  |  |  |  | The commitment has been formally ceased and will continue to be monitored as part of RIS3 governance.
4.2 Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage | Q2 2021-22 | This metric was formally ceased at the Feasibility stage.
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on National Highways work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in Year 1 of RP2, as well as potential implementation opportunities identified by that stage. |  |  |  |  | This commitment was removed as metric in development as agreed with ORR and DfT. Monitoring will continue as a commitment only. Managed by SES.
4.3 Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on National Highways work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in year 1 od RP2, as well as potential implementation opportunities identified by that stage.
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21. A detailed timetable was produced in 2020-21 in line with the commitment.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## PS5-Needs of all road users
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS5: Meeting the needs of all road users |  |  |  | For a definition of the metric and parameters for measuring and monitoring performance regarding vulnerable users see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Road user satisfaction
The percentage of drivers who are satisfied with their journey on the strategic road network as measured by the Strategic Roads User Survey (SRUS) conducted by Transport Focus.
Target: Achieve an 82% road user satisfaction score in 2020-21 and 2021-22, with year-on-year increases in the following years. The exact targets for 2022-23, 2023-24, and 2024-25 will be set during 2021-22.
2020-21 | Performance Specification | N/A |  | KPI | N/A
2021-22 | Performance Specification | N/A |  | KPI | N/A
2022-23 | Performance Specification | N/A |  | KPI
2023-24 | Performance Specification |  | 73% | KPI
2024-25 | Performance Specification |  |  | KPI
Due to target setting and sample calibration, during the face-to-face Strategic Roads User Survey (SRUS) transition to a web-based survey (SRUS Online) as a result of Covid-19, it has not been possible to monitor progress for the KPI. The revised survey has now been assessed as being analytically representative since April 2022, and target agreed for 2023-24.
Roadworks information timeliness and accuracy
The percentage of overnight road closures that are accurately notified by Highways England seven days in advance. A correctly notified road closure is one that commences within +/- 1 hour of the start time stated 7 days in advance on the Network Occupancy Management System (NOMS).
Target: Achieve 90% accuracy of roadworks information seven days (rolling) in advance of works by 2024-25, with an increasing trajectory of improvement through Road Period 2 from the level of performance achieved by the end of Road Period 1
2020-21 | Performance Specification | 54.5% |  | KPI
2021-22 | Performance Specification | 68.1% |  | KPI
2022-23 | Performance Specification | 70% |  | KPI
2023-24 | Performance Specification |  |  | KPI
2024-25 | Performance Specification |  | 90% | KPI
Performance remained stable at 70.0% in 2022-23, with a slight improvement of 1.6% compared to the previous year.
PIs
Timeliness of information provided to road users through electronic signage
The average median time to set signs and signals on (all) motorways after Highways England has received notification of an incident, that requires signs and signals to be manually set.
2020-21 | Performance Specification | 0:02 | N/A | PI | N/A
2021-22 | Performance Specification | 0:02 | N/A | PI | N/A
2022-23 | Performance Specification | 0:02 | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance has ranged from 2:00 to 2:37 over 2022-23. The year-to-date median time was 2:20 which is 9 seconds longer than 2021-22.
Ride Quality
This measure reports the ride quality for the strategic road network using a subset of the pavement condition metric condition parameters. It is represented by the percentage of pavement asset delivering ride quality consistent with the 3m Enhanced Longitudinal Profile Variance (ELPV) value in Highways England’s standards, which is based on engineering factors and driver comfort. Percentage of the network (as defined by HAPMS, excluding DBFOs) where 3m ELPV is deemed to be category 2 and better, in accordance with the road condition standard, HD29.
2020-21 | Performance Specification | 98.5% | N/A | PI | N/A
2021-22 | Performance Specification | 98.4% | N/A | PI | N/A
2022-23 | Performance Specification | 98.6% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
Performance remained stable for the Ride Quality PI throughout 2022-23, reporting 98.6% at year-end. Performance was between 98.4% and 98.6% over the year.
Working with local highways authorities to review diversion routes for unplanned events.
2020-21 | Performance Specification | 53% | N/A | PI | N/A
2021-22 | Performance Specification | 97.2% | N/A | PI | N/A
2022-23 | Performance Specification | 99% | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The reported performance for 2022-23 is 99% which is 1.8% higher compared to last year. This metric annually reports the percentage of local highway authorities which National Highways engaged with to review diversion routes for unplanned events.
Commitments
Work with Transport Focus to develop satisfaction surveys for cyclists and pedestrians that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | Concept and Feasibiity Stage are expected for completion in Q2 2023/24. In 2023-24 and 2024-35, NH will continue to engage and input with TF on the scope and location of further customer insight surveys in relation to walking, cycling and horse-rider infrastructure on the SRN.
5.1 Work with TF to develop satisfaction surveys for cyclists & pedestrians that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Work with Transport Focus to develop satisfaction surveys for logistics and coach managers that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | Survey is currently in Concept and Feasibility Stage - the survey has been developed and is currently being administered. We will shortly explore the viability of using the data to inform our performance.
5.2 Work with TF to develop satisfaction surveys for logistics & coach managers that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22. |  |  |  | Commitment completed. The revised online survey has now been assessed as being analytically representative since April 2022, and target agreed for 2023-24. At end 2023-24, with further data avaliable, the target will be reassessed.
5.3 Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22
OMM Stages |  | Milestone
Concept Stage |  | N/A | N/A
Feasibility Stage |  | N/A | N/A
Development Stage |  | N/A | N/A
Validation Stage |  |  | N/A
Develop with Transport Focus during RP2 a measure of ride quality which reflects road users’ experience of the network. |  |  |  | Commitment Completed. The validation stage for the PI was completed in Q2 2022-23 and the metric went live in April 2023.
5.4 Develop with Transport Focus during RP2 a measure of ride quality which reflects road users' experience of the network
OMM Stages |  | Milestone
Concept Stage |  | Q2 2020-21 | The milestone was achieved in Q2 2020-21.
Feasibility Stage |  | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Development Stage |  | Q1 2022-23 | The milestone was achieved in Q1 2022-23.
Validation Stage |  | Q2 2022-23 | The milestone was achieved in Q2 2022-23.
Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks. |  |  |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in April 2022.
5.5 Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  |  | N/A
Validation Stage |  |  | N/A
Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs. |  |  |  | Further investigation of this commitment has been ceased following approval at the Change Control Decision Committee in May 2022.
5.6 Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | N/A
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  |  | N/A
Validation Stage |  |  | N/A
Notes and commentary

## PS6-Efficiency of delivery
National Highways Performance Monitoring Statements Year end 2022-23
Statement PS6: Achieving efficient delivery
Performance specification
| Source of Target |  | Actual (£m) | Annual forecast milestone (£m) | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Total efficiency
The value of operational and capital expenditure efficiency achieved by the end of Road Period 2.
Target: Demonstrate efficiency of £2.110 bn of capital and operational expenditure by the end of Road Period 2. | [6 empty] | National Highways delivered efficiencies of £346m over 2022-23. This means that cumulative efficiencies of £848m have been achieved so far over Roads Period 2. This is against a milestone target of £776m. The annual forecast milestone numbers will be updated annually in line with the delivery plan update.
2020-21 | EIMM | In-year: | 243 | 233 | KPI
|  | Cumulative: | 243 | 233 | KPI | 10
2021-22 | EIMM | In-year: | 259 | 238 | KPI
|  | Cumulative: | 502 | 471 | KPI | 31
2022-23 | EIMM | In-year: | 346 | 305 | KPI
|  | Cumulative: | 848 | 776 | KPI | 72
2023-24 | EIMM | In-year: |  | 444 | KPI
|  | Cumulative: | 848 | 1220 | KPI | -372
2024-25 | Performance Specification | In-year: |  | 891 | KPI
|  | Cumulative: | 848 | 2111 | KPI | -1263
PIs
Cost performance index and Schedule performance index Progress of schemes in construction through reporting Cost performance index (CPI) and Schedule performance index (SPI).
100% of schemes in construction are reporting CPI and SPI through PRISM.
Cost Performance Index (CPI): Represents the amount of work being completed on a project for every unit of cost spent. CPI is computed by Earned Value / Actual Cost. A value above one means that the project is doing well against the budget. Schedule Performance Index (SPI): Represents how close actual work is being completed compared to the schedule. SPI is computed by Earned Value / Planned Value. A value of above one means that the project is doing well against the value.
Commitments
Investigate and look to develop new or improved metrics to monitor cost and schedule for enhancement scheme development and construction, engaging with ORR. |  |  |  |  | The focus remains on establishing CPI/SPI for schemes in construction to meet present commitments, with the concept still in development. Further investigation is required before agreeing whether to develop a new metric or consider the commitment closed.
6.1 Investigate & look to develop new or improved metrics to monitor cost & schedule for enhancement scheme development & construction, engaging with ORR
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | N/A
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## IP1
Statement IP1: Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
National Highways Delivery Plan - Major Improvements
Milestone Definitions and Key:
Construction Phase - Start of Works - The date when the start of the works is declared, following approval of final business case and construction budget, award of contract is in place along with completion of “Notice to proceed” and where applicable the “Notice to Treat”. Physical construction works will be evident on site.
Open for Traffic - The date when works are substantially complete and the scheme is open to traffic. There may be partial or overnight closures to finalise any remedial works.
Delivery Plan Commitment - The date committed to in the 2022-23 delivery plan update.
Actual Achieved - The actual date the Delivery Plan commitment has been achieved.
*Scheme commitment under review - Scheme is under review and is subject to formal change control governance.
| Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works (SOW) |  | Open for Traffic
|  |  |  | Delivery Plan Commitment | Actual Achieved | Delivery Plan Commitment | Actual Achieved | Lane miles delivered (Actual)
| North East | 1 | A1 Scotswood to North Brunton | Pre RP2 | 2020-03-20 | 2022/2023 Q2 | 2022-09-22 | 9.2
|  | 2 | A19 Testo's | Pre RP2 | 2019-03-19 | 2021/2022 Q3 | 2021-06-21 | 3
|  | 3 | A19 Norton to Wynyard | Pre RP2 | 2020-03-20 | 2021/2022 Q3 | 2021-11-21 | 6.7
|  | 4 | M621 Junctions 1-7 | Pre RP2 | 2019-11-19 | 2024/2025
|  | 5 | A61 Westwood Roundabout | Pre RP2 | 2020-03-20 | 2021/2022 Q1 | 2021-02-21 | 0.8
|  | 6 | A1 Morpeth to Ellingham | 2022/2023 Q2 |  | 2024/2025
|  | 7 | A1 Birtley to Coal House | 2021/2022 Q2 | 2021-05-21 | 2024/2025
|  | 8 | A19 Downhill Lane | 2020/2021 Q4 | 2020-09-20 | 2022/2023 Q2 | 2022-03-22 | 2.3
|  | 9 | A63 Castle Street | Pre RP2 | 2020-03-20 | 2024/2025
|  | 10 | M62 Junctions 25-30 | *paused |  | *paused
| North West | 11 | A585 Windy Harbour to Skippool | Pre RP2 | 2020-03-20 | 2023/2024 Q4
|  | 12 | M62 Junctions 20-25 | *paused |  | *paused
|  | 13 | M6 Junction 19 | Pre RP2 | 2020-03-20 | 2021/2022 Q3 | 2021-11-21 | 2.1
|  | 14 | A66 Northern Trans-Pennine | 2023/2024 Q4 |  | RP3
|  | 15 | A5036 Princess Way | RP3** |  | RP3**
|  | 16 | M6 Junctions 21a-26 | 2020/2021 Q4 | 2021-03-21 | 2022/2023 Q4
|  | 17 | Mottram Moor Link Road & A57 Link Road | 2022/2023 Q4 |  | RP3
|  | 18 | M56 Junctions 6-8 | Pre RP2 | 2020-03-20 | 2022/2023 Q2
|  | 19 | M60/M62/M66 Simister Island Interchange | 2024/2025 Q4 |  | -
| Midlands | 20 | A500 Etruria | Pre RP2 | 2019-02-19 | 2020/2021 Q3 | 2020-07-20 | 1
|  | 21 | M6 Junctions 13-15 | Pre RP2 | 2018-03-18 | 2022/2023 Q2 | 2022-08-22 | 32.9
|  | 22 | M42 Junction 6 | Pre RP2 | 2020-03-20 | 2024/2025
|  | 23 | A46 Coventry Junctions | Pre RP2 | 2020-03-20 | RP3
|  | 24 | M40/M42 Interchange | Pre RP2 | 2020-02-20 | - | *paused
|  | 25 | A45/A6 Chowns Mill Junction | Pre RP2 | 2019-11-19 | 2021/2022 Q4 | 2021-12-21 | 0
|  | 26 | M1 Junctions 13-19 | Pre RP2 | 2015-11-15 | 2022/2023 Q4 | 2023-03-23 | 45.9***
|  | 27 | A38 Derby Junctions | 2023/2024 Q2 |  | RP3
|  | 28 | M54-M6 Link Road | 2022/2023 Q4 |  | RP3
|  | 29 | A5 Dodwells to Longshoot |  | cancelled |  | cancelled
|  | 30 | A52 Nottingham Junctions | Pre RP2 | 2017-01-17 | 2023/2024 Q4
|  | 31 | M6 Junction 10 | Pre RP2 | 2020-01-20 | 2022/2023 Q1
|  | 32 | A46 Newark Bypass | RP3 |  | -
|  | 33 | M42 Junctions 4-7 | *paused |  | *paused
|  | 34 | M6 Junctions 4-5 | *paused |  | *paused
|  | 35 | M6 Junctions 5-8 | *paused |  | *paused
|  | 36 | M6 Junctions 8-10a | *paused |  | *paused
| East | 37 | A14 Cambridge to Huntingdon | Pre RP2 | 2016-10-16 | 2020/2021 Q3 | 2020-05-20 | 134
|  | 38 | A47 Wansford to Sutton | 2022/2023 Q4 |  | 2024/2025
|  | 39 | A47 Great Yarmouth Junctions | 2023/2024 Q4 |  | 2024/2025
|  | 40 | A47 Guyhirn Junction | 2020/2021 Q4 | 2021-02-21 | 2022/2023 Q1 | 2022-03-22 | 0.3
|  | 41 | A47 North Tuddenham to Easton | 2022/2023 Q4 |  | 2024/2025
|  | 42 | A47 Thickthorn Junction | 2022/2023 Q4 |  | 2024/2025
|  | 43 | A47 Blofield to North Burlingham | 2022/2023 Q4 |  | 2024/2025
|  | 44 | A428 Black Cat to Caxton Gibbet | 2022/2023 Q3 |  | RP3
|  | 45 | A12 Chelmsford to A120 | 2023/2024 Q4 |  | RP3
|  | 46 | M1 Junctions 10-13 | *paused |  | *paused
| South East | 47 | M4 Junctions 3-12 | Pre RP2 | 2017-03-17 | 2022/2023 Q3 | 2022-12-22 | 57.6
|  | 48 | A34 Newbury to Oxford Enhancements | Pre RP2 | 2019-08-19 | 2021/2022 Q4 | 2021-11-21 | 0
|  | 49 | M3 Junctions 9-14 | Pre RP2 | *paused | - | *paused
|  | 50 | M27 Junctions 4-11 | Pre RP2 | 2018-04-18 | 2022/2023 Q1 | 2022-06-22 | 20.9
|  | 51 | M25 Junction 25 | 2020/2021 Q4 | 2021-01-21 | 2022/2023 Q3 | 2022-09-22 | 1.1
|  | 52 | M25 Junction 28 | 2023/2024 Q1 | 2022-09-22 | RP3
|  | 53 | M25 Junctions 10-16 | - | *paused | - | *paused
|  | 54 | M25 Junction 10 | 2022/2023 Q3 | 2022-10-22 | RP3
|  | 55 | M3 Junction 9 | 2024/2025 Q4 |  | RP3
|  | 56 | M27 Southampton Junction 8 | 2023/2024 Q3 |  | RP3
|  | 57 | A27 Arundel Bypass | 2024/2025 Q2** |  | RP3**
|  | 58 | A27 Worthing and Lancing improvements | 2024/2025 Q4 |  | RP3
|  | 59 | A31 Ringwood | 2020/2021 Q4 | 2021-03-21 | 2022/2023 Q4 | 2022-11-22 | 0.5
|  | 60 | A2 Bean and Ebbsfleet | Pre RP2 | 2020-03-20 | 2022/2023 Q1 | 2022-06-22 | 2.6
|  | 61 | M2 Junction 5 | 2021/2022 Q2 | 2021-09-21 | 2024/2025
|  | 62 | A27 East of Lewes Package | Pre RP2 | 2020-03-20 | 2022/2023 Q4 | 2023-03-23 | 1
|  | 63 | Lower Thames Crossing | 2024/2025 Q4 |  | RP3
| South West | 64 | A303 Sparkford to Ilchester | 2021/2022 Q3 | 2021-09-21 | 2023/2024 Q4
|  | 65 | A303 Amesbury to Berwick Down | 2024/2025 Q2 |  | RP3
|  | 66 | A358 Taunton to Southfields | 2024/2025 Q4 |  | RP3
|  | 67 | A30 Chiverton to Carland Cross | Pre RP2 | 2020-03-20 | 2023/2024 Q4
|  | 68 | A417 Air Balloon | 2023/2024 Q2 | 2023-02-23 | RP3
|  | 69 | M4 Junctions 19-20 and M5 Junctions 16-17 | *paused |  | *paused
|  | 70 | A21 Safety Package | 2021/2022 Q1 | 2021-06-21 | 2024/2025
|  |  | *Paused | Schemes that have subsequently been cancelled as result Governement announcement in April
|  |  | ** | A27 Arundel Bypass and A5036 Princess Way schemes were deferred as result of Written Ministerial Statement. Also LTC construction to be rephased
|  |  | *** | Only lane miles for M1 Junction 13-16 are being reported. M1 19-16 opened in RP1. The lane miles for M1 19-16 are: 27.49. However, that part of the scheme was claimed for in RP1.
Housing Infrastructure Fund schemes and Third Party schemes - these schemes will be delivered by local authorities and third parties with our support and are subject to future planning decisions. They are subject to different governance and funding arrangements.
Delivery Plan - the date in the Highways England Delivery Plan
Start of Works forecast / actual - start of construction date as provided by external delivery organisation (third parties, local authority)
Open for Traffic forecast / actual - open for traffic date as provided by external delivery organisation (third parties, local authority)
* SOW / OFT Delivery Plan - dates updated to financial year format
External Delivery Organisation | Region |  | Scheme Name | Construction Phase |  | Open for Traffic
Start of Works
|  |  |  | *Delivery Plan | Actual | *Delivery Plan | Actual
Housing infrastructure fund schemes | East |  | A120: Tendring/Colchester Border Garden Community | 2023/24 |  | RP3
| South West |  | M5 junction 10 and link road | 2024/25 |  | RP3
| South East |  | A249: Swale transport infrastructure | 2021/22 | 2021/22 | 2024/25
| North West |  | M6: South Lancaster Growth Catalyst – junction 33a | 2024/25 |  | RP3
| East |  | A5 Dordon to Atherstone | RP3 |  | RP3
External Delivery Organisation | Region |  | Scheme Name | Construction Phase |  | Open for Traffic
Start of Works
|  |  |  | Delivery Plan | Actual | Delivery Plan | Actual
Third party schemes | Midlands |  | A5 Towcester relief road | 2022/2023 | 2022-09-22 | RP3
| East |  | M11 junction 7a | 2020/21 Q2 | 2020-06-20 | 2022/23 | 2022-06-22
| North West |  | M55 junction 2 | RP1 | 2019-09-19 | 2023/24
| North West |  | M62 junction 19 | 2020/21 Q3 | 2020-10-20 | 2022/23 | 2022-09-22

## IP2
Region | RIS3 Development Pipeline | Programme (National) level update
|  | No. schemes started development | Programme level commentary
North | A19 North of Newcastle Junctions | 33 | Development work has been undertaken on all 33 RIS3 Pipeline schemes. Following the Government announcement in March 2023, "schemes earmarked for RIS 3 will continue to be developed, in line with the statutory process, but for consideration for inclusion during RIS 4 (beyond 2030). Given many of these schemes were previously expected towards the end of RIS 3, this extra time will help ensure better planned and efficient schemes can be deployed more effectively". Work will continued in line with this announcement. This year we have continued development work at PCF stage 0, Stage 1 and Stage 2 on 23 schemes, 8 schemes are currently paused or stopped and 1 scheme has progressed to PCF Stage 3.
A64 Hopgrove
M1 Leeds Eastern Gateway
M1/M62 Lofthouse interchange
M6 Junctions 19 to 21a Knutsford to Croft extra capacity
M1 Junctions 35a to 39 Sheffield to Wakefield extra capacity
A1 Doncaster to Darrington
M6 Junction 22
Manchester South East Junctions Improvements
East | A47/A1101 Elm Road junction
A11 Fiveways Junction
M11 Junction 13 Cambridge West
A12/A14 Copdock Interchange
A120 Braintree to A12
Tilbury Link Road
A34 N&S Oxford
Midlands | M6 Junction 15 Potteries Southern Access
A483 Pant-Llanymynech bypass (in cooperation with the Welsh Government)
M1 North Leicestershire extra capacity
M1 Leicester Western Access
A5 Hinckley to Tamworth
South and West | Severn Resilience Package (formally stopped in PCF Stage 1)
A404 Bisham Junction
A2 Brenley Corner
A303 South Petherton to Southfields
A3/A247 Ripley South
A2 Dover Access
A27 Lewes to Polegate
A27 Chichester Improvements
M27 Southampton Access
A38 Trerulefoot-Carkeel Safety Package
A404/M40 Junction 4 High Wycombe
[A21 Safety Package]*

## IP3
Statement IP3: Designated funds
There are 4 designated funds outlined in Highways England's Delivery Plan 2020-2025: 1. Safety and congestion - Safety schemes; Congestion schemes; Suicide Prevention schemes; and Economic Development 2. User and communities - Integration; Walkers, Cyclists & Horse Riders; Roadside Facilities; Communities; Freight; and Information 3. Environment and wellbeing - Biodiversity; Noise; Air Quality; Flooding; Water Quality; Carbon; Cultural Heritage; Landscape; and Environmental Legacy 4. Innovation and modernisation - Design, Construction & Maintenance; Connected & Autonomous Vehicles; Customer Mobility; Energy & Environment; and Operations Under each designated fund there are individual themes. Projects which use designated funds are aligned to a fund and an individual theme.
Key Definitions: No. planned projects completing either feasibility, detailed design or implementation 2022-2023 - The combined number of projects planned to complete either the feasibility, detailed design or implementation stage for each fund Feasibility - The number of projects that have completed the feasibility stage at the end of the year Detailed design - The number of projects that have completed the detailed design stage at the end of the year Implementation - The number of projects that have completed the implementation stage at the end of the year Comments - Justification for any deviation or any supporting commentary
Fund | Projects planned 2022-2023 |  |  |  | Total count of stages complete | Comments
| No. planned projects completing either feasibility, detailed design or implementation | Feasibility | Detailed design | Implementation
Safety and Congestion fund | 124 | 7 | 11 | 11 | 29 | Safety and Congestion has had assured 29 stage gates as a pass. A larger number of stage gates will be collected and validated in FY 23/24.
Users and Communities fund | 146 | 15 | 8 | 4 | 27 | Users and Communities has had assured 27 stage gates as a pass. A larger number of stages gates will be collected and validated in FY 23/24.
Environment and Wellbeing fund | 197 | 21 | 22 | 13 | 56 | Environment and Wellbeing has had assured 56 stage gates as a pass. A large number of stages gates will be collected and validated in FY 23/24.
Innovation and Modernisation fund | 41 | 4 | 1 | 7 | 12 | Innovation and Modernisation has had assured 12 stage gates as a pass. A number of stages gates will be collected and validated in FY 23/24.

## IP4
Statement IP4: Renewal Volume Reporting
This statement details National Highways’ capital renewals delivery performance against planned volumes of activity associated with different asset types and interventions across the Strategic Road Network in 2022-23 (as set out in NH’s annual Delivery Plan).
Asset | Description | Unit | 2022-23
Full year Actual
|  |  | Total | Baseline | Variance | Comments
Asphalt road surface (pavement) | Total length of existing asphalt resurfaced | Lane Kilometers | 1606 | 1350 | 256 | The Asphalt Pavement plan of 1,350lkms (838.9 lane miles) was comprised of 234 schemes. Of the 1606lkms delivered; - 3lkms were delivered on 9 Non-Renewals schemes (eg. Safety & Congestion) - 180lkms were delivered on Non-Asphalt PIT schemes - 49lkms were delivered on 'simple’ pavement and lining schemes - 1373lkms on complex schemes delivering multiple output types The outturn on the targeted schemes was 1,362lkms and met the plan overall. The additional 244lkms on non-target schemes was spread across all regions. The total over delivery of 256lkms (19%) was higher than the 11% additional spend against PIT.
Concrete road surface (pavement) | Total length of existing concrete road surface reconstructed and replaced with asphalt surface | Lane Kilometers | 81 | 77 | 4 | The original concrete output target of 76.5lkms (47.5 lane miles) consisted of 12 schemes nationally, of which 6 schemes in the East planned 53 lkms of reconstruction and 6 schemes in other regions planned 23 lkms of life extension works. Reconstruction is high cost/low output. The schemes for reconstruction moved to the right due to the complexity of the solution and contracts with only 22.63 lkms of reconstruction delivered. The shortfall in output was met by additional LEW (Life Extension Works) outputs progressing, 35.2 lkms in the East region with LEW outputs falling a little in other areas. This asset need was due to the accelerated deterioration of the concrete network caused by very high temperatures in the summer of 2022.
Safety barriers (steel) | Total length of steel safety barriers installed or renewed | Linear metres | 376770 | 350000 | 26770 | The Road Restraint Systems - Steel plan of 350,000 was comprised of 118 schemes. Included in the target were; - 51,592 (15%) planned on 44 Non-RRS Steel PIT schemes (eg delivered alongside Pavement and Structures schemes) - 150,908 on 56 ‘simple’ RRS Steel schemes - 147,500 on 21 complex schemes delivering multiple output types Of the 376,770 delivered; - 17,389 were delivered on 11 Non-Renewals schemes (eg Safety & Congestion) - 48,215 were delivered on Non-RRS Steel PIT schemes - 180,140 were delivered on simple’ RRS Steel schemes - 131,027 on complex schemes delivering multiple output types The additional delivery of 26,770 (+7%) was matched by the change in PIT spend (+7%). The main reason for the increase was the de-risking of the programme in the MIdlands due to the Area 9 move to Asset Delivery and greater delivery of less complex work, such as steel barrier works, in this region.
Safety barriers (concrete) | Total length of concrete safety barriers installed or renewed | Linear metres | 9833 | 12500 | -2667 | The Road Restraint Systems - Concrete plan of 12,500 was comprised of 5 schemes. Of the 9,833 delivered; - 858 were delivered in YNE which was short of their plan as the largest scheme, due to delivery 3,750m, was delayed due to greater complexity than expected in agreeing the financial arrangements with the DBFO operator delivering the scheme. - 1,397 was delivered in the NW on 3 schemes with additional concrete restraint outputs being included on 2 further schemes and delivering slightly more on the main planned scheme. - 7,482 was delivered in the Midlands on two schemes, with the planned scheme delivering to target and a further 120 lms delivered as part of a steel restraint scheme - 96 was delivered by the East region on one structures parapet scheme The reduction in delivery of 2,667 was reflected by a the reduction in PIT spend and these outputs and spend will be delivered in 24-25.
Significant structures | Number of significant structures | Number | 44 | 39 | 5 | We achieved 44 delivery milestones against the target of 39 with 10 schemes starting design, 13 starting construction and 21 completing construction.
Road markings | Length along the centre line of the road markings, including marking on new or replacement road surfacing | Linear metres | 3665234 | 3300000 | 365234 | The Road Markings plan of 3,300,000 consisted of 263 schemes. These were planned to be predominantly delivered in conjunction with the Pavement schemes but 2 schemes were mainly standalone marking schemes. In addition to the markings reported we also delivered 316,026 road studs (not part of the target). In common with previous years (see causes above), there was an over-delivery of markings compared to the target (365,234 – 11%). However, the over delivery is part of a declining trend and is the lowest since we began recording the output (40% over-delivery in 20-21 for comparison, 20% over-delivery in 21-22).
Kerbs | Total length of kerbs laid or renewed | Linear metres | 17764 | 9500 | 8264 | The Kerbs plan of 9,500 consisted of 35 schemes. These were planned to be predominantly delivered in conjunction with the pavement and lining or more complex schemes. Only one of the scheme was a ‘standalone’ scheme delivering kerbs as part of a layby footpath renewal. There was a higher over-delivery than previous years. There was an over-delivery of kerbs compared to the target (8,264 – 87%). The increase relates to Midlands de-risking of their programme leading to more pavement and associated kerb replacement. East region also did not identify the secondary kerb outputs related to concrete roads in the forward programme. East and South West had other secondary outputs for some significant pavement schemes including some that were carried over from 21-22. There is no separate PIT for kerbs as this is recorded as part of the wider ancillaries’ expenditure.
Drainage | Total length of drainage installed or renewed | Linear metres | 240447 | 130000 | 110447 | The Drainage plan of 130,000 was comprised of 79 schemes. Included in the target were; - 63,377 planned on 31 Non-Drainage PIT schemes (eg delivered alongside RRS, Pavement and Structures) - 40,890 on 21 ‘simple’ Drainage schemes - 25,733 on 27 complex schemes delivering multiple output types Of the 240,447 delivered; - 8600 were delivered on 5 Non-Drainage schemes (eg Designated Funds, Environment) - 59,521 were delivered on Non-Drainage PIT schemes - 172,326 were delivered on Drainage schemes PIT schemes The total over delivery of 110,447 (85%) was higher than the 60% additional spend, however, while some of the increased spend can be directly matched to the drainage outputs in the Midlands this was not the case with Brock spend in the SE. The Midlands de-risking programme meant additional drainage output and spend and in addition to this the south east identified the opportunity to deliver extra drainage outputs on the M20 J8-J9 Brock capital scheme. This was a higher over delivery than previous years.
Geotechnical | Total length of embankment / cutting treated parallel to the carriageway | Linear metres | 2462 | 1800 | 662 | The geotechnical plan of 1,800 was comprised of 15 schemes. Of the 2,462 delivered; - 245 were delivered on non-renewals schemes - 873 were delivered on non-geotech PIT schemes - 1343 on complex multi-output schemes The over delivery of 662 (34%) was mainly delivered by 518 additional Geotech units in the SE. This was due to an opportunity to deliver Geotech outputs as part of two safety barrier schemes on the A34 and on the A21, the latter scheme which was funded outside of Renewals, by designated funds. The total over delivery was higher than the 13% additional spend, however, while some of the increased spend can be directly matched to the Geotech outputs, almost half of the outputs were delivered by schemes that were not predominantly Geotech.
Traffic signs (non-electrical) | Number of permanent non-electrical traffic signs installed or replaced | Number | 2117 | 2000 | 117 | The traffic signs (non-electrical) plan of 2,000 was comprised of 59 schemes. Of the 2,117 delivered; - 549 were delivered on non-renewals schemes - 1,499 were delivered on non-traffic signs PIT schemes - 58 on ‘simple’ traffic signs schemes - 11 on complex multi-output schemes The over delivery of 117 (6%) was mainly delivered by an additional 232 signs from non-Renewals funded schemes with renewals funded schemes delivering slightly less than expected. There was an underspend on Traffic Signs of 73%. The PIT is not a good measure of Traffic Sign delivery due to the high proportion of delivery alongside other PITs over 2,048 units were delivered under other PIT schemes (for example the main delivery alongside Pavement schemes).
Guardrail | Total length of new or replacement pedestrian guardrail | Linear metres | 780 | 500 | 280 | The guardrail plan of 500 was comprised of 4 schemes. Of the 780 delivered; - 115 were delivered on non-renewals schemes - 665 were delivered on non-guardrail PIT schemes The main increase on the Renewals funded schemes was in the North West. The scheme in NW had been expected to deliver in 21-22 but delivered 207.5 units early in 22-23 instead. In the East the increase related to a designated funds scheme with 95 units.
Boundary fencing | Total length of new or replacement boundary fencing | Linear metres | 62561 | 57000 | 5561 | The boundary fencing plan of 57,000 was comprised of 38 schemes. Of the 62,561 delivered; - 19,574 were delivered on non-boundary fencing PIT schemes - 42,987 were on 'simple' boundary fencing schemes PIT schemes [This number is correct] The over delivery of 5,561 (9.8%) was due to additional delivery on more complex renewals funded schemes as part of efficient delivery. Boundary Fencing and Guardrail expenditure is captured as a single PIT. Expenditure came in to budget.
Lighting | Number of road lighting columns installed or replaced | Number | 712 | 600 | 112 | The lighting (column renewal) plan of 600 was comprised of 17 schemes. Of the 712 delivered; - 30 were delivered on non-renewals schemes - 161 were delivered on non-lighting PIT schemes - 521 on complex multi-output schemes The over-delivery was accounted for by one additional scheme in YNE that delivered 172 units, which was not part of the original programme, with mulitple other projects delivering slightly less than planned. PIT spend was 18% lower than planned - PIT spend does not track well to outputs for lighting as all of the delivery is on complex multi-output schemes.
Bridge joint | Number of bridge deck expansion joint installations installed or renewed | Number | 469 | 350 | 119 | The bridge joint plan of 350 was comprised of 79 schemes. Of the 469 delivered; - 2 were on non-renewals schemes - 268 were delivered on non-bridge joint PIT schemes - 5 on ‘simple’ bridge joint schemes - 194 on complex multi-output schemes The majority of the overdelivery, 94 joints, were delivered on non-bridge joint PIT schemes. This majority was in the NW where bridge joints are not routinely included in non-bridge joint PIT scheme outputs prior to construction, due to uncertainty as to whether they are required. Most of the remainder were in the MIdlands where there were additional outputs due to de-risking of the programme following challenges with the move to Asset Delivery in Area 9. There was slight overdelivery in other areas. Spend on this PIT was up 38% refecting the 34% increase in outputs, there is unlikely to be a direct causal link though as most extra output was on non-bridge joint PIT projects, and for the bridge joint projects only 5 schemes delivered bridge joint outputs only.
Bridge bearing | Number of bridge bearing units installed or renewed | Number | 99 | 100 | -1 | The bridge bearing plan of 100 was comprised of 8 schemes. Of the 99 delivered; - 30 were delivered on non-bridge bearing PIT schemes - 69 on ‘simple’ bridge bearing schemes The shortfall on outputs was related to a single scheme in YNE which moved to the right and is now expected to be delivered in FY23-24. Spend against this PIT was 21% lower than planned and, as outputs were as expected against simple bridge bearing schemes, this is assumed to be more efficient delivery.
Parapet | Total length of vehicle parapet installed or renewed | Linear metres | 5006 | 4500 | 506 | The parapet plan of 4,500 was comprised of 17 schemes. Of the 5,006 delivered; - 623 were delivered on non-renewals schemes - 1,383 were delivered on non-parapet PIT schemes - 1,882 on ‘simple’ parapet schemes - 1,118 on complex multi-output schemes PIT spend was 34% lower than budget, and this was reflected in lower outputs on PIT parapet schemes down by 12%. The increased outputs related to increases on non-parapet PIT schemes and outputs delivered by non-renewals schemes.
Waterproofing | Total surface area treated for waterproofing | Square metres | 21909 | 24000 | -2091 | The waterproofing plan of 24,000 was comprised of 28 schemes. Of the 21,909 (which was 9% below target) delivered; - 150 were delivered on non-renewals schemes - 10,592 were delivered on non-waterproofing PIT schemes - 389 on ‘simple’ waterproofing schemes - 10,779 on complex multi-output schemes There were reductions in outputs in the East and the Midlands and increased outputs in YNE. The Midlands underdelivery is related to the issues with Area 9 move to Asset Delivery and re-prioritising the programme. In the East Programme delays on M1 Ridgmont & M11 Haymead schemes contributed to reductions in outputs. There were also reductions in the East due to scope change on A14 Exning & Windmill due to less waterproofing being needed than originally identified. This reduced scheme output from 2300 down to circa 900. Excluding the 1400 of outputs not required would have taken us up to around 97% of our national target. The situation in YNE was that there were in year changes to the programme across a range of schemes both up and down, and there was an opportunity to delivery additional outputs to meet asset need so this was opportunity was taken. PIT spend was 35% lower than expected and this matched delivery on Waterproofing PIT schemes which delivered 28% lower than expected. The majority of this shortfall, as discussed above, was made up through non-renewals funded delivery and waterproofing delivered through non-waterproofing PIT schemes.
Motorway communications equipment | Number of new or replaced motorway communications equipment items | Number | 353 | 300 | 53 | The motorway comms equipment plan of 300 was comprised of 56 schemes. Of the 353 delivered; - 224 on 'non-renewal of technology' PIT schemes - 113 on 'renewal of technology' PIT schemes with complex mulitple outputs - 16 on 'renewal of technology' PIT schemes delivered on a simple single output schemes Motorway Comms Equipment and Technology Renewals expenditure is captured as a single PIT. Spend on this PIT was 31% below plan but delivery was contributed primarily by 'non-technology renewals' PIT schemes and of the 'renewal of technology' PIT schemes the majority were multi-output.
Technology renewals | Number of technology assets renewed or improved | Number | 447 | 450 | -3 | The technology renewals plan of 450 was comprised of 58 schemes. Of the 447 delivered; - 163 were delivered on non-technology renewals PIT schemes - 175 were delivered on 'renewal of technology" schemes on simple single output schemes - 109 were delivered on 'renewal of technology" schemes on complex multi-output schemes Motorway Comms Equipment and Technology Renewals expenditure is captured as a single PIT. Spend on this PIT was 31% below plan but delivery was contributed heavily by non-technology renewals PIT schemes and a large proportion of the 'renewal of technology' PIT schemes were multi-output.

## IP5
Statement IP5: Maintenance Delivery Reporting
This statement details National Highways' 2022-23 performance against a set of key maintenance activity measures. They represent a combination of planned, cyclical and reactive maintenance activities. The purpose of the statement is to provide supplementary reporting and assurance, in addition to the asset KPI’s and PI’s, that Highways England is keeping the network in good condition and meeting the requirements of the Licence to operate a safe and serviceable network.
Activity | Type | % Completed 24 Hour Priority Defects within the required timescale | % Completed within the required timescale | Comments
Defects | Drainage Asset Defects/Service Duct Defects (AD Areas) | 84.2% | 62.5% | On defects management, as more areas transition to Asset Delivery, we have seen an increase in the number of defects reported. We continue to focus our attention placed on defects resolution and the improved consistency in reporting across regions. Addressing Geotechnical asset defects rose from 94% to 100% and Soft Estate/Landscape defects increased from 85% to 89%.
| Fences/Walls Defects | 91% | 86.1%
| Geotechnical asset defects (AD Areas) | None reported | 100%
| Lighting defects | 80.9% | 78.3%
| Pavements/Paved area defects | 85.6% | 85.7%
| Road restraint systems defects | 93.9% | 85.3%
| Soft estate landscape defects (AD Areas) | 86.9% | 88.9%
| Structure defects (AD Areas) | None reported | 90.2%
| Sweeping and cleaning - (including offensive and non-offensive graffiti) | 83% | 86.9%
| Traffic signs/Road markings/Road studs defects | 89.6% | 84.8%
Activity | Type | % completed |  | Comments
Winter Service | The percentage of precautionary salting delivered within the precautionary salting and turnaround time as stated within the Severe Weather Plan | 99.7% |  | Consistent performance in salting throughout the year for all regions and nationally.
| Percentage of instances where running lanes were available in accordance with the Service Provider Severe Weather Plan in relation to snow clearance. | 99.9% |  | Consistent strong performance throughout the year for all regions and nationally.
Activity | Type | % of total catchment length with a low risk status |  | Comments
Drainage | Drainage Performance Indicator | 71.2% |  | Stable performance throughout the year, starting the year at 72% and EOY at 71.2%.
Activity | Type | % of planned litter clearance completed |  | Comments
Litter | Percentage of planned litter clearance activities undertaken in accordance with ASC requirements or the accepted programme set out in ADAMr (AD) | 92.3% |  | Consistent performance throughout the year which was comparable to EOY 21-22 (92%)
Activity | Type | % of cyclic works completed |  | Comments
Cyclical Maintenance (AD Areas only) | Percentage of Cyclic works that are completed within the required timescales | 83% |  | Consistent performance throughout the year with an improvement compared to EOY 21-22 (79%) Work continues with regions to improve this metric
Activity | Type | % of <24hr reactive works completed |  | Comments
Reactive Maintenance (AD Areas only) | Percentage of Reactive <24hr works that are completed within the required timescales | 93.4% |  | Consistent performance throughout the year which was comparable to EOY 21-22 (93%)
Activity | Type | Total No of claims |  | Comments
Red Claims | Total number of claims | 2097 |  | The number of red claims received in 2022-23 has increased compared to 2021-22. We have seen a significant increase in the number of green claims in 2022-23 as we see more areas transition to asset delivery.
| Total number of settled claims | 419
Green Claims | Total number of claims | 8762
| Total number of settled claims | 6397
Activity | Type | % of programme completed |  | Comments
Planned Asset Condition Inspections | Structures | 96.5% |  | Operations have continued to work on completing the programme of inspections and ensuring inspections don’t become overdue. Structures inspections performance remains comparable with previous year’s performance, with 96.5% of the programme completed. A total of only 50 structures had inspections that are overdue due to access and possession issues.
| VRS | 90.9%
| Lighting | 76.7%
| Geotech | 88.4%
| Traffic Signs & Technology | 107.9%

## F1
F1: Total income and expenditure
£m | RP1 | 2020-21 | 2021-22 | 2022-23 |  |  | £m | Baseline
| Actual | Actual | Actual | FY Actual | Budget | Budget Difference |  | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | RIS2 Total
Operating expenditure | [6 empty] | Note - some activities are classified differently in this table compared to the Statement of Funds Available (SoFA).
Operations and Maintenance (B1, B2, B3) | 2403.4 | 537.9 | 505.5108 | 461.9844 | 419.5627 | -42.4216 | Operations & Maintenance (Opex) | 1033.8115 | 1014.019 | 1029.0107 | 1033.0546 | 1078.8259 | 5188.7217
Private Finance Initiative (PFI) payments (B5) | 2135.6 | 434.7 | 419.504 | 453.4848 | 458.6609 | 5.1761 | Operations & Maintenance (Capex) | 238 | 350 | 322 | 259 | 202 | 1371
Corporate Support (C1) | 799.4 | 133 | 149.1658 | 228.7338 | 215.3237 | -13.4102 | Renewals | 734 | 858 | 902 | 859 | 914 | 4267
Business Services (C2) |  | 44.9 | 39.0863 | 34.2528 | 43.7539 | 9.5011 | Enhancements | 2027 | 1773 | 1983 | 2228 | 2474 | 10485
Protocols (D1) | 240.4 | 55.5 | 63.463 | 65.8757 | 66.0988 | 0.22307 | Designated Funds | 162 | 150 | 165 | 232 | 247 | 956
Total resource expenditure | 5578.8 | 1206 | 1176.7299 | 1244.3315 | 1203.4 | -40.9315 | RP3 preparation and development | 20 | 70 | 130 | 180 | 143 | 543
Capital expenditure | [6 empty] | How we run our business (Opex) | 166.7885 | 146.011 | 162.3893 | 171.1289 | 173.6741 | 819.9918
RIS1 Enhancements (A1) | 7059.5 | 1727.2 | 1346.6938 | 1171.3817 | 1441.8155 | 270.4338 | How we run our business (Capex) | 76 | 85 | 66 | 66 | 85 | 378
RIS 2 Enhancements (A2) |  | 292.5 | 421.7444 | 491.3379 | 507.1704 | 15.8325 | Total | 4457.6 | 4446.03 | 4759.4 | 5028.1835 | 5317.5 | 24008.7135
RIS3 Development (A3) | X | 21.3 | 54.6631 | 63.5587 | 104.5827 | 41.0241
Designated Funds (A4) | X | 162.5 | 123.318 | 148.3274 | 164.7419 | 16.4145 | Note: As agreed with the government this plan was originally £27,358m as set out in the RIS and which was re-profiled in Spending Review 2020 as well as including additional funding (£146m) for the acceleration of the A66 as part of Project Speed. The funding profile and total £24,009m has been amended to reflect the outcome of the (SR21) 2021 Spending Review as confirmed in the government’s Autumn Budget. The Enhancements total post SR21 funding has been re-categorised from £10,535m to £10,485m with a project now being shown in RP3 preparation and development and the moveable barrier on the M20 being shown in Enhancements (from Operations and Maintenance capex). The split of spending between years and categories is subject to change within the total RIS funding, remaining at £24,009m,. These changes include an agreed transfer of £100m from capex funding to opex in 2023-24. A similar transfer of £100m of capex to opex funding has been requested for 2024-25. We were allocated additional funding of £49m during 2020-21 to 2020-24 for deliverables outside the scope of RIS2 such as the Historical Rail Estate (HRE) and Operation Brock. Additional funding will be agreed during 2023-24 for these items. These amounts are not included in the table above which captures the funding within the scope of RIS2 only.
Other capital expenditure (A5) | X | 35.7 | 8.8526 | 17.9997 | 25.8092 | 7.8095
Operations (B1, B2) | X | 187.9 | 222.302 | 233.442 | 274 | 40.558
Maintenance and Renewals (B3) | 3494 | 759.6 | 881.0926 | 911.2054 | 925.6327 | 14.4273
Business Costs (C1, C2) | X | 109.2 | 126.8408 | 173.4205 | 126.8553 | -46.5652
Total capital expenditure | 12160.3637 | 3295.9 | 3185.5073 | 3210.5732 | 3570.6078 | 359.9346
Total expenditure | 17739.1652 | 4501.9 | 4362.2372 | 4454.9047 | 4774.0078 | 319.0031
Resource Expenditure by Type
Income | -182.2 | -47.2 | -60.5743 | -56.2145 | -33.7635 | 22.451
Pay | 668.9 | 161.4 | 154.0543 | 159.9065 | 165.7346 | 5.8282
Non-Pay | 314.45 | -41.6 | -37.8618 | -41.8659 | -48.7784 | -6.9125
Projects | 4777.65 | 1133.4 | 1121.1003 | 1182.5054 | 1120.2073 | -62.2982
Total resource expenditure | 5578.8 | 1206 | 1176.7185 | 1244.3315 | 1203.4 | -40.9315
Commentary:
We have ended the financial year successfully, in line with the final funding agreed with the Department for Transport. On capital, our full year outturn of £3,211million is within £2million (0.1%) of the revised funding agreed as part of HMT’s supplementary estimate process at P7. Of the £358m variance against the original budget, £357m of that represents the 10% flex we agreed with the department to move into future years. Operational costs were 1% (£9m) overspent against the revised funding of £1,235m agreed at P7 with the Department, and £41m overspent against the original budget. We have ended the financial year successfully, in line with the final funding agreed with the Department for Transport. On capital, our full year outturn of £3,211million is within £2million (0.1%) of the revised funding agreed as part of HMT’s supplementary estimate process at P7. Of the £358m variance against the original budget, £357m of that represents the 10% flex we agreed with the department to move into future years. Operational costs were 1% (£9m) overspent against the revised funding of £1,235m agreed at P7 with the Department, and £41m overspent against the original budget.

## F2
F2: Regional operating income and expenditure
£m | 2020-21 | 2021-22 | 2022-23
| Actual | Actual | FY Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
Centrally managed | 136.8 | 110.8924 | 56.2812 | 33.9495 | -22.3317
East | 59.4 | 59.0371 | 62.6496 | 58.7794 | -3.8702
Midlands | 97.4 | 94.4202 | 96.3081 | 91.9589 | -4.3491
North West | 73.7 | 72.2356 | 62.5167 | 63.3948 | 0.878
South East | 75.4 | 71.5382 | 79.8242 | 71.9875 | -7.8367
South West | 46.5 | 44.0986 | 46.7511 | 45.1298 | -1.6214
Yorkshire & North East | 48.6 | 53.2887 | 57.6534 | 54.3628 | -3.2906
Subtotal | 537.9 | 505.5108 | 461.9844 | 419.5627 | -42.4216
Private Finance Initiative (PFI) payments (B5)
Centrally managed | -116 | -84.7159 | -91.9984 | -91.999 | -0.00056532
East | 64.8 | 58.9324 | 65.6692 | 66.3812 | 0.71208
Midlands | 11.1 | 10.9116 | 12.209 | 11.31 | -0.89895
North West | 0 | 0 | 0 | 0 | 0
South East | 303.2 | 308.8152 | 329.1405 | 336.389 | 7.2485
South West | 28.2 | 23.0648 | 21.6117 | 23.114 | 1.5023
Yorkshire & North East | 143.2 | 102.4958 | 116.853 | 113.4657 | -3.3873
Subtotal | 434.7 | 419.504 | 453.4848 | 458.6609 | 5.1761
Corporate Support (C1)
Centrally managed | 127.2 | 142.207 | 223.1516 | 215.3237 | -7.8279
East | 0 | 0.019178 | 0.048781 | 0 | -0.048781
Midlands | 0 | 0.014612 | 0.035557 | 0 | -0.035557
North West | 0 | 0.0020183 | -0.0044703 | 0 | 0.0044703
South East | 5.7 | 6.9139 | 5.5024 | 0 | -5.5024
South West | 0 | 0 | 0 | 0 | 0
Yorkshire & North East | 0 | 0.0068448 | 0 | 0 | 0
Subtotal | 133 | 149.1636 | 228.7338 | 215.3237 | -13.4102
Business Services (C2)
Centrally managed | 44.9 | 38.9513 | 34.0356 | 43.7735 | 9.7379
East | 0 | 0.001553 | 0 | 0 | 0
Midlands | 0 | 0.0053641 | 0.0050717 | 0 | -0.0050717
North West | 0 | 0.033617 | 0 | 0 | 0
South East | 0 | 0.000793 | 0.21214 | -0.019599 | -0.23174
South West | 0 | 0.093024 | 0 | 0 | 0
Yorkshire & North East | 0 | 0.000709 | 0 | 0 | 0
Subtotal | 44.9 | 39.0863 | 34.2528 | 43.7539 | 9.5011
Protocols (D1)
Centrally managed | 32 | 39.157 | 44.8425 | 45.4156 | 0.57307
East | 0 | 0 | 0 | 0 | 0
Midlands | 0.1 | 0.055872 | 0.057 | 0.056994 | -6e-06
North West | 0 | 0 | 0 | 0 | 0
South East | 0 | 0 | 4.5e-05 | 0 | -4.5e-05
South West | 10.5 | 11.3974 | 11.8709 | 11.6208 | -0.2501
Yorkshire & North East | 13 | 12.853 | 9.1052 | 9.0053 | -0.099855
Subtotal | 55.5 | 63.4633 | 65.8757 | 66.0988 | 0.22307
Total | 1206 | 1176.728 | 1244.3315 | 1203.4 | -40.9315
Commentary:
In a year where we have experienced significant inflation costs across our business, our overall Operational costs were within 1% (£13million) of our revised funding envelope that we agreed with the Department in November. We entered the year with £19million (1.6%) over-programming. We balanced this pressure with savings generated from a prioritisation exercise which included a large contribution from Digital Services and more realistic workforce plan assumptions. As part of the Treasury’s Supplementary Estimate process in October, we negotiated additional £32millionIn a year where we have experienced significant inflation costs across our business, our overall Operational costs were within 1% (£13million) of our revised funding envelope that we agreed with the Department in November. We entered the year with £19million (1.6%) over-programming. We balanced this pressure with savings generated from a prioritisation exercise which included a large contribution from Digital Services and more realistic workforce plan assumptions. As part of the Treasury’s Supplementary Estimate process in October, we negotiated additional £32million funding from the Department to cover inflationary pressure on maintenance and index linked DBFO contracts (£20million); previously unfunded Operation Brock costs (£10million); and new scope for mobilising the RAPID charging fund project (£2million).

## F2.1
F2.1: Operating income and projects expenditure
£m |  | 2020-21 | 2021-22 | 2022-23
|  | Actual | Actual | FY Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
| Pay | 85.6 | 82.0347 | 88.2864 | 88.9642 | 0.67783
| Non-Pay | 12 | 20.1981 | 25.6795 | 24.0144 | -1.6651
| Income | -38.8 | -48.1309 | -43.1458 | -25.8164 | 17.3294
Non-projects | Non-projects Subtotal | 58.8 | 54.102 | 70.8201 | 87.1622 | 16.3421
Projects - Maintenance and Renewals | Routine Maintenance | 273.2 | 265.0861 | 271.2124 | 239.6007 | -31.6117
| Winter Maintenance | 3.7 | 2.5856 | 4.0995 | 2.3025 | -1.797
| Technology - Maintenance | 34.4 | 36.0021 | 19.5805 | 20.6667 | 1.0862
| Renewal of Roads | 1.5 | 1.5984 | 2.751 | 2.7908 | 0.039798
| Renewal of Structures | 9.1 | 8.0111 | 6.6783 | 7.5307 | 0.85235
| Other Maintenance | 2.8 | 1.3645 | 0.4318 | 0 | -0.4318
Projects - General Operations | S274/S278 Works | 15.6 | 19.8604 | 9.8988 | 0 | -9.8988
| Technology | 37.2 | 12.0002 | -4.0696 | 1.19 | 5.2596
| Other | 68.6 | 71.2095 | 60.0077 | 36.8292 | -23.1784
Projects - Customer Operations | Customer Operations | 32 | 33.6655 | 20.5739 | 21.49 | 0.91607
1.2
| Projects Subtotal | 479.1 | 451.3834 | 391.1644 | 332.4005 | -58.7638
| Total | 537.9 | 505.4854 | 461.9844 | 419.5627 | -42.4217
PFI (Private Finance Initiative)
| Pay | 0 | 0 | 0 | 0 | 0
| Non-Pay | -81.2 | -86.4323 | -91.9984 | -91.999 | -0.00056532
| Income | 0 | 0 | 0 | 0 | 0
Non-projects | Non-projects Subtotal | -81.2 | -86.4323 | -91.9984 | -91.999 | -0.00056532
Projects | A1(M) Darrington to Dishforth | 62 | 58.4076 | 23.5004 | 23.0043 | -0.49605
| A19 Dishforth to Tyne Tunnel | 71.1 | 28.9329 | 37.0223 | 37.0081 | -0.01423
| A249 Iwade to Queenborough | 14 | 13.6487 | 14.2947 | 14.3248 | 0.030052
| A30/A35 Exeter to Bere Regis | 9.6 | 9.753 | 9.1917 | 10.13 | 0.9383
| A419/A417 Swindon to Gloucester | 18.6 | 13.3118 | 12.42 | 12.984 | 0.56402
| A50/A564 Stoke - Derby link | 11.1 | 10.9116 | 12.209 | 11.31 | -0.89895
| A69 Carlisle to Newcastle | 11.5 | 11.6829 | 12.1138 | 11.5451 | -0.56866
| M1-A1 Yorkshire link | 22.8 | 23.826 | 26.4907 | 25.7703 | -0.72037
| M25 London Orbital Motorway contract | 289.2 | 295.1665 | 314.8457 | 322.0642 | 7.2185
| M40 Junctions 1-15 | 40.6 | 38.5789 | 42.1688 | 43.3769 | 1.2081
| Other | -34.8 | 1.7164 | 41.2262 | 39.1422 | -2.084
| Projects Subtotal | 515.9 | 505.9363 | 545.4832 | 550.6599 | 5.1767
| Total | 434.7 | 419.504 | 453.4848 | 458.6609 | 5.1761
Corporate Support (C1)
| Pay | 46.7 | 45.3657 | 50.2828 | 47.4143 | -2.8685
| Non-Pay | 36.8 | 38.6274 | 36.7271 | 30.8438 | -5.8833
| Income | -7.4 | -6.7682 | -10.6396 | -6.6771 | 3.9625
Non-projects | Non-projects Subtotal | 76.1 | 77.2249 | 76.3703 | 71.581 | -4.7893
Projects | Lands | 52.3 | 5.1538 | 5.8325 | 0 | -5.8325
| Other | 4.6 | 66.8305 | 146.5311 | 143.7427 | -2.7884
| Projects Subtotal | 56.9 | 71.9843 | 152.3636 | 143.7427 | -8.6209
| Total | 133 | 149.2092 | 228.7338 | 215.3237 | -13.4102
Business Services (C2)
| Pay | 22.7 | 20.2039 | 14.9 | 22.6 | 7.7
| Non-Pay | -9.4 | -10.3358 | -12.5 | -12.2 | 0.3
| Income | -0.6 | -4.7096 | -1.8 | -1 | 0.8
Non-projects | Non-projects Subtotal | 12.6 | 5.1584 | 0.6 | 9.4 | 8.7
Projects | Research and Development | 8.9 | 23.0347 | 13.1 | 12.9 | -0.2
| Other | 23.4 | 10.8939 | 20.551 | 21.5 | 0.949
| Projects Subtotal | 32.3 | 33.9286 | 33.651 | 34.4 | 0.749
| Total | 44.9 | 39.0869 | 34.251 | 43.8 | 9.549
Protocols (D1)
| Pay | 6.5 | 6.4501 | 6.4538 | 6.7879 | 0.33409
| Non-Pay | 0.2 | 0.080725 | 0.17867 | 0.55262 | 0.37395
| Income | -0.3 | -0.93558 | -0.66501 | -0.3 | 0.36501
Non-projects | Non-projects Subtotal | 6.4 | 5.5952 | 5.9675 | 7.0405 | 1.0731
Projects |  | 49.2 | 57.8678 | 59.9083 | 59.0582 | -0.85005
| Projects Subtotal | 49.2 | 57.8678 | 59.9083 | 59.0582 | -0.85005
| Total | 55.5 | 63.463 | 65.8757 | 66.0988 | 0.22301
| Total resource expenditure | 1206 | 1176.7485 | 1244.3298 | 1203.4461 | -40.8837

## F2.2
F2.2: Analysis of protocols expenditure
£m | 2020-21 | 2021-22 | 2022-23
| Actual | Actual | FY Actual | Budget | Budget Difference
Abnormal Loads | 0.8 | 1.5433 | 1.5873 | 1.7738 | 0.1865
Dart Charge | 25.1 | 27.792 | 32.7529 | 33.1579 | 0.40499
M6 Toll | 0.1 | 0.055872 | 0.057 | 0.056994 | -6e-06
Historical Railways Estate | 13 | 13.4371 | 9.1052 | 9.0053 | -0.099855
National Salt Reserve | 0.5 | 1.0628 | 1.0213 | 0.94868 | -0.072657
Severn Crossings | 14 | 17.4718 | 19.252 | 19.056 | -0.19596
Technical Regulations | 2.1 | 2.1 | 2.1 | 2.1 | 0
Total Protocols Expenditure | 55.5 | 63.463 | 65.8757 | 66.0988 | 0.22301

## F2.3
F2.3: Analysis of FTE
Directorates £m | 2020-21 | 2021-22 | 2022-23
| Actual | Actual | FY Actual | Budget | Budget Difference
Commercial and Procurement | 439.1 | 454.9911 | 442.7943 | 546 | 103.2057
* Customer, Strategy and Communications | 302.7 | 295.4405 | 346.487 | 376.6187 | 30.1317
Finance and Business Services | 374.4 | 362.3093 | 380.731 | 394.5662 | 13.8352
Human Resources | 109.3 | 111.5617 | 303.9748 | 261.428 | -42.5468
Major Projects | 784.5 | 814.6414 | 724.3913 | 830 | 105.6087
Lower Thames Crossing | 31.7 | 40 | 32 | 59 | 27
Operations | 3185.6 | 3261.2953 | 3512.0134 | 3647.8877 | 135.8743
Digital Services Directorate | 229.2 | 246.2567 | 332.9459 | 439.6446 | 106.6987
Safety, Engineering and Standards | 410.1 | 397.4244 | 365.8162 | 395.0171 | 29.2009
General Counsel | 43.2 | 51.6972 | 57.4015 | 61.45 | 4.0485
FTE Total | 5909.7 | 6035.5823 | 6498.5554 | 7011.6123 | 513.0569
Regions £m | 2020-21 | 2021-22 | 2022-23
| Actual | Actual | Actual | Budget | Budget Difference
Centrally managed | 2599.6 | 2486.5994 | 3281.3827 | 3657.2209 | 375.8382
East | 632.6 | 530.4172 | 499.8416 | 515.2351 | 15.3935
Midlands | 605.2 | 722.8375 | 701.7511 | 733.6132 | 31.8621
North West | 645.3 | 621.437 | 524.0113 | 557.5 | 33.4887
South East | 526.3 | 707.8174 | 669.4798 | 638.0794 | -31.4004
South West | 440.1 | 415.5052 | 185.7389 | 207.3473 | 21.6084
Yorkshire & North East | 460.5 | 550.9686 | 636.35 | 702.6164 | 66.2664
FTE Total | 5909.7 | 6035.5823 | 6498.5554 | 7011.6123 | 513.0569
* Note : Communications and Corporate Affairs and Strategy and Planning Directorate combined

## F3
F3: Capital Expenditure
£m |  | 2020-21 | 2021-22 | 2022-23
|  | Actual | Actual | FY Actual | Budget | Budget Difference
Maintenance and Renewals
| Renewal of Roads | 521.5 | 627.097 | 693.5729 | 651.0818 | -42.4911
| Renewal of Structures | 176.2 | 194.6982 | 177.8325 | 224.551 | 46.7185
| Renewal of Technology | 35.7 | 26.6715 | 39.8 | 50 | 10.2
| Maintenance | 26.2 | 32.626 | 0 | 0 | 0
| TOTAL Maintain/Renew | 759.5 | 881.0926 | 911.2054 | 925.6327 | 14.4273
RIS1 Enhancements
| RIP | 654.6 | 708.5863 | 887.6279 | 786.7174 | -100.9105
| SMP | 876.9 | 448.9327 | 266.1648 | 213.2874 | -52.8774
| CIP | 131.6 | 97.2045 | 61.6802 | 81.4449 | 19.7647
| Other RIS1 expenditure including Portfolio Risk/Contingency and Surpus Funding | 64.2 | 91.9703 | -44.0912 | 360.3658 | 404.4569
| Total RIS1 Enhancements | 1727.2 | 1346.6938 | 1171.3817 | 1441.8155 | 270.4338
RIS2 Enhancements
| RIP | 42 | 76.6949 | 129.1445 | 138.4622 | 9.3177
| SMP | 14.4 | 190.148 | 166.3948 | 195.2035 | 28.8086
| CIP | 0 | 9.7069 | 14.0814 | 10.7253 | -3.3561
| Lower Thames Crossing | 235 | 136.7288 | 167.593 | 129.2018 | -38.3912
| Other RIS2 expenditure including Portfolio Risk/Contingency | 1.1 | 8.4658 | 14.1242 | 33.5777 | 19.4535
| Total RIS2 Enhancements | 292.5 | 421.7444 | 491.3379 | 507.1704 | 15.8325
RIS3 Development
| RIS3 Development | 21.3 | 54.6631 | 63.5587 | 104.5827 | 41.0241
| Total RIS3 Development | 21.3 | 54.6631 | 63.5587 | 104.5827 | 41.0241
Designated Funds
| Environment and Wellbeing | 58.2 | 53.4041 | 69.2335 | 66.2408 | -2.9927
| Innovation and Modernisation | 39.1 | 22.5683 | 24.9096 | 54.7031 | 29.7935
| Safety and Congestion Fund | 33.6 | 18.7964 | 28.3576 | 18.1562 | -10.2015
| Users and Communities | 31.6 | 28.549 | 25.8267 | 25.6418 | -0.18486
| Total Designated Funds | 162.5 | 123.318 | 148.3274 | 164.7419 | 16.4145
Operations, Business Costs and Other Capital
| Operations | 187.9 | 222.302 | 233.442 | 274 | 40.558
| Business Costs | 109.2 | 126.8408 | 173.4205 | 126.8553 | -46.5652
| Other Capital | 35.7 | 8.8526 | 17.9997 | 25.8092 | 7.8095
| Total Operations, Business Costs, and Other Capital | 332.8 | 357.9954 | 424.8622 | 426.6645 | 1.8023

## F3.1
F3: Enhancement expenditure
£m | Scheme name | 2020-21 | 2021-22 | 2022-23
|  | Actual | Actual | FY Actual | Budget | Budget Difference
RIS1 Enhancements
| A1 Birtley to Coal House | 13.1193 | 42.8325 | 106.331 | 57.0333 | -49.2977
| A1 Morpeth to Ellingham and A1 North of Ellingham | 20.0692 | 16.7549 | 7.8475 | 27.1365 | 19.289
| A1 Scotswood to North Brunton | 33.2788 | 49.8229 | 14.5786 | 7.5805 | -6.998
| A12 Chelmsford to A120 | 32.31 | 37.5918 | 60.3924 | 61.9716 | 1.5792
| A14 Cambridge to Huntingdon | 84.804 | 48.0071 | 13.5988 | 14.2401 | 0.64124
| A19 Down Hill Lane | 14.9881 | 23.1712 | 2.3763 | 2.0493 | -0.327
| A19 Norton to Wynyard | 46.9885 | 6.5371 | -1.5558 | 0.70738 | 2.2632
| A19 Testos | 46.3598 | 15.9979 | -1.0126 | 1.1719 | 2.1845
| A2 Bean and Ebbsfleet | 24.3915 | 28.9161 | 5.5908 | 2.2024 | -3.3883
| A27 Arundel Bypass | 14.0271 | 26.9656 | 15.7626 | 21.8809 | 6.1183
| A27 East of Lewes Package | 14.7555 | 20.139 | 11.9698 | 5.8424 | -6.1274
| A30 Chiverton to Carland Cross | 43.2388 | 73.4245 | 133.4067 | 86.7955 | -46.6112
| A303 Amesbury to Berwick Down | 26.2264 | 21.1565 | 13.8143 | 7.2034 | -6.6108
| A303 Sparkford to Ilchester | 8.624 | 15.1186 | 42.7117 | 48.0593 | 5.3477
| A31 Ringwood | 2.741 | 8.5525 | 14.4178 | 10.76 | -3.6578
| A34 Newbury to Oxford Enhancements | 0.86328 | 3.6814 | -0.016413 | 0 | 0.016413
| A358 Taunton to Southfields | 7.7588 | 18.3118 | 18.167 | 19.1468 | 0.97975
| A38 Derby Junctions | 11.2493 | 8.1463 | 6.5419 | 14.0742 | 7.5322
| A428 Black Cat to Caxton Gibbet | 24.9242 | 28.0409 | 34.2593 | 60.0014 | 25.7422
| A45/A6 Chowns Mill Junction | 13.7 | 10.609 | -0.027993 | 0 | 0.027993
| A46 Coventry Junctions Binley | 16.0239 | 33.289 | 17.6874 | 6.2358 | -11.4516
| A47 Blofield to North Burlingham | 4.0033 | 5.0794 | 8.5867 | 16.9213 | 8.3345
| A47 Guyhirn Junction | 4.38 | 6.2974 | 1.798 | 0.54252 | -1.2554
| A47 North Tuddenham to Easton | 7.7071 | 6.8728 | 14.2131 | 18.0814 | 3.8683
| A47 Thickthorn Junction | 3.2825 | 5.5227 | 7.4352 | 12.3096 | 4.8744
| A47 Wansford to Sutton | 2.9343 | 3.1544 | 8.6797 | 13.9025 | 5.2228
| A500 Etruria | 1.0972 | 0.58599 | 0.00046592 | 0.32257 | 0.32211
| A5036 Princess Way | 1.3444 | 1.1738 | 1.9028 | 7.8954 | 5.9926
| A52 Nottingham Junctions | 1.9943 | 4.8 | 9.6279 | 7.6878 | -1.9401
| A585 Windy Harbour to Skippool | 23.564 | 46.3471 | 48.9274 | 33.2643 | -15.6631
| A61 Westwood Roundabout | 13.6425 | 1.6883 | 1.952 | 1.1825 | -0.7695
| A63 Castle Street | 48.5344 | 52.1836 | 62.5644 | 69.7217 | 7.1573
| M1 Junctions 13-19 | 165.8621 | 82.9244 | 2.373 | 18.2954 | 15.9224
| M2 Junction 5 | 4.0936 | 8.1038 | 35.7145 | 27.623 | -8.0915
| M25 Junction 10 | 13.4572 | 6.1864 | 38.6661 | 45.155 | 6.489
| M25 Junction 25 | 3.8785 | 11.3373 | 3.3945 | 2.3172 | -1.0773
| M25 Junction 28 | 6.5705 | 7.0508 | 31.2656 | 20.6778 | -10.5878
| M25 Junctions 10-16 | 5.1074 | 9.4549 | 0.04237 | 0.044476 | 0.0021062
| M27 Junctions 4-11 | 125.7276 | 50.3682 | -2.5166 | 3.5093 | 6.0259
| M27 Southampton Junction 8 | 1.7206 | 2.862 | 0.72447 | 0.59563 | -0.12884
| M3 Junction 9 | 5.0213 | 4.7007 | 7.7559 | 10.4255 | 2.6696
| M3 Junctions 9-14 | 9.8587 | 25.56 | 40.0105 | 37.8729 | -2.1376
| M4 Junctions 3-12 | 329.8769 | 156.5455 | 41.4439 | 20.3314 | -21.1125
| M40/M42 Interchange | 4.7979 | 11.3446 | 16.5683 | 16.8397 | 0.27145
| M42 Junction 6 | 23.7923 | 44.7778 | 76.8814 | 68.025 | -8.8564
| M54-M6 Link Road | 7.8346 | 8.0531 | 6.4983 | 12.8058 | 6.3075
| M56 Junctions 6-8 | 18.1315 | 32.8062 | 29.3999 | 15.9357 | -13.4642
| M6 Junction 10 | 14.7413 | 19.5 | 18.1575 | 2.349 | -15.8085
| M6 Junction 19 | 26.0602 | 12.56 | 4.9763 | 0.69202 | -4.2843
| M6 Junctions 13-15 | 97.7331 | 6.3389 | 1.7175 | 2.5219 | 0.80436
| M6 Junctions 21a-26 | 10.815 | 59.8081 | 113.4715 | 94.7955 | -18.676
| M62 Junctions 20-25 | 8.1442 | 11.5581 | 13.1777 | 11.7049 | -1.4728
| M621 Junctions 1-7 | 2.9102 | 2.0822 | 16.4195 | 12.113 | -4.3065
| Mottram Moor Link Road & A57 Link Road | 5.7936 | 9.3326 | 8.2761 | 9.2596 | 0.98348
| A47 Great Yarmouth Junctions | 0.092442 | 1.542 | 4.8988 | 3.042 | -1.8568
| Other RIS1 expenditure | 222.0569 | 91.1238 | -20.4641 | 368.9591 | 389.4232
| Total RIS1 Enhancements | 1727.2492 | 1346.6938 | 1171.3817 | 1441.8155 | 270.4338
RIS2 Enhancements
| A46 Newark Bypass | 1.1863 | 4.0551 | 19.6806 | 14.5805 | -5.1002
| A27 Worthing and Lancing improvements | 0.2584 | 0 | 0.91419 | 0.87012 | -0.044066
| A417 Air Balloon | 17.858 | 15.7419 | 27.3115 | 33.8083 | 6.4968
| M60/M62/M66 Simister Island Interchange | 1.2501 | 6.071 | 8.0499 | 8.0174 | -0.03252
| Lower Thames Crossing | 234.9985 | 136.7288 | 167.593 | 129.2018 | -38.3912
| A66 Northern Trans-Pennine | 13.7437 | 42.3108 | 66.7643 | 70.9443 | 4.18
| M4 Junctions 19-20 and M5 Junctions 16-17 | 0.15683 | 2.0437 | 5.442 | 11.2747 | 5.8327
| M42 Junctions 4-7 | 0.21848 | 0.79589 | 1.4596 | 2.5593 | 1.0997
| M6 Junctions 4-5 | 0.37552 | 4.4489 | 16.709 | 15.3853 | -1.3237
| M6 Junctions 5-8 | 0.26256 | 1.2269 | 3.2294 | 4.9014 | 1.672
| M6 Junctions 8-10a | 0.17451 | 2.202 | 2.007 | 13.8946 | 11.8875
| M62 Junctions 25-30 | 0.2178 | 3.7966 | 19.912 | 24.4593 | 4.5474
| M1 J10-13 DHS to ALR upgrade | 0.2 | 1.4476 | 5.2209 | 18.9638 | 13.7428
| A21 Safety Package | 0 | 0.090804 | 1.3075 | 3.58 | 2.2725
| Other RIS2 expenditure | 21.9 | 200.7842 | 145.7058 | 154.7097 | 9.0039
| Total RIS2 Enhancements | 292.4545 | 421.7444 | 491.3067 | 507.1504 | 15.8438

## F3.2
F3.2: Regional capital income and expenditure
£m | 2020-21 | 2021-22 | 2022-23
| Actual | Actual | FY Actual | Budget | Budget Difference
Maintenance & Renewals
Centrally managed | 18.5 | 29.7423 | 36.9914 | 44.5 | 7.5086
East | 128.5 | 246.0127 | 219.8337 | 203.8176 | -16.0161
Midlands | 164.7 | 132.2056 | 178.9868 | 189.312 | 10.3252
North West | 130.7 | 136.1097 | 140.621 | 131.1333 | -9.4878
South East | 112.9 | 118.3229 | 115.6459 | 139.7697 | 24.1238
South West | 95.2 | 99.7892 | 90.4147 | 88.111 | -2.3037
Yorkshire & North East | 109 | 118.9058 | 128.6752 | 129.0035 | 0.32826
Subtotal | 759.5 | 881.0882 | 911.1688 | 925.6471 | 14.3783
RIS1 Enhancements
Centrally managed | 5.3 | 83.402 | -38.0276 | 348.4034 | 386.4309
East | 178.7 | 142.0884 | 138.5159 | 180.7836 | 42.2677
Midlands | 375.5 | 212.1912 | 160.4749 | 154.7405 | -5.7344
North West | 157.2 | 165.9784 | 212.4152 | 166.8435 | -45.5717
South East | 648.6 | 379.6689 | 265.8951 | 234.1805 | -31.7146
South West | 102 | 135.2353 | 209.0607 | 162.8599 | -46.2009
Yorkshire & North East | 260.1 | 228.1296 | 223.0473 | 194.0041 | -29.0432
Subtotal | 1727.2 | 1346.6938 | 1171.3817 | 1441.8155 | 270.4338
RIS2 Enhancements
Centrally managed | 13.8 | 118.0645 | 234.9678 | 284.5141 | 49.5463
East | 6.5 | 5.8983 | 1.5784 | 5.9761 | 4.3977
Midlands | 2.5 | 44.5394 | 58.6891 | 77.3413 | 18.6522
North West | 14.9 | 48.3439 | 27.9619 | 32.4767 | 4.5149
South East | 235.4 | 182.6014 | 72.5645 | 2.1097 | -70.4547
South West | 19 | 17.7856 | 27.3115 | 33.8083 | 6.4968
Yorkshire & North East | 0.4 | 4.5113 | 68.2649 | 70.9443 | 2.6794
Subtotal | 292.5 | 421.7444 | 491.3379 | 507.1704 | 15.8325
RIS3 Development
Centrally managed | 6 | 24.1926 | 35.206 | 56.0987 | 20.8928
East | 0 | 0 | 0 | 0 | 0
Midlands | 0.8 | 5.4039 | 4.8059 | 7.7949 | 2.989
North West | 5 | 1.6688 | 4.1822 | 10.0792 | 5.897
South East | 5.9 | 17.4762 | 15.1915 | 25.0969 | 9.9055
South West | 1.2 | 1.1829 | 0.7679 | 0.65852 | -0.10938
Yorkshire & North East | 2.4 | 4.7387 | 3.4052 | 4.8544 | 1.4492
Subtotal | 21.3 | 54.6631 | 63.5587 | 104.5827 | 41.0241
Designated Funds
Centrally managed | 58.5 | 34.3032 | 68.0701 | 98.8003 | 30.7302
East | 9.8 | 10.0223 | 22.0796 | 17.6674 | -4.4121
Midlands | 10 | 19.4712 | 7.2757 | 6.0683 | -1.2075
North West | 15 | 13.1942 | 14.6208 | 8.0352 | -6.5856
South East | 27.1 | 20.1025 | 19.6158 | 18.1323 | -1.4835
South West | 22.5 | 19.3547 | 11.3596 | 9.1714 | -2.1882
Yorkshire & North East | 19.6 | 6.8699 | 5.3058 | 6.867 | 1.5612
Subtotal | 162.5 | 123.318 | 148.3274 | 164.7419 | 16.4145
Operations, Business Costs, and Other Capital Expenditure
Centrally managed | 260.6 | 308.4586 | 366.442 | 358.2 | -8.242
East | 4.4 | 5.2847 | 7.2437 | 7.459 | 0.21529
Midlands | 7.4 | 5.5051 | 6.6616 | 5.5694 | -1.0923
North West | 7.0 | 9.8427 | 9.0107 | 10.3441 | 1.3334
South East | 44.7 | 19.2805 | 26.4014 | 33.3508 | 6.9494
South West | 3.5 | 3.2998 | 3.7215 | 4.4359 | 0.71442
Yorkshire & North East | 5.2 | 6.3241 | 5.373 | 7.3255 | 1.9525
Subtotal | 332.8 | 357.9954 | 424.8539 | 426.6846 | 1.8308
Total | 3,295.8 | 3185.5029 | 3210.6283 | 3570.6423 | 359.914
Commentary:
At the start of 2022-23, our capital business plan contained £438million less delivery than the Spending Review 2021 had provided funding for. This funding mismatch arose due to delays in Development Consent Order approvals, together with scope changes following the Transport Select Committee’s report on smart motorways. We informed the Department from the outset that we would seek to move £357million of this funding into years 4 and 5 of RP2, as we are able to ‘flex’ 10% of budget from one year to the next. Having reviewed the portfolio in the first quarter, we forecast to spend the remaining £81million of headroom (difference between opening £438m headroom and our £357m 10% flex limit) on our enhancements programme, reflecting acceleration of activity to de-risk project delivery and account for emerging cost pressures. This meant that we agreed a revised funding of £3,213million as part of the Treasury’s Supplementary Estimate process at the end of October 2022 (P7). Our full year outturn of £3,211million is within £2million (0.1%) of the revised funding envelope. In achieving this we have balanced delivery risks and opportunities.
Note on A52: Rowlands, Charlotte: Corporate Support, Business Services, Other Capital, Operate General, Support General